TERMS OF REFERENCE

for

Expert for Provision of Technical Assistance for improving the quality assurance system for primary & secondary education in the Republic of North Macedonia

- Background of the Project

The Primary Education Improvement Project (PEIP) is being implemented by the Ministry of Education and Science of the Republic of North Macedonia (MoES) and will support the Government and the MoES to invest more, and more effectively, in the quality of teaching and learning in primary education as well as  improve the conditions for learning in primary education. The project will be implemented country-wide, in urban, peri-urban and rural locations across the county. The PEIP project will be organized around three main elements that need to be aligned in order to be complementary to each other. Two are system-level reforms regarding the development  of a comprehensive national assessment program and enhancing competences of teachers, multi professional support teams and school leaders that would create the necessary enabling conditions, so the school teams are empowered with data on learning and up-to-date training. The third focuses on school-level interventions. Additionally, the PEIP project would strengthen sector management, project management and monitoring & evaluation.

Specific information/background regarding the assignment

School self-evaluation and integral evaluation have emerged as a key mechanisms to support school development in the recent decades. With an increased decentralisation in North Macedonia over the past decade (primary schools are “owned” by the municipality, including the appointment of principals, payment of salaries etc.), schools have greater responsibility for student outcomes, and more latitude to tailor responses appropriate for the school’s own context.

State Education Inspectorate (SEI), is a government agency, which leads and supports regular external and internal school evaluations in North Macedonia. The purpose of school evaluation is to help schools improve their practices and keep them accountable for the quality of the education that they provide to their students. North Macedonia has a school evaluation framework that covers seven key areas that are important for an effective school evaluation system. However, this framework has not been fully implemented or appropriated by stakeholders. Both external and self-evaluation focus largely on complying with the framework, rather than encouraging a culture of reflection and improvement in schools. Fundamentally, this reflects a disconnection between the aims of the framework – to enhance school quality and school-led improvement - and the perception of evaluation among inspectors and schools as an administrative requirement. This is exacerbated by a useful, yet complicated evaluation framework, which inspectors and schools find difficult to apply, and by the lack of support given to schools on how to use evaluation results to inform improvement efforts. At the school level, evaluation is a valued process but encourages schools to focus on procedural compliance, rather than critically reviewing how their learning environment is supporting students to develop their knowledge and skills.

School self-evaluation can lead to greater sensitivity about areas in need of improvement, it is found to lead to more frequent and open consultation about the quality of education and more classroom visits by the school leader. The process of school self-evaluation allows teachers to develop a perspective beyond their own classroom, particularly when they are involved in decision-making. School self-evaluation is an diagnostic approach of school needs, weaknesses and strengths followed by action for improvement which in the case of North Macedonia is the so called “Development Plan “  aka School Improvement Plan  (SIP ).

The system is set up in a way where the school performs the self-evaluation every 2 years, and based on the results of the pre-defined indicators, compiles the SIP which is a road-map for overcoming the deficiencies identified in the self-evaluation. The SIP is drafted thru an inclusive procedure, taking into consideration the opinions of the school staff as well as the local community, parents, students and other relevant stakeholders. Promoting SIPs as a key instrument to improve student learning outcomes implies a new vision for the role of the school, the school team (that is, school leaders, teachers, and the MPSTs), and the school community. Building on the schools’ preexisting level of decision-making autonomy, they would be expected to work together to improve student learning outcomes.

- Objective of the assignment

The main objective of the consultancy is to provide technical assistance and support the MOES and SEI in improving the quality assurance system (school self-evaluation and integral evaluation with focus on follow up evaluation as the most weak component of quality assurance process), existing School Performance Quality Indicators (SPQI) framework and bylaws for conducting school self-evaluation and school integral evaluation (revision of the quality performance indicators and fields of school assessment and all related bylaws)  in order to modernize and synchronize the self-evaluation and the integral evaluation systems as well as provide advice for improving the SIP scheme, logistic and expert support in providing training (with focus on self-evaluation, integral evaluation, follow up evaluation report writing) for key players (school principals and key staff, SEI inspectors, school board members, municipality officials) in order to ensure uniformity in understanding of the SPQI framework as well as raise awareness about the importance of the quality improvement culture. The school improvement cycle that currently exists should be revised to ensure that the schools’ decision-making autonomy is harnessed towards school improvement and school teams can clearly identify the benefit from the self-evaluation and production of SIPs. The SIPs produced must convincingly demonstrate ways to improve student-learning outcomes, entitling some schools to receive grants to implement their ideas.

- Scope of work

The selected international consultant should work closely with the MoES & SEI in order to perform a comprehensive review of the school quality assurance mechanisms and practices, and improving the efficiency and administrative capacity of SEI and Scholl management teams.

The consultant is expected to perform the following activities:

Activity 1:  Inception Phase (Preparatory activities) - The Consultant is expected to:

- Review all documentation related to the assignment, including the existing framework documents, laws, bylaws, existing strategic materials, reports on school integral evaluation, annual reports on conducted school integral evaluation,  background reports conducted in the country (OSCE and UNICEF reports, 2019), and all additional existing materials pointed out by the MoES or the SEI for the purpose of improving the quality assurance framework relevant for the assignment;

- Develop the work plan, with clear timelines and responsibilities, including the identification of key milestones connected to possible legislative interventions that need to be done in order to perform any of the tasks envisaged in the plan.

- Present and discuss the work plan and initial findings with MoES, SEI, other relevant stakeholders and agree on the next steps.

Activity 2: Improvement of the self-evaluation & integral evaluation framework and quality assurance indicators

Consultant shall work together with SEI & working groups on the:

- Review of the self-evaluation framework and schools’ experience of self-evaluation and proposing new and updated indicators for ensuring the creation of environment that will allow increased quality of teaching and learning,

- Review of the integral evaluation framework , proposing new and updated indicators and ensuring their alignment with the changes and the purpose of the self-evaluation framework;

- Review of the follow up evaluation as the most weak component of quality assurance process and propose revision of the school improvement cycle that currently exists to ensure that the schools’ decision-making autonomy is harnessed towards school improvement and school teams can clearly identify the benefit from the self-evaluation and production of SIPs;

- Prepare clear guidelines for the execution of both evaluations for the end users;

- Prepare clear guidelines for writing clear integral evaluation reports for SEI inspectors;

- Organize consultative meeting with SEI working groups and with key stakeholders representatives;

- Propose additional support and/or harmonization of other legislation related to the task.

Activity 3: Improvement of the SIP (Development plan) and strengthening its role

- Review of the current format of the SIP and, identify possible deficiencies of the current plan and areas form improvement in consultation  process with the all relevant stakeholders;

- Propose changes to the current plan and propose mechanisms for increasing the relevancy of the SIP and its role in the quality assurance scheme as well as ensuring active participation and engagement of local communities via their school board. The SIPs produced must convincingly demonstrate ways to improve student learning outcomes;

- Preparation of clear guidelines for the preparation of the SIP for all relevant stakeholders that will be involved in its preparation.

Activity 4: Improving the efficiency & administrative capacity of SEI

- Conduct a functional analysis of SEI and identify possible deficiencies and area for improvement

- Propose new or adjust current organizational structure and job description of SEI, based on the findings from the functional analysis

- Conduct an analysis of all business processes and business workflows of SEI operations for the purposes of Document Management System (DMS) implementation.

Activity 5: Develop and prepare training program for different stakeholder groups

The Consultant shall design and deliver a set of training programs and courses, training materials and manuals for all different newly developed outputs and for all different stakeholder groups.

- Training of the MoES and SEI staff as well as school principals and key actors, covering all aspects of the introduction of the improved self-evaluation framework with a focus on explaining the purpose of school evaluation and developing key evaluation competencies, (up to 310 participants)

- Training of the MoES and SEI staff as well as school principals and key actors, covering all aspects of the introduction of the improved integral - evaluation framework with a focus on explaining the purpose of integral evaluation and developing key evaluation competencies, (up to 310 participants)

- Training of the SEI inspectors on report writing (clear, specific and actionable evaluation reports delivering constructive feedback to schools)  (up to 60  participants)

- Training of the MoES and SEI staff as well as school management board in preparation of the School Improvement Plan based on the results and the indicators of the evaluations (up to 810 participants)

The Consultant in close cooperation with the SEI and MoES shall prepare a plan for the training workshops in order to ensure high quality delivery of the training focused on the improving the teaching- learning process in the classroom.

- Reporting obligations and deliverables

- Inception report outlining the process of the review of documentation, including the agreed  work plan, key milestones connected to possible legislative interventions and proposed texts of legislative interventions in order to ensure the execution of the tasks

- Report related to the activities connected to the improvement of the self-evaluation & integral evaluation matrix and indicators, including the overview of the process, the new and improved evaluation frameworks, as well as clear guidelines for the execution of both evaluations for the end users

- Report related to the actives connected to the review of the current format of the SIP, mechanisms for ensuring active participation and engagement of local communities in its preparation as well as set of clear guidelines for the preparation of the new SIPs for all relevant stakeholders that will be involved in its preparation

- Functional analysis of the SEI and recommendation for improvement, including new organizational structure and job description of SEI, based on the findings from the functional analysis

- Report of all business processes and business workflows of SEI inspectors for the purposes of the  implementation of Document Management System (DMS)

- Comprehensive reports on delivered trainings and workshops (including but not limited on: training program, plan and training materials and manuals) for all different target groups:

- training of the MoES and SEI staff as well as school management team, covering all aspects of the introduction of the improved self-evaluation framework,

- training of the MoES and SEI staff as well as school management team, covering all aspects of the introduction of the improved integral-evaluation framework;

- training of the MoES and SEI staff as well as school management board in preparation of the School Improvement Plan,

All deliverables shall be prepared in English and Macedonian and will be reviewed and approved by the SEI director, Minister of education and Project Director.

- Minimum Qualifications

- Advanced university degree in education, human development, public policy, sociology or other social science field;

- Minimum of 8 years of relevant work experience in the field of educational policies, which includes provision of consultancy and technical advice services to public institutions related to quality assessment and evaluation in education;

- At least 6 years of proven experience in the field of quality assurance in education (with focus on primary and secondary education), including development and implementation of the comprehensive quality assurance system (school self-evaluation, external evaluation (including inspection), evaluation of teachers and school leaders and student assessments;

- Demonstrated experience and knowledge in research approaches and methods;

- Previous experience in organizing and implementing large scale trainings for public servants, government officials;

- Proven analytical skills and ability to work with others to develop strategy into action and communicating and influencing this to a wider audience;

- Previous work experience in Western Balkan countries would be an advantage

- Excellent English writing ability and verbal skills for project proposals, reports, and communications,

- Procurement and Contract arrangements

The contract for this assignment will be until 27 February 2026. Expected start of services is October 2021. The Consultant is expected to work in the Republic of North Macedonia during the missions and must be able to travel to North Macedonia as needed.  The contract will be on lump sum basis, and payments will be based on deliverables as per agreed schedule.