PRIMARY EDUCATION IMPROVEMENT PROJECT

TERMS OF REFERENCE

for Design of Tutoring Program and Grant Program to Support Implementation of Tutoring Activities in the Primary Schools

- Background of the Project

The Primary Education Improvement Project (PEIP) will be implemented by the Ministry of Education and Science of the Republic of North Macedonia (MoES) and will improve conditions for learning in primary education. The project will be implemented country-wide, in urban, peri-urban and rural locations across the county. North Macedonia has recently undertaken important reforms of the preschool education and care system. To capitalize further on this important investment, the overall project will support the Government of the Republic of North Macedonia’s (MoES) to invest more, and more effectively, in the quality of teaching and learning in primary education. The PEIP project will be organized around three main elements that need to be aligned in order to be complementary to each other. Two are system-level reforms regarding the development  of a comprehensive national assessment program and enhancing competences of teachers, multi professional support teams and school leaders that would create the necessary enabling conditions, so the school teams are empowered with data on learning and up-to-date training. The third focuses on school-level interventions. Additionally, the PEIP project would strengthen sector management, project management and monitoring & evaluation.

Specific information/background regarding the assignment

North Macedonia’s Human Capital Index is lower than the average for its region and income group. Poor educational outcomes largely explain this loss of lifetime productivity. Children in North Macedonia can expect to complete 11 years of preprimary, primary, and secondary school by age 18. However, when years of schooling are adjusted for quality of learning, the result is equivalent to 7.3 years of education, with a learning gap of 3.7 years. Gaps in human capital start early and expand over time. The education system fails to provide students with the skills they need to successfully complete each stage and move confidently to the next. System deficiencies are visible even in the early years of primary education. The current student assessment system does not adequately inform teaching and learning processes at the system or school levels. International student assessment (EGRA, EGMA, TIMSS, PIRLS, PISA) indicate significant learning deficiencies, which start in the first few years of schooling. System deficiencies are visible even in the early years of primary education. EGRA and EGMA assessments (USAID 2017) give an indication of literacy and numeracy in early primary years. Even though there are improvements in reading skills between grades 2 and 3, the results for oral reading fluency and comprehension (the sub-tasks most highly correlated with literacy) are still significantly below international benchmarks. Results also differ by the language of the test taker, particularly for the more advanced reading sub-tasks, with Macedonian-speaking students doing better than Albanian and Turkish-speaking students in these.

Despite a swift education sector response to the COVID-19 pandemic in North Macedonia, learning losses are anticipated, requiring mitigation and recovery measures. During school closures, the Ministry responded to the immediate health risks to pupils and the education workforce from COVID-19 by closing schools in March, 2020.  Distance learning measures were put in place with the intention of covering primary and secondary education in all areas of the country. Despite the significant efforts made by the government to ensure continuity of learning,the management and organization of the learning process was left largely to the discretion of individual schools and teachers, creating unequal opportunities for learning and leading to significant learning losses, on top of already existing challenges with learning outcomes and learning inequality that preceded COVID-19. While the new Government program places a big emphasis on distance learning education, and digitalization overall, the pandemic revealed that the education system is facing a myriad of preexisting issues to going digital: including, access to broadband connectivity, particularly for marginalized and low-income populations, and low ICT adoption. According to the recent UNICEF survey (July 2020) with selected North Macedonian school directors, teachers and parents, almost 77 percent of the teachers could not maintain regular communication with students during the distance learning. Close to 80 percent of parents – who play a critical role for students’ achievements – had difficulty supporting their kids with distance learning and close to 65 percent had technical difficulties accessing necessary equipment (including lack of connectivity, computer, printer, etc.). Such findings reinforce the need for further support on digital education. Disadvantaged and vulnerable students face the greatest risk of learning loss. Primary schools have been reopened in October, 2020, but only for students up to third grade while for the students up to nine grade a distance learning were ensured. In the new school year 2021, the education process starts with the students physical presences, except for several municipalities. For students who are back to school, the Ministry will continue to ensure the health and wellbeing of students and the workforce, while planning mitigation and learning recovery measures for all students after this unanticipated break by putting into place diagnostic student assessments, catch-up sessions, and training on remedial approaches for weak students. For those who will remain following the teaching through distance learning, the Ministry will assure access to the internet and will provide devices especially for disadvantaged students, and adequate support to the teachers.

- Objective of the assignment

The main objective of the consultancy is to provide technical assistance to the MOES in establishing mitigation and learning recovery measures for all students in need directly affected by the learning challenges caused by  the COVID 19 pandemic  (Roma students, students with special education needs, students from low income families, other students with high drop-our risk etc.), by developing tutoring activities or other learning assistance modalities, , supported by carefully designed School Grants Program.

- Scope of work

The selected consultant should work closely with the MoES, PMU, Schools leaders and multi-professional teams to develop Tutoring Program and School Grant Program to support implementation of activities for vulnerable group of students, which will also support the  schools in their efforts to become more inclusive, and ensure  equal opportunity for all children.

The consultant is expected to perform the following activities:

Activity 1:  Inception Phase (Preparatory activities) - The Consultant is expected to:

- Review all documentation related to the assignment, including the existing framework documents including laws, bylaws, existing strategic materials, background reports for international assessment conducted in the country (EGRA, EGMA, TIMSS, PIRLS, PISA), NA pretesting results, and relevant evidence-based research on effective tutoring programs.

Activity 2: Develop the Tutoring Program – The Consultant is expected to propose cost-effective Tutoring program grounded in the following:

- Landscape analysis (criteria for identifying & targeting students at risk & those who have experienced the largest learning losses);

- Diagnostic assessment tools for assessing a learners’ current knowledge base and to allows for charting their learning progress by comparing pre - and post-tests results;

- Instructions for preparation of the individual learning plans and assessment tools for monitoring the progress.

- Identifying content areas & grades levels to be addressed by the tutoring program (foundational knowledge and skills should be prioritized: math, language (reading/comprehensive) skills and socio-emotional skills)

- Identifying mode of delivery (tutor-student ratios, timing and location of tutoring);

- Tutoring program duration, frequency and length, and overall number of lessons (duration, frequency of tutoring sessions),

- Criteria for tutor selection & recruitment including tutors training & support, tutors compensation;

- Measures and Data Collection  (identifying measures of success in alignment with tutoring model, including non-academic measures of impact; develop tools to collect data on the identified measures, including both quantitative and qualitative data; setting of benchmarks to monitor progress towards outcomes);

- Evaluation and improvement of the tutoring model;

- Feedback from the community and stakeholders group;

- Present and discuss the tutoring Program with Ministry of education and Science, PMU and agree upon the program.

Activity 3: Design of a school grant program to support tutoring activities

- Design a Grant Program that will be aimed at facilitating the execution of the tutoring activities;

- Prepare a comprehensive structural and functional manual for school grants (Grant Operational Manual GOM) which will define the grants’ approval and implementation arrangements for awarding grants including but not limited to the following: proposed model of Grant program and proposed methodology of grant award and operating procedures for both PIU/MoES and grant beneficiaries in line with project’s Operation Manual and other project documents; procedures for application and application forms; sample model of Grant agreement between the Ministry and the awarded schools as well as all other required draft documents.

Prepare guidelines aimed at assisting the School leaders and School Boards in preparing clear and comprehensive grant proposals aimed at implementing the tutoring program.

Activity 4: Supervision of the pilot-phase of the program

- Supervise in close cooperation with PEIP PMU the pilot-phase of the program implementation

- Revision of the program (if necessary) based on the experiences and data collected during the pilot phase

- Reporting obligations and deliverables

- Inception Report

- Full Toolkit for Tutoring Program (defining inputs, activities, outputs, and outcomes) including Guidelines for Tutors;

- Operation Manual describing the Grant Program (process and procedures for the school grants in all its stages including all pertinent forms and documents).

- Final Report incorporating any revisions to the program

All deliverables shall be prepared in English and Macedonian and will be reviewed and approved by the Minister of education and science and Project Director.

- Minimum Qualifications

- An advanced university degree (Master’s or higher).

- Work experience in education in developing countries, with specific reference to research, policy, and implementation of mentoring and tutoring programs tailored to the needs and circumstances of students;

- Knowledge/Experience in developing and/or implementation of Grant Programs;

- Previous work experience in Western Balkan will be considered as an advantage;

- Experience on World Bank or other IFIs  projects will be an advantage

- Strong interpersonal skills and ability to dialogue with diverse stakeholders to create consensus around issues and capable of working in multi-cultural environments;

- Strong (written and oral) command of English.

- Procurement and Contract arrangements

The contract for this assignment will be until June 2023. Expected start of services is January 2022.  The contract will be on lump sum basis, and the consultant will be entitled to remunerations upon submission of the deliverables as per agreed schedule. Local teachers and university professors are expected to apply for this position.

EGRA and EGMA stand for Early grade reading/mathematics assessments