## ANNEX I – IPA III Action Fiche

|  | Indicative title of the Action | EU Integration Facility |
| --- | --- | --- |
| CRITERIA FOR RELEVANCE ASSESSMENT | Key thematic priority | WINDOW 2 - GOOD GOVERNANCE, ACQUIS ALIGNMENT, GOOD NEIGHBOURLY RELATIONS AND STRATEGIC COMMUNICATION Thematic Priority 2: Administrative capacity and acquis alignment Thematic Priority 4: Strategic communication, monitoring, evaluation and communication activities |
|  | Links with specific policy instruments of the enlargement process | The EU Integration Facility (EUIF) is established under IPA II as a flexible funding tool, able to mobilise resources quickly in order to address issues as they arise. This approach will continue with IPA III, while the EUIF will more focus on supporting the accession process since North Macedonia has entered into a new stage of accession as of March 2020. The EUIF will allow the Commission and SEA to employ funds at short notice to support smaller projects addressing one of the EUIF objectives: - To effectively conduct accession negotiations, achieve high level of alignment with the acquis, and solid track record in reform processes - To improve the management of the EU funds by the national authorities - To ensure the Macedonian society is well informed on the EU accession process In addition, the EUIF aims to provide emergency response in the IPA III thematic priorities when needed. EUIF turned very useful in 2015 when the migration crisis hit Europe and in 2020 with COVID19 pandemic. The action is designed to address the IPA III thematic priority 2 Administrative capacity and acquis alignment and thematic priority 4 Strategic communication, monitoring, evaluation and communication activities within the Window 2: Good Governance, acquis alignment, good neighbourly relations and strategic communication. It builds on the requirements set in the 2018 Credible enlargement perspective for and enhanced EU engagement with the Western Balkans, to address reforms in the area of the rule of law, fundamental rights and good governance. It also takes into account the new negotiating methodology “Enhancing the accession process - A credible EU perspective for the Western Balkans”, which aims to increase the effectiveness of the overall accession process and its credibility and, thus, to make it more predictable, more credible and more dynamic. The principles of the new methodology will be translated in the Negotiating framework for North Macedonia which is expected to be adopted by the end of 2020. The methodology introduces clusters of chapters, placing focus on the Fundamentals Cluster as being the most important for the overall country’s advancement in the accession negotiations. The Action also considers the announced Economic and Investment Plan in support of the reform processes in the Western Balkan countries towards full-fledged membership including transformation of local economies into fully functional market economies able to fully assume the obligations and integrate in EU’s Single Market. The country has been implementing the Stabilization and Association Agreement (SAA) for over 15 years, has positive track record in implementation and an advanced level of harmonisation. As of 2018, North Macedonia has entered in the second stage of the SAA. The new negotiating methodology further underlines the importance of SAA and its bodies for steering accession negotiations as a platform to ensure stronger monitoring of progress and address aspects of accelerated integration in the respective clusters. The action is designed to support the implementation of the National Program for adoption of the Acquis (NPAA) as North Macedonia’s key strategic and programming document aiming to steer the process of European integration by defining priorities, dynamics and resources necessary for alignment of national legislation with ЕU acquis, as well as activities for adjustment of national institutions to European administrative structures. NPAA is revised annually and includes short-term and mid-term priorities. It has recently been restructured to respond to the clustering of chapters under the new methodology and will be basis for the bilateral screenings. It incorporates recommendations of the EC Country Report, SAA obligations, pending Urgent Reform Priorities, recommendations from peer review missions and UN SDGs and other international bodies. The most recent update of NPAA also includes plans for alignment based on the screening lists presented at the explanatory meetings for each chapter. NPAA is aligned with the Government Annual Work Plan, the Economic Reform Programme (ERP) and other national sectoral strategies. Efficient NPAA coordination, monitoring and reporting mechanism has been set. The Action also takes into account Economic Reform Program (ERP) and the joint conclusions adopted in the frame of the Economic and Financial Dialogue with EU. The European Commission's assessment of the ERP 2020 – 2022 states that the country has achieved 46.7% implementation of the jointly adopted country-specific policy guidance at the Economic and Financial Dialogue in May 2019, and has best performance in comparison to other candidate and potential candidate countries in the Western Balkans. The EU Council in March 2020 adopted decision for start of accession negotiations with North Macedonia. Given the new methodology, it will be crucial to provide systematic, targeted and streamlined assistance to the negotiation structures, with emphasis on chapters from Fundamentals Cluster as well as other selected linked chapters from other clusters. This Action is also designed to address potential alignment gaps in other IPA III Action fiches or additionally identified priority intervention areas arising from bilateral screening reports. |
|  | Links with national, regional and global strategies | The Action is contributing to the objectives of United Nation’s 2030 Agenda for Sustainable Development; more specifically, the action contributes to meeting one of North Macedonia’s priority sustainable development goals - SDG16. Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels, as well as SDG 8. Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all. The Action is in line and directly linked with the reform priorities identified in NPAA as a key strategic document of overall EU related reforms and basis for the bilateral screening. It is a horizontal document which, including but not limited to the above listed sectoral strategies: - Public Administration Reform Strategy (PAR); - Justice Reform Strategy; - State Program for prevention and suppression of corruption and conflict of interests; - Strategy for ICT in Judiciary 2019-2024; - National Strategy for Reform of Penitentiary System; - Police Reform Strategy; - Strategy for fight against human trafficking and illegal migration 2017-2020; - National Strategy for Counter Terrorism; - National Strategy for Countering Violent Extremism; - Strategy for Financial Investigations; - Economic Reform Program (ERP); - Public Finance Management Strategy; - Government Communication Strategy 2019-2020; - Transparency Strategy 2019-202;1 - Open Government Partnership National Action Plan 2018-2020 |
|  | Coherence with the Sector Approach | The Action will support all sectors, windows and thematic priorities. All Sector Working Groups (SWGs) will be involved in the implementation of this Action taking into consideration the crosscutting aspects of the negotiation process, the acquis related issues and the communication to the general public on the different impacts of the EU integration. Thus, the Action will contribute to improving the relevant strategic framework in all sectors and serve as platform of discussion and debate of the legal implications of the negotiation process, including the donors and civil society organisations. Linked with IPA 3 Window 2 TP 1 but is closely linked to priorities under W1 and W4 Linked with sector working groups on Rule of Law (Justice and Home Affairs), Democracy and Governance (PAR and PFM), Education, Employment and Social Affairs, and Roma. |
|  | Regional dimension | Not applicable |
| Indicative budget |  | Total budget : EUR 10.000.000 IPA funding : EUR 10.000.000 |
| Implementation Modality |  | The Action will be implemented under Direct Management, and entails numerous procurements and grants |
| Budget Support Readiness (only if the action is implemented through Budget Support) |  | Not applicable |

LOGICAL FRAMEWORK MATRIX [2 PAGES MAXIMUM]

| OVERALL OBJECTIVE(S) / (IMPACT(S)) | OBJECTIVELY VERIFIABLE INDICATORS | BASELINES (INCL. VALUE & REFERENCE YEAR) | MILESTONES [OPTIONAL] (INCL. VALUE & REFERENCE YEAR ) | TARGETS (INCL. VALUE & REFERENCE YEAR) | SOURCES & MEANS OF VERIFICATION |  |
| --- | --- | --- | --- | --- | --- | --- |
| To enhance the EU accession of the Republic of North Macedonia | Progress made in negotiation process | Some progress (2020) | Good progress in several sectors (2025) | Sufficiently met accession criteria for most of the clusters (2027) | - Report from negotiation team; |  |
| - SPECIFIC OBJECTIVE(S) / OUTCOME(S) | OBJECTIVELY VERIFIABLE INDICATORS (*) | BASELINES | MILESTONES | TARGETS | SOURCES OF VERIFICATION | - ASSUMPTIONS |
| - Specific Objective 1: To back-up the accession process in its entirety, enhance the alignment with the EU acquis and EU/International standards and the implementation of the legal framework in practice, and increase the public support for the EU accession process; | Number of open/closed chapters Societal support for the accession process/ Eurobarometer / Positive attitude | 0 (2020) 52% (11/2019) |  | 15 (2025) > 80% (2027) | - EC Country reports; Eurobarometer | - EU integration remains a government priority, which entails a continuous high-level political commitment to EU accession, support for the reforms and active participation in the sector policy dialogue. - There is willingness on behalf of the EU member states to support future enlargement Macroeconomic and political stability is maintained |
| - Specific Objective 2: - To improve the management of the EU funds by the national authorities | Level of absorption of EU funds: IPA II - contracting rate on IPA II and IPA III - disbursement rate on IPA II and IPA III IPA III - Value of supported projects - Project approval rate (ratio between the projects retained for funding and those submitted) | IPA II 26% (end 2019) 12% (end 2019) IPA III 0(2020) 0% |  | IPA II 95% (2026) 85% (2026) IPA III (2027) >600 MEUR 90% | Commission report on implementation of IPA Annual IPA Report Financing agreement |  |
| - OUTPUTS | OBJECTIVELY VERIFIABLE INDICATORS (*) | BASELINES | MILESTONES | TARGETS | SOURCES OF VERIFICATION | - ASSUMPTIONS |
| Output 1: Strengthened management of the accession process; | Number of adopted Roadmaps and Action Plans Number of prepared guidelines, instructions, rules of procedure and unified methodology tools for effective coordination Number of civil servants and other participants in negotiation structures trained e-Accession IT tools developed and operational: - software for translated national and translated EU acquis; - e-learning software on various EU topics) – number of logs | 0 (2020) 0 (2020) 0 (2020) 0 (2020) |  | >15 >50 > 5000 (2027) >10,000/year | Government legislative agenda reports - Project report - e-Accession on-line | Strong support for the accession to the European Union on behalf of the public administration, authorities, civil society, media and business The fundamental reforms (such as Public Finance Management, Public Administration Reform, Judiciary) are well progressing and create a favourable environment for the alignment with the acquis and the implementation in practice of the new legislation |
| Output 2: High level of alignment of the national legislation with the EU acquis; | Number of adopted laws ensuring the harmonisation with the acquis | 0 (2020) |  | > 150 laws (2024) |  |  |
| Output 3: Improved enforcement capacity of the national institutions | Number of people trained on the new laws Number of institutions with enhanced administrative capacity to implement the harmonised legislation | 0 (2020) 0(2020) |  | 20,000 (2027) > 300 (2027) |  |  |
| Output 4: Strengthened national capacity for management of the EU funds | IPA III - Value of funds under indirect management Financial management and control systems operate smoothly (number of critical audit findings) | 0 (2020) AA: 10 EC: 5 |  | >50% (2027) Max AA: 5 EC: 1 | Financing agreement Audit authority report Commission report |  |
| Output 5: Improved awareness of the citizens of North Macedonia on the country’s accession to EU. | Number of stakeholders reached through the implementation of the communication strategy Number of EU-specific spokespersons in national institutions trained Number of journalist on EU affairs trained Number of outreach events and communication products produced Number of entities involved in communication activities on EU accession | 0 (2020) 0 (2020) 0 (2020) 5 (2020) |  | >300,000/year 50 (2027) > 100 (2027) > 500 (2027) >200 (2027) | Project reports Media |  |
| BROAD ARRANGEMENTS FOR IMPLEMENTATION (IF AVAILABLE) | Direct management involving procurement and grants |  |  |  |  |  |

The baseline value may be "0" (i.e. no reference values are available as the Action represents a novelty for the beneficiary) but cannot be left empty or include references such as "N/A" or "will be determined later".