PRIMARY EDUCATION IMPROVEMENT PROJECT

TERMS OF REFERENCE

Educational expert for standard setting & test/item writing for the

National Assessment in Primary Education in the Republic of North Macedonia

- Background of the Project

The Primary Education Improvement Project (PEIP) will be implemented by the Ministry of Education and Science of the Republic of North Macedonia (MoES) and will improve conditions for learning in primary education. The project will be implemented country-wide, in urban, peri-urban and rural locations across the county. North Macedonia has recently undertaken important reforms of the preschool education and care system. To capitalize further on this important investment, the overall project will support the Government of the Republic of North Macedonia’s (MoES) to invest more, and more effectively, in the quality of teaching and learning in primary education. The PEIP project will be organized around three main elements that need to be aligned in order to be complementary to each other. Two are system-level reforms regarding the development  of a comprehensive national assessment program and enhancing competences of teachers, multi professional support teams and school leaders that would create the necessary enabling conditions, so the school teams are empowered with data on learning and up-to-date training. The third focuses on school-level interventions. Additionally, the PEIP project would strengthen sector management, project management and monitoring & evaluation.

Specific information/background regarding the assignment

North Macedonia’s Human Capital Index is lower than the average for its region and income group. Poor educational outcomes largely explain this loss of lifetime productivity. Children in North Macedonia can expect to complete 11 years of preprimary, primary, and secondary school by age 18. However, when years of schooling are adjusted for quality of learning, the result is equivalent to 7.3 years of education, with a learning gap of 3.7 years. Gaps in human capital start early and expand over time. The education system fails to provide students with the skills they need to successfully complete each stage and move confidently to the next. System deficiencies are visible even in the early years of primary education. The current student assessment system does not adequately inform teaching and learning processes at the system or school levels. International student assessment (EGRA, EGMA, and PISA) indicate significant learning deficiencies, which start in the first few years of schooling. This confirms a need to systematically investigate the extent of these deficiencies in primary education as well as the factors affecting outcomes. The lack of this data prevents effective evaluation of education quality and formulation of evidence-based education policies that are aimed at improving learning outcomes. Reforms needed to modernize assessment policy and practice have begun, but support is needed to scale them up and build institutional capacity. The National Examination Center (NEC) of the country represents a well-established and respected institution for the conduct of a wide range of assessments including high-stake examinations and sample-based assessments. Recently, the status of the NEC has been revised to make it more independent from the Bureau for Development of Education (BDE) and its structure has been adjusted to better match its increasing range of core functions, including the conduct of the proposed NAP. Most importantly, the Government recently adopted a Concept for National Assessment in primary education to guide the development and conduct of the NAP in primary grades.

- Objective of the assignment

The main objective is to hire a consultant that will support the international expert hired to provide technical assistance to the MOES and NEC in establishing the NAP in primary education and provide quality assurance of all stages of the entire process. The process of establishing NAP will require developing age-appropriate sample-based assessments for, initially, Grades 3 and 5. These will focus on the key enabling skills of basic mathematics (numeracy) and language (that is, mother tongue/language of instruction). The assessment frameworks and tests for the NAP for primary education that will be developed will be rooted in the curricula of the MoES and the levels of achievement used for reporting will reflect both the learning objectives contained within national curricula, associated standards, and the reality of the situation in the nation’s classrooms. Data obtained will be aggregated at the system and district levels with an acceptable level of precision.

- Scope of work

The selected consultant should work closely with the MoES & NEC team, and with other experts engaged for technical and logistical support to the NEC to develop and implement the NAP as stipulated in the Concept for National Assessment in Primary Education (Decision No. 18-5737/1, June 12, 2020) and in the Law on primary education (Off. Gazette of RNM no.161/2019). The consultant shall support development and administration of at least two cycles of mathematics in Grades 3 and 5 initially. The process for each grade takes three years to complete: the first year includes survey design and pre-testing of instruments, main data collection (testing) takes place in the second year, and reporting and dissemination take place in the year following the main data collection. On June 2 and 4, 2021, the State Examination Center conducted the pre-testing phase in Grade 3 in which 80 primary schools participated (40 schools with instruction in Macedonian language and 40 schools with instruction in Albanian language). About 2750 students from III grade were tested in the subject of mother tongue (Macedonian language or Albanian language), and about 1650 students in the subject of mathematics (in Macedonian language and in Albanian language). For the pre-test, four tests in Macedonian language, four tests in Albanian language and five tests in mathematics (in Macedonian and Albanian language) were prepared, as well as questionnaires for students, teachers and school principals. Technical assistance and logistical support will be required at each stage of developing, analyzing and finalizing test items , and analyzing results. The consultant is expected to be responsible for test booklets, standard settings, detailed assessment frameworks derived from national curricula and standards for mathematics, sampling, survey implementation, analysis, and dissemination in close consultation with the NEC and MoES.

Consultant shall work together with the NEC team & team of experts engaged for this task on the following activities:

Activity 1: Inception Phase (Preparatory activities) - The Consultant is expected to:

- Review all documentation related to the assignment, including the existing framework documents including laws, bylaws, curricula for the relevant grades, review the National Standards, background reports for international assessment conducted in the country (EGRA, EGMA, TIMS, PISA), and of additional existing materials relevant for the establishment  of the national assessment program in primary education;

Activity 2: Phase of main data collection (testing) in Grade 3

- Participate in the design and construction of assessment instruments (test items, variety of test booklets, background questionnaires, and sampling strategy for accuracy analysis of main data (probability sampling);

- Participate in organization of main testing in Grade 3 in selected schools;

- Participate in developing guidelines for collecting and evaluating each task and recording student responses;

- Participate in data collection and processing preparation (data entry, processing and preliminary analysis);

- Assist in reporting and dissemination of NA data

Activity 3: Phase of pre-testing in Grade 5

- Participate in the design and construction of assessment instruments (test items, variety of test booklets, background questionnaires and sampling strategy for accuracy analysis of pretesting data (probability sampling);

- Participate in developing guidelines for collecting and evaluating each task and recording student responses;

- Participate in organization of pre-testing in Grade 5 in selected schools;

- Participate in data collection and processing preparation (data entry, processing and preliminary analysis);

- Assist in reporting and dissemination of NA data

Activity 4: Phase of main data collection (testing) in Grade 5

- Participate in the design and construction of assessment instruments (test items, variety of test booklets, background questionnaires, and sampling strategy for accuracy analysis of main data (probability sampling);

- Participate in developing guidelines for collecting and evaluating each task and recording student responses;

- Participate in organization of testing in Grade 5 in selected schools;

- Participate in data collection and processing preparation (data entry, processing and preliminary analysis);

- Assist in reporting and dissemination of NA data

Activity 5: Support in design & implementation of the training program for different stakeholder groups at different phases of development and administration of NA

The Consultant shall support the international expert and team of local experts in the organization of training program, plan and training materials and manuals for different target groups. He will mainly assist in the following activities:

- Training of the working groups for preparation of the tasks for pre-testing prior to use in the National Assessment Programme. Also training for those involved in scoring/coding student responses to open-ended tasks.

- Training of all primary school principals and teachers, regardless of whether their schools are included in the testing sample or not, in order to acquaint them with: the objectives of measuring student achievement at the state level; the type of tasks used in testing, the process of creating and using standardized tasks to improve the teaching-learning process in classrooms.

- Training of NEC and MoES for setting standards of student achievement based on empirical results.

- Prepare and deliver dissemination workshops for different stakeholder groups.

- Reporting obligations and deliverables

- Inception Report

- Report on design and construction of assessment instruments (test items for, variety of test booklets, background questionnaires, and sampling strategy for accuracy analysis of main testing data (probability sampling) for Grade 3 of  NAP;

- Report on design and construction of assessment instruments (test items, variety of test booklets, background questionnaires and sampling strategy for accuracy analysis of pretesting data (probability sampling) for Grade 5 of NAP;

- Report on design and construction of assessment instruments (test items, variety of test booklets, background questionnaires, and sampling strategy for accuracy analysis of main testing data (probability sampling) for Grade 5 of  NAP;

- Report on processes for collecting and evaluating each task and recording student responses for each cycle of NAP;

- Report on the quality of the tasks of pre-testing for Grade 5 (for the needs of the working groups in question);

- Report on delivered trainings and workshops (including but not limited on: training program, plan and training materials and manuals) for different target groups as specified in the activity 5;

All deliverables shall be prepared in English and Macedonian and will be reviewed and approved by the NEC Director, Minister of education and science and Project Director.

- Minimum Qualifications

- Advanced university degree in the fields of education with focus on curriculum design, learning assessment and development of teaching and learning materials or another field related to the area relevant for the assignment;

- At least 8 years of work experience in developing, implementing and analysis of  the results in the national or international large scale assessment;

- Strong knowledge of education with specific focus on standard setting;

- Experience in development of curriculum standards and developing assessment instruments;

- Experience in sample design and sample drawing, surveys and questionnaires, test design, administering and evaluating of tests;

- Experience in setting standards of student achievement based on empirical results;

- Strong interpersonal skills and ability to dialogue with diverse stakeholders to create consensus around issues and capable of working in multi-cultural environments;

- Excellent writing, communication and presentation skills with stakeholders;

- Demonstrated experience in working with government institutions is an asset;

- Excellent command of English, both oral and written.

- Previous work experience in Western Balkan countries would be an advantage

- Procurement and Contract arrangements

The contract for this assignment will be until 27 February 2026. Expected start of services is October 2021. The Consultant is expected to work in Republic of North Macedonia during the missions and must be able to travel to North Macedonia as needed.  The contract will be on lump sum basis. Payment shall be done upon submission of the deliverables acceptable to the Client as per agreed schedule.