The Republic of North Macedonia Ministry of Finance

Improving Public Expenditure, Accountability and Tax Administration in North Macedonia (IMPACT) (P513182)

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

Draft for Appraisal

June, 2026

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Republic of North Macedonia Ministry of Finance (the Borrower) will implement the Improving Public Expenditure, Accountability and Tax Administration in North Macedonia (IMPACT) Project (the Project), as set out in the Original Loan Agreement (the Agreement). The International Bank for Reconstruction and Development (the Bank), has agreed to provide the original financing for the Project, as set out in Agreement.

- The Borrower shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this Environmental and Social Commitment Plan (ESCP), in a manner acceptable to the Bank. The ESCP is a part of the Agreement. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the Agreement.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Borrower shall carry out or cause to be carried out, including, as applicable, their respective timeframes; institutional, staffing, training, monitoring and reporting arrangements; and grievance management. The ESCP also sets out the environmental and social (E&S) documents that shall be prepared or updated, consulted, disclosed and implemented under the Project, consistent with the ESSs, in form and substance acceptable to the Bank. Said E&S documents may be revised from time to time with prior written agreement by the Bank. As provided for under the referred Agreement, the Borrower shall ensure that there are sufficient funds available to cover the costs of implementing the ESCP.

- As agreed by the Bank and the Borrower, this ESCP will be revised from time to time, if necessary, to reflect adaptive management of Project changes or unforeseen circumstances or in response to Project performance. In such circumstances, the Bank and the Borrower agree to update the ESCP to reflect these changes through an exchange of letters signed between the Bank and the Borrower’s Representative specified in the Agreements or the Director of Project Implementation Unit. The Borrower shall promptly disclose the updated ESCP.

- The subsection on “Indicators for Implementation Readiness” below identifies the actions and measures to be monitored to assess Project readiness to begin implementation in accordance with this ESCP. Nevertheless, all actions and measures in this ESCP shall be implemented as set out in the “Timeframe” column below irrespective of whether they are listed in the referred subsection.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBLE ENTITY |
| --- | --- | --- | --- |
| IMPLEMENTATION ARRANGEMENTS AND CAPACITY SUPPORT |  |  |  |
| A | ORGANIZATIONAL STRUCTURE a. Establish and maintain a PCU with qualified staff and resources to support management of environmental, social, health and safety (E&S) risks and impacts of the Project including E&S Focal Point appointed to the PCU from the existing staff in the MoF’s Department for EU and International Financial Relations or PCU employee. | a. Establish a PCU and appoint the E&S Focal Point prior to Project Negotiations and thereafter maintain the PCU and E&S Focal Point and these positions throughout Project implementation. | MoF |
| B | CAPACITY BUILDING PLAN/MEASURES Prepare and implement the capacity building plan: - training for PCU staff, stakeholders, communities, Project workers on ESSA Action Plan and GRM. | Throughout project implementation | E&S Focal Point appointed to the PCU |
| MONITORING AND REPORTING |  |  |  |
| C | REGULAR REPORTING Prepare and submit to the Bank regular monitoring reports on the environmental, social, health and safety (E&S) performance of the Project as a part of the Project Progress Report. The reports shall include: - Status of preparation and implementation of E&S documents required under the ESCP. - Summary of stakeholder engagement activities carried out as per the Stakeholder Engagement Plan. - Complaints submitted to the grievance mechanism(s), the grievance log, and progress made in resolving them. - E&S performance related to ESSA Action Plan implementation - Number and status of resolution of incidents and accidents reported under action E below. | Submit annual reports to the Bank throughout Project implementation, commencing after the Effective Date. Submit each report to the Bank no later than 30 days after the end of each reporting period. | PCU |
| D | INCIDENTS AND ACCIDENTS Notify the Bank of any incident or accident relating to the project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers, including those resulting in death or significant injury to workers or the public; acts of violence, discrimination or protest; unforeseen impacts to cultural heritage or biodiversity resources; pollution of the environment; dam failure; forced or child labor; displacement without due process (forced eviction); allegations of sexual exploitation or abuse (SEA), or sexual harassment (SH); or disease outbreaks. Provide available details of the incident or accident to the Bank upon request. Arrange for an appropriate review of the incident or accident to establish its immediate, underlying and root causes. Prepare, agree with the Bank, and implement a Corrective Action Plan that sets out the measures and actions to be taken to address the incident or accident and prevent its recurrence. | Notify the Bank no later than 48 hours after learning of the incident or accident. Provide available details upon request. Provide review report and Corrective Action Plan to the Bank no later than 10 days following the submission of the initial notice, unless a different timeframe is agreed to in writing by the Bank. | PCU |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ENVIRONMENTAL AND SOCIAL ASSESSMENTS AND/OR PLANS 1. Prepare and implement an ESCOP to address possible downstream risks related to digitalization (waste generation and management), energy efficiency, and installation of IT equipment, also relevant for the Project as well as Associated Facilities. | 1. Prepare ESCOP prior to commencement of project activities and thereafter implement the ESCOP throughout Project implementation. | PCU |
| 1.2 | TECHNICAL ASSISTANCE Carry out the consultancy, studies (including feasibility studies, if applicable), capacity building, training, and any other technical assistance activities under the Project in accordance with terms of reference acceptable to the Bank, that are consistent with the ESSs. Thereafter prepare and finalize the output of such activities in compliance with the terms of reference. | Throughout Project implementation. | PCU |
| 1.3 | ASSOCIATED FACILITIES Ensure that the activities in the purchase of IT equipment for equipment for the IFMIS, ITIS, and SAMIS systems and other Program supported institutions are carried out in accordance with the applicable requirements of this ESCP and the ESSs, including, inter alia, ESCOP. | Prepare ESCOP prior to commencement of project activities and thereafter implement the ESCOP throughout Project implementation. | PCU |
| ESS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURES Prepare and implement the Labor Management Procedures (LMP) section within a OM (Operational Manual) for the Project. | Prepare the LMP section within a OM prior to commencement of Project activities and thereafter implement the measurements throughout Project implementation. | PCU |
| 2.2 | OCCUPATIONAL HEALTH AND SAFETY MANAGEMENT PLAN Prepare and implement an OHS Management Plan as a part of ESCOP to assess and manage the OHS risks and impacts of the Project. AND Require contractors and subcontractors to implement OHS Management Measures in accordance with ESCOP. | Prepare the OHS Management Plan as part of the ESCOP prior to commencement of project activities and thereafter implement the ESCOP throughout Project implementation. | PCU |
| 2.3 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Establish and operate a grievance mechanism for Project workers, as described in the LMP and consistent with ESS2. | Establish grievance mechanism prior engaging Project workers and thereafter maintain and operate it throughout Project implementation. | PCU |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | WASTE MANAGEMENT PLAN Prepare and implement a Waste Management Plan (WMP), as part of the ESCOP prepared for the Project, to manage hazardous and non-hazardous wastes, consistent with ESS3. | Prepare the WMP as part of the ESCOP prior to commencement of project activities and thereafter implement the ESCOP throughout Project implementation. |  |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT Incorporate resource (energy) efficiency and pollution prevention and management measures in the ESCOP to be prepared under action 1.1 above. | The same timeframe as for the preparation and implementation of the ESCOP. |  |
| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY |  |  |  |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES |  |  |  |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES |  |  |  |
| ESS 8: CULTURAL HERITAGE |  |  |  |
| ESS 9: FINANCIAL INTERMEDIARIES [This standard is only relevant for Projects involving Financial Intermediaries (FIs).] |  |  |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN Update and implement a Stakeholder Engagement Plan (SEP) for the Project, consistent with ESS10, which shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. | Prepare SEP prior to Appraisal and thereafter implement the SEP throughout Project implementation. | PCU |
| 10.2 | PROJECT GRIEVANCE MECHANISM Establish, publicize, maintain, and operate an accessible grievance mechanism, to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of SEA/SH complaints, including through the referral of survivors to relevant gender-based violence service providers, all in a safe, confidential, and survivor-centered manner. | Establish the grievance mechanism prior to commencement of project activities and thereafter maintain and operate the mechanism throughout Project implementation. | PCU |
| INDICATORS FOR IMPLEMENTATION READINESS |  |  |  |
| The following actions are indicators for implementation readiness: Appointment of the E&S Focal Point in the PCU. |  |  |  |