Minutes of the IPA Sectoral Monitoring Committee Meeting

(VI official meeting) held on 25 November 2013

Component I Transition Assistance and Institution Building

Prepared by:

TAIB Technical Secretariat/NIPAC office

Skopje,

December 2013

The Agenda and is  attached as Annex to these minutes.

I INTRODUCTION

1. Welcome and introductory speeches

The Deputy Prime Minister for European Affairs and NIPAC (National IPA Coordinator) opened the sixth official TAIB Sectoral Monitoring Committee meeting (TAIB SMC), reiterating on the NIPAC objectives during its mandate: fostering and further on strengthening the Decentralised Implementation System on long run, Implementing IPA, as per the priorities of the Government and its EU agenda; Planning and preparation of the new IPA 2014-2020, based on the positive experiences and lessons learned from the current IPA and Increasing the level of transparency and inclusiveness in IPA implementation.

NIPAC expressed his gratitude to the contribution given by one representative from the non governmental sector in the course of the previous Sectoral Monitoring Commitees.  However, following her resignation from the position of Executive director in the NGO she represented in the SMC, her place as a member in the SMC is no longer available and has to be replaced with another appointed representative from the same NGO.

In addition, NIPAC elaborated on the following:

- TAIB Committee Technical secretariat drafted a brief Implementation report for the period January-November 2013 as a supporting document and for the benefit of this gathering.

- EC services were asked to send to the NIPAC Secretariat the results of the internal discussions as to identify how the controls and support provided by the Commission services under the current DIS system can be carried out in the most efficient and effective way.

- Regarding discussions towards IPA II-programming and implementation modalities – note was given on the whole processes which is delayed and still not clear in terms of IPA regulations and guidelines.

- Strengthening the coordination efforts in regular updates of the state of play of IPA through regular IPA coordination meetings and regular update submissions to the Government.  In the past few months, 17 meetings have been held and one should not underestimated the progress made with regards tendering of supplies for TETRA 3, Customs administration, Ministry of environment and physical planning, investigative centres for Ministry of Justice, etc.

- Because of the long periods experienced in tendering stages in addition to the slow and complex exchange of comments and approval procedures resulting from ex-ante regime, the enthusiasm of the project beneficiaries at all levels seems to have been weakened.

The co-chair from the Unit of DG Enlargement for introductory words:

- Anticipation of discussion for the important issues linked to management of EU funds, the DIS (Decentralised Implementation System) system and the necessary procedures the country should have in place for more efficient and effective implementation of pre-accession assistance as it is indispensable for the proper implementation of the programmes.

- Even though IPA is introduced in 2007, in practice the programmes are being implemented since 2009 and the real impact and lessons learnt would be best seen in the coming period.

- EC welcomed the progress achieved and the hard work done since the last SMC meeting in July, and recognised the challenges National authorities are facing;

- EC equally addressed the state of play with the implementation of the national programmes (NP 2009, 2010 and 2011) programming of IPA II, and how to minimise loss of funds under IPA Component I;

- EC and EUD (EU Delegation) support the DIS structures;

- Need for continuity under IPA II, without excluding any other management modes that would help reducing backlog and bringing implementation of IPA programmes forward.

- Proposal for Amendment of the Rules of Procedure of TAIB SMC

The Proposal for Amendment of the Rules of Procedure of TAIB SMC was approved by the Committee members, with no additional amendments proposed.

- Adoption of the draft agenda

The draft agenda was approved by the Committee members, with no amendments proposed.

- Approval of the minutes from the 5th official TAIB SMC meeting

The minutes were approved by the Committee.

- Presentation of the main decisions/conclusions made on the previous SMC meetings

NIPAC presented the following:

- The regular weekly meetings resulted in advancing of several files in procurement.

- Online tool has been designed for updating the state of play with regards the implementation.

- The Government is regularly informed about the state of play and the actions taken for improving the implementation.

- New public call for employments is published by Ministry of Finance to increase the number of employees in the CFCD (Central Financing and Contracting Department) and National Fund (NF).

- Communication and visibility efforts have been vested in new Strategy on communication and visibility of IPA, revised web site of SEA, participation on conferences for IPA, number of trainings conducted and to be delivered by the end of 2013.

- Improved conditions in the CFCD for more evaluations at once.

- Imposed strict deadlines for evaluation, working over weekends etc.

EC co-chair addressed the authorities regarding the activities they undertook or will undertake in order to:

- Accelerate implementation in order to meet IPA TAIB National Programmes 2009 and 2010 in respect to contracting and disbursement deadlines and the processing of additional upcoming national programmes;

- Strengthen the administrative capacities of the Operating Structures;

- Ensure more thoroughly that all agreed project related conditionalities are met by the respective beneficiaries

- Visibility and sustainability of IPA assistance.

II DIS MANAGEMENT AND CONTROL SYSTEMS

The floor was given to the Head of Department, National Fund:

- In the period between 16-18 July 2013, an Audit Mission by DG Enlargement was carried out in Republic of Macedonia.  The main objective of the audit was to assess the actions taken by the national authorities to address the outstanding audit findings on IPA Component I as well as any other issues linked to the functioning of the DIS system. The audit mission confirmed that most of the findings have been closed while for some of the audit finding that are not yet completely closed the activities for their implementation are at final stage.

- NF presented the latest changes and current administrative capacity in DIS structure

- An analysis is ongoing for the possible changes of the DIS modalities under the IPA II.  The analysis are not finalised yet since there are still uncertainties as to how the IPA II will be structured.  During the drafting of National Strategic Document there were some discussions abnd request for clarification for the DIS modalities based on which the final decision will be made.

- 4 million euro within IPA 2012 National Programme is in the pipeline for strenhtening the capacities of NIPAC, NAO and Audit Authority to comply with the requirements for new IPA.  The preparatory activities for this project are expected to start at the beginning of next year.

The Head of DG ELARG Audit section took the floor and emphasized the following points:

- The Operation structure, particularly CFCD needs to strengthen the human resources capacities for effective implementation (including premises).

- Clear definition of responsibilities between NAO, PAO and NIPAC has to be made on all levels.  The Contracting Authority should assume fully its responsibilities.

- Structured and regular monitoring of the progress of  implementation must be continued, bearing in mind the relevant responsibilities.  It is good that regular meetings are taking place so the needed actions are taken at appropriate time which goes in favour to overall supervision of IPA implementation on Governement level.

III RESULTS OF IMPLEMENTATION (FINANCIAL AND OPERATIONAL)

Overview of contracting and payments under DIS for IPA component I (2009-2011) Foreseen extensions and reallocations of the Programme IPA 2011 and 2012-2013

PAO (Programme Authorising Officer) and Head of CFCD presented the state of play under DIS for TAIB (2009)

- Until 25 November 2013, 40 projects have been contracted in total amount of EUR 19,87 million (52,87% vs. total available budget).

- Savings in total amount of EUR 2,1 million (planned vs. contracted Project Budget) for these 40 projects were done - 5,6% vs. total available budget

- At the moment three (3) Supplies in total amount of EUR 5,33 million are under contracting. By 21 December 2013, another 8 projects are expected to be signed in total amount of around EUR 3,44 million.

- The projected contracting rate by 21 December 2013 is expected to be around 78-80% vs. total available budget.

- A sound portfolio of around 40 projects, (20 small size projects) are already under implementation.

- The following activities are to be achieved: Development of appropriate administrative and organizational structures of the police units at regional and local level and further strengthening of the forensic capacity for inspections of crime scenes - Twinning project in the Ministry of Interior.

- Enhancing the capacity of Commission for Protection of the Competition (CPC) to manage and enforce EU state aid policies, to raise knowledge and understanding by state aid providers and to improve the overall planning, reporting and monitoring of state aid – Twinning project in the Commission for Protection of the Competition.

- Improving the operational, management and administrative capacity of the State Transport Inspectorate in order to be able to implement responsibilities with regards to road transport inspection deriving from the EU acquis as transposed in the Law on Road Transport, Law on Public Roads and the Law on Transport of Dangerous Goods by Road and Rail – Service contract in the Ministry of Transport and Communications.

- Strengthening the national and regional capabilities that are required to tackle the priorities for EU accession and market-orientated reforms and development in the sector with a particular emphasis on the further upgrade of the Land Parcel Identification System within the Integrated Administration and Control System – Service contract in the Ministry of Agriculture, Forestry and Water Economy.

- Strengthening of the operational capacity of the Macedonian Customs Administration in accordance with EU standards in the core Customs and Taxation business areas of the European Community Customs tariff and ensuring full compatibility and interoperability of the Macedonian Customs IT systems with the related EU Customs IT interoperability systems. (The concerned systems are TARIC, European Binding Tariff Information (EBTI), Quota, Surveillance, the European Customs Inventory of Chemical Substances (ECICS) – Service contract in the Customs Administration.

State of play under DIS for TAIB (2010)

- Financing Agreement – signed on 1st of December 2011;

- The Contracting deadline has been extended until 1 December 2014.

- Intensive preparation of tender documents – however still the implementation is in early stage;

- The Procurement Plan needs to be revised NAO and the PAO (CFCD) have to ensure realistic planning and proper execution of the procurement plans as agreed with the Commission, to avoid delays in procurement;

- NIPAC office should launch the necessary procedures inquiring the information from the main beneficiaries in case further changes to the fiches are needed, to be able to process the files on time, making them more realistic to the current needs of the beneficiaries.

State of play under DIS for TAIB (2011)

- Financing Agreement – signed on 18th December 2012;

- Preparation of tender documents started;

- So far only Twinning Contract for Supporting Gender Equality where the Ministry of Labour and Social Policy acts as a Beneficiary – advanced stage of preparation.

PAO also mentioned some horizontal issues from which it could be learned:

- 2013 was  a huge experience for CFCD as a contracting authority.  Contracting is a complex procedure and there are a lot of steps that require time and proper planning.

- Coordination meetings are good tool for detecting the different stage of the tendering documents;

- The quality of the tender documents will have to be improved with the coordination meetings, which is a new step to be undertaken;

- The beneficiary institutions should be visionary when programming projects in a manner to anticipate the implementation of the same projects.

- CFCD worked on giving on the job support and coaching the institutions to manage the preparation of the tender documents, workshops and bilateral meeting were also a useful tool;

- After 21st of December all aspects could be summarized and agree on the next steps that need to be undertaken by the national authorities and to discuss with the colleagues from the EU Delegation how to further improve the process of contracting and implementation.

The Head of NIPAC Office emphasized the following:

- Modification process (the National Programme 2010, the process for modification was launched on 27.12.2012 and the 6 project fiche modification dossiers were prepared in the period January-May 2013.  The last package was sent at the beginning of the summer and the approval is still pending.  Hence official information on the modifications of the 2010 National Programme, is expected as soon as possible).

- The Project Preparation Facility has been used as per the procedure of the NIPAC manual in light of the available funds under 2009-2011.  If the whole programme of 2009 has 37 contract, in parallel there are 30 PPF request prepared that also takes a great deal of time to contract.  Content wise there are fairly equal number of PPF request that are related to preparation of technical specification and ToRs and requests that are on an ad-hoc basis deriving from the EU acquis requirements.

- In respect to capacity building, i.e. trainings, it should be noted that the SEA TC in December 2012 has designed and in the first quarter of 2013 has conducted the first Training Needs Assesment (TNA) over the OS of TAIB. A report with findings and a development plan for 2013 was produced. In the second half of 2013, SEA TC together with the IPA Trainers is conducting revision of the generic IPA module and had initiated the work on development of modules for the most needed and desired topics detected through the conducted TNA, such as PRAG, Twinning, Irregularity and Fraud, Programming and Strategic Planning, Contracts, as well as a specific training on M&E. Also SEA TC is currently scheduling  the delivery of  PCM trainings with contracted external trainers paid by national funds, and this week starts with delivery of  generic IPA trainings for Local self-government units and other stakeholder in the 8 plan regions.

- SEA had conducted additional registration of its legal status, adding the definition of providing other educational/training activities to its portfolio, which enables us as institution to actively pursue and undergo the process of certification of modules and services that the SEA TC provides.

The representative from the Foundation Open Society Macedonia was interested in contracting of 8.2 million EUR from the IPA 2009 Programme and speciifically for the most risky Project fiche “Active civil society” about the grant scheme in amount of 1.6 million EUR dedicated to the civil society. It has been more than 14 months that the open competition has been finalized, and they have some information that if the money are not contracted by the EU Delegation by the mid of November, the funds will be lost.

After long discussion involving NIPAC, PAO and EUD representatives, it was concluded that:

- About the information that 8 million EUR from IPA 2009 will be lost, the real decommitment could not be estimated, it is for sure that some of the funds will be de-committed.  The de-commitment is a very realistic thing, and it happens even to the member states or the pre-accession states, it should not sound like an excuse, but the de-commitment exists everywhere.

- the evaluation of the grant scheme is still ongoing which is a why the national authorities could not reveal any information about the grant scheme.  This is according to the rule of confidentiality which should be respected, but once the results are known, the NGO’s will have the opportunity to ask questions.  However it was agreed to intensify the efforts by both sides in successful ccontracting of these grant agreements by end of contracting deadline.

Overview of payments and project implementation for Component I under centralised management (IPA 2007-2008)

EU Delegation representative presented the following:

- Many lessons were learned in the process, which mostly affected the programming of the TAIB Component, but could also contribute to the factors that affect efficiency, absorption of funds, project management and aid dependence.

- Procurement plans should be elaborated more realistically and with precise timelines for each actor in the procurement process. This practise of preparing indicative timelines for all the activities that should be undertaken within the process should be followed by CFCD and by the line ministries.

- The 1st Country Interim Programme Evaluation should provide us some more specific information on programme level, and hopefully these findings could be followed up on for the new financial perspective as well as the current projects.

- Implementation and enforcement of project results should always be appropriately followed up on;

- Maintenance of supplied goods have to be looked after following their delivery.

IV MONITORING AND EVALUATION

Follow up on the National Monitoring Plan

PAO point out the following:

- Out of 40 contracts signed from TAIB 2009, 8 are finalized and 32 in implementation;

- During the year, 7 on the spot checks were preformed by the SPOs, out of which 2 jointly with CFCD;

- On the spot checks included:

o	Twinning contract in the Ministry of Interior (2 on the spot checks, out of which 1 jointly with CFCD):

o	Service contract in the Ministry of Health (1 on the spot check):

o	Service contract in the Ministry of Agriculture, Forestry and Water Economy (2 on the spot checks):

o	Service contract in the Customs Administration (1 jointly with CFCD):

o	Framework contract in the Direction for personal data protection (1 on the spot check):

- No major findings identified

NIPAC office representative elaborated on the programme monitoring performed by the NIPAC office:

- Regular follow up of conditionalities is undertaken by national authorities.  In general, the biggest challenges in meeting the conditionalities, are with the lack of human resources and drafted tender documentation, the adoption of laws and bylaws and transition period for entry into force of some of this legislation with regards to the start of the project implementation,

- The rest are repeating and are conditionalities that will be followed up once the project implementation starts. These conditionalities are as follows: i) Endorsement by relevant key stakeholders of the Terms of Reference, specifications for the individual contracts to be engaged; ii) Appointing counterpart personnel by beneficiary prior to launch of the tender procedure; iii) Allocation of working space and facilities by the beneficiary before the launch of the tender process; iv) Participation by the beneficiary in the tender process as per EU (Twinning) regulations; v) Organisation, selection and appointment of members of working groups, steering and coordination committees, seminars by the beneficiary as per work plan of the project; vi) Appointing relevant staff by the beneficiaries to participate in training activities.

- As far as ROM is concerned, regular analysis of ROM reports are done by NIPAC office.

EC co-chair elaborated:

- The EC appreciate that NIPAC have taken on board the recommendations and established a Monitoring Plan for IPA 2009-2010 projects, knowing that this is indicative list and will change with the signatures of the contracts;

- This to be supported with a more methodical Monitoring Strategy – Guidelines from the CFCD to the SPO's which would be streamlined with the Monitoring Strategy under DIS of the EUD;

- Monitoring of project fiche level, is the responsibility of the NIPAC, thus, there must be some Statement of Assurance signed by the SPO's which would be a guarantee for the CFCD to start the procurement phase;

- The EUD would be much stricter with the pre-conditions for project start in the future;

- Greater attention should be paid to this Unit and the M&E Units in all line ministries, if we want to have successful projects and effects on the ground from the IPA assistance.

V  PROGRAMMING AND SBA

EC co-chair opened the point:

- The IPA Regulation would be adopted by February next year, CSP should be adopted around summer 2014, and immediately afterwards the NP 2014.

- All templates and programming guidelines would be hopefully shared with the beneficiaries before the end of this year.

- The financial allocation to IPA II instrument is comparable to the allocation of IPA 2007-2013

- In general, allocations under each programme are subject to discussions and would depend on the capacities, readiness and maturity of the individual sectors.They share an overall agreement on the sectors and we took into account the proposal of the Government to have separate sectors on Employment and on Competitiveness;

- The EU conducted a wide consultation with Member States, International Fininacing Institutions and Non State  Actors, and have received very positive feedback regarding the outlined sectors and identified needs, which confirms to us (both EU and the Government) that the goals and the activities are properly identified;

- The actual timeline on the relevant reforms;  at the same time the EU should make sure that these targets are in line with the overall Enlargement Strategy, the SEE Strategy and the EU 2020 Agenda.

- EUR 75-85 million are foreseen for MK in 2014

- Sector Approach means results-based programming, a better focus on prioritisation and sequencing, improved needs assessment and better risk analysis.  Support on the basis of the sector approach could be provided to: Justice and Environment, and Local and regional competitiveness

- Support on the basis of the project approach shall be provided to:, CBC (cross border cooperation), IPARD (IPA for rural development). The programme may include also an EU integration facility.

- Management modes will be decided on the basis of the IPA I backlog and readiness of each sectors;

- Direct discussions with the EUD on the annual programme are needed in order to start preparing the sectors for the sector based approach principles.

NIPAC added that the EUD during April 2013 has presented the new PRAG rules and management modes in CFCD and NIPAC office. As a result Information has been prepared and presented to the Government in May 2013. The management modes are discussed on several occasions on the level of Government and the decisions is pending due to a need to have more information on the rules of application in order to decide how to proceed.

Potential modalities to be implemented in the upcoming period are being considered with relevant stakeholders in the context of IPA II preparations and CSP.  All options are open and possible:

- The current DIS system is very complicated and has produced a backlog of projects, however it is a fact that also the DIS are in implementation only for three years and that the system should gives the first results in the following period.

- It is expected to receive second draft of the CSP, Programming guidelines and templates,  Sector Budget Support guidline in order to have  full picture in front of us

- Transfer of funds from IPARD 2013 to TAIB in cooperation with World Bank, paved the way to IFI and other donors in the IPA II. This project can be assumed as a “model” for an implementation by the inclusion of another donor and following the successful implementation, replication could be possible in the upcoming period under various sectors.

Besides, the Direct Grant agreement method with the other international organizations which have special expertise in various areas has been broadly utilized for the implementation of the funds and will remain to be one of the donor coordination mechanisms in the second period of IPA. 
Entrusting the implementation of IPA to DEU is also possibility, but in limited range.

VI. AUDIT AUTHORITY

Audit plan and Audit Report for Component 1

The floor was given to Head of Audit Authority (AA), where she elaborated the following:

- Information was given on the status of audit activities planned within the Annual Audit Work Plan (AAWP) for 2013,

- Audit of sample of operation was carried out by the auditors from the Audit Authority in the following auditees in NF, CFCD, IPA Units in Line ministries and Beneficiary institutions and Projects’ final beneficiaries on the basis of paid funds for signed contracts under NP 2009 and NP 2010.

- According to AAWP 2013, follow-up audits were planned and performed in October 2013 and they included follow-up of activities taken by auditees according to recommendations from the findings from performed system audits for IPA Component 1. It was found that auditees have taken appropriate measures for implementation of the recommendations and overcoming of part of identified weaknesses.

- Technical meeting in Brussels with DG Employment and DG Regio was initiated by the AA and agreed date of the meeting is 17 December 2013.

VII COMMUNICATION AND VISIBILITY

Communication and visibility strategy, action plan and organisation of events

VIII WRAP UP

- This Strategy for communication and visibility on IPA was discussed and approved on 149th Government session held on 14.08.2013, whereas NIPAC is envisaged to act as an initiator and head institution in publishing relevant news about IPA.

- Also, in the reporting period SEA web site was revised and new and updated information on IPA were published.  After today’s amendment of the Rules of Procedure of the TAIB Sectoral Monitoring Committee, SEA will ensure more transparency of the held sessions and availability of relevant data to our web site.

- This year the Parliament of the Republic of Macedonia expressed their interest for control and monitoring of IPA for which several sessions (11 and 26 July and 7-9 October) have been organized and held in the period July-October 2013 as per the 2010 Law on Assembly (more specifically the Articles 20-23).    The organizer of these hearings was the Parliament’s Commission on European Affairs in cooperation with the Parliamentary Institute.

EC co-chair added the following points:

- Continuation of the partnership in organising visibility events is crucial pre-condition for successful events;

- When it comes to IPA Component I Communication and Visibility, the responsibility is with NIPAC and the line ministries as well;

- The Strategy is well designed and the trainings for government representatives dealing with IPA, creation of IPA common web-platform where all IPA related information will be published, creation of interactive map on EU-funded projects, etc, but must be further streamlined with the main Communication and Vissibility  principles of the EU. Regular Quarterly Report on EU visibility to be prepared by CFCD/SEA;

- As envisaged in the EU Visibility Manual,  each project should present its communication plan to the Steering Committee, in order timely planning of visibility activities to be ensured;

- Detailed instructions for contractors on EU visibility to be prepared by both institutions, including templates;

- Translated Manual for Visibility and Communication of EU External Actions into local languages to be published on CFCD website.

General Conclusions and Recommendations

- The national authorities will uphold their efforts with respect to addressing systemic problems and increasing the absorption of IPA funds under decentralised management (DIS) at all levels.

- In order to tackle the procurement backlog and follow up on the NIPAC initiated "lessons learnt exercise" on DIS, NIPAC, NAO and PAO will prepare an outline of Action plan which will be presented at the JMC on 06/12/2013.

- The CFCD and the EC will continue to ensure, and, where necessary, improve their constructive working relations in order to further improve the quality of tender documents.

- The National Authorities should do their outmost to implement more and make the maximum out of the programme.

- The CFCD, in cooperation with NIAPC will prepare updated and realistic procurement plans for TAIB 2010, 2011 and 2012 by 31 January 2014.

- All modifications on the approved TAIB Programmes should be timely prepared and submitted to the Commission which will be processed once the IPA Regulatory Framework is in force.

- The NIPAC will provide their views on the 2014 Annual Programme taking into account the needs and sector readiness as soon as possible.

- CFCD must publish the contract awarded information along the agreed template by February 2014 on its website, following the IPA Regulation.

- The EC, together with NIPAC will agree on the template regarding the publication of the summary Minutes and Annual Implementation Report, following which SEA will publish the information its website, before the end of 2013.

- The Operating Structure (SEA, CFCD, and Line Ministries) must commit to strengthen and implement the M&E Plan (s) as of January 2014.

Arrangements for the next (VI official meeting) TAIB Sectoral Monitoring Committee

The next meeting would be scheduled for the period

The concrete data would be arranged between NIPAC office and EU services.