IMPLEMENTATION REPORT

IPA Component I – Transitional Assistance and Institution Building (TAIB)

Final brief

Prepared by:

National IPA Coordinator Office

Date: November 2013

Identification

| SECTORAL ANNUAL IMPLEMENTATION REPORT | Reporting year 2013 (from January 1st to November 1st 2013) |
| --- | --- |
| On-going IPA – national programmes under Component I covered under this report: |  |
| - IPA 2007 part 1 | - Final date for contracting: 30th October 2009 (2 years from the date of the conclusion of the Financing Agreement) - Final date for execution of contracts: 30th October 2011 (2 years from the final date for contracting) |
| - IPA 2007 part 2 | - Final date for contracting for all projects: 19 May 2010 - Final date for contracting for Project Fiche “Local Infrastructure for Social and Economic Cohesion”: 16 November 2010 - Final date for execution of contracts: 19 May 2012 (extension deadline to be confirmed) - Final date for execution of contracts under Project Fiche “Local Infrastructure for Social and Economic Cohesion”: 16 November 2012 |
| - IPA 2008 | - Final date for contracting: 23 February 2011 - Final date for contracting for Project Fiche ”Integrated Border Management”: 23 February 2012 - Final date for execution of contracts: 23 February 2013 - Final date for execution of contracts under the Project Fiche “Integrated Border Management”: 23 February 2014 |
| - IPA 2009 | - Original final date for contracting: 21 December 2012 - Proposal for extension of the contracting deadline for all contracts has been granted on 8 August 2012 - New final date for contracting 21 December 2013 - Final date for execution of contracts: 21 December 2015 |
| - IPA 2010 | - Final date for contracting: 1 December 2013 - The new proposal for extension of the contracting date is to be approved by Commission - Final date for execution of contracts: 1 December 2015 |
| - IPA 2011 | - Final date for contracting: 20 November 2015 - Final date for execution of contracts: 20 November 2017 |
| - IPA 2012 | - Final date for contracting: 2 October 2016 - Final date for execution of individual contracts: 2 October 2018 |
|  | Dates of the TAIB Sectoral Monitoring Committee: 17 July 2013 and 25 November 2013 |

ABBREVIATIONS

| AEC | Agency for Electronic Communication |
| --- | --- |
| BC | Broadcasting Council |
| CARDS | Community Assistance for Reconstruction, Development and Stabilisation |
| CBC | Cross Border Cooperation |
| CFCD | Central financing and Contracting Department |
| CfP | Call for Proposals |
| CIP-EIP | Competitiveness and Innovation Programme |
| CPC | Commission for Protection of Competition |
| CSO | Civil Society Organisations |
| DG | Directorate General |
| DPDP | Directorate for Personal Data Protection |
| EU | European Union |
| EUD | Delegation of the European Union |
| FA | Financing Agreement |
| FVA | Food and Veterinary Agency |
| GACU | General Affairs and Contracting Unit with CFCD |
| GEF | Global Environment Facility |
| IPA | Instrument for Pre-accession Assistance |
| IPA IR | IPA Implementing Regulation |
| IT | Information Technology |
| MAPAS | Agency for Supervision of Fully Funded Pension Insurance |
| MIPD | Multi-annual Indicative Planning Document |
| MIS | Management Information System |
| MoISA | Ministry of Information Society and Administration |
| MoC | Ministry of Culture |
| MoLSP | Ministry of Labour and Social Policy |
| MoAFWE | Ministry of Agriculture, Forestry and Water Economy |
| MoE | Ministry of Economy |
| MoEPP | Ministry of Environment and Physical Planning |
| MoES | Ministry of Education and Science |
| MoI | Ministry of Interior |
| MoP | Manual of Procedures |
| MoU | Memorandum of Understanding |
| NAO | National Authorising Officer |
| NBRM | National Bank of the Republic of Macedonia |
| NF | National Fund |
| NIPAC | National IPA Coordinator |
| NGO | Non-governmental organisations |
| NPAA | National Programme for Adoption of Acquis |
| OS | Operating Structure |
| PAO | Project Authorising Officer |
| PBA | Programme Based Approach |
| PF | Project Fiche |
| PPF | Project Preparation Facility |
| ROM | Result Oriented Monitoring |
| SAA | Stabilisation and Association Agreement |
| SARI | Sectoral Annual Report on Implementation |
| SEA | Secretariat for European Affairs |
| SMC | Sectoral Monitoring Committee |
| SME | Small and Medium Sized Enterprises |
| SPO | Senior Programme Officer |
| TAIB | Transition Assistance and Institution Building |
| TAIEX | Technical Assistance and Information Exchange Programme |
| TOR | Terms of Reference |
| ToT | Training of Trainers |
| TNA | Training Needs Assessment |
| TW | Twinning Contracts |
| UNDP | United Nations Development Programme |
| WLA | Work-load Analysis |

Table of Contents

1.	Quantitative and qualitative elements about the progress of the ongoing programme under IPA Component I and detailed information about financial implementation of the programme	7

1.1.	IPA 2007 State of Play	8

1.2.	IPA 2008 State of Play	9

1.3.	IPA 2009 State of Play	9

1.4.	IPA 2010 State of Play	15

1.5.	IPA 2011 State of play	19

1.6.	IPA 2012 state of play	21

2.	assessment of the management and control system of the Component I	23

2.1.	Existing management and control system	23

The remaining finings that need to be addressed are as follows:	27

2.2.	Administrative capacity	28

2.2.1.	Trainings of OS staff	29

2.3.	Monitoring	31

2.3.1.	Monitoring at Contract Level	31

2.3.2.	Monitoring at Programme Level (TAIB Sectoral Monitoring Committee)	31

2.3.3.	Result Oriented Monitoring	33

2.4.	Evaluations	36

3.	Programme Publicity and Visibility	37

4.	Cooperation with Civil Society Organisations	38

5.	Overview of the upcoming period:	38

Introduction

The Sectoral Monitoring Committee is scheduled to take place on 25 November 2013.  For such purpose, an Implementation Report has been drafted encompassing all the developments that have occurred in the period January-June 2013.

This Report should give an overview of all the activities undertaken in the reporting period and to facilitate the TAIB Sectoral monitoring committee members the discussion with sufficient data, during the Sectoral Monitoring committee meeting and consolidation of the conclusions and recommendations for future undertakings.

# Quantitative and qualitative elements about the progress of the ongoing programme under IPA Component I and detailed information about financial implementation of the programme

Key challenges addressed with 2007-2011 programmes are further improvement of governance and the rule of law, full implementation of the Ohrid Framework Agreement, the creation of a stable and professional civil service, to fight against corruption, to ensure full independency, efficiency and accountability of the judiciary, to strengthen the civil society dialogue and to strengthen the capacity to manage EU funds. Also, pre-accession assistance aims at supporting economic development and social cohesion and to support the country in adopting the acquis as well as with building institutional and administrative capacity to transpose, implement and enforce Community standards.

Since the 2011 National Programme has been programmed using for the first time the sector based approach, the specific attention has been committed via 10 (ten) sector fiches, specifically supporting the sectors of public administration reform and e-government, rule of law, media, bankruptcy, agriculture, professional qualifications, local integration of refugees, internally displaced persons and minorities integration, reinforcement to build administrative capacities and the participation into the EU Programmes and Agencies.

## IPA 2007 State of Play

As regards to the forms of assistance required within both parts of the National Programme for Component I TAIB 2007, the majority of the projects implemented were service contracts, with respective supply and works contracts, one grant with a Member State, one Twinning and four Twinning Light arrangements.

The 2007 TAIB programme is being implemented on a centralised basis by the Delegation of the European Union in Skopje, in accordance with Article 53a of the Financial Regulation and the corresponding provisions of the Implementing Rules.

Projects implementation

The benchmarks foreseen in both Financing Agreements (FA) for 2007 have been met. Under the FA all projects were contracted as planned.  Not all the funds allocated were disbursed to the full amount due to savings in procurement process and the fact that not all funds allocated under PPF were used.

IPA 2008 State of Play

The 2008 programme encompassed 14 projects with 48 contracts, totalling EUR 37.122 million contributing to the areas of political criteria, civil society development, customs union, judiciary, fiscal decentralisation, agriculture and rural development, etc. In addition EUR 4 million as part of the Multi Beneficiary Regional Programme, were allocated  for two projects - Tempus with EUR 3.5 million and Nuclear Safety with EUR 0.5 million, totalling up to EUR 41.122.001.

Projects Implementation

Out of the 48 contracts which were foreseen in the procurement plan, all the envisaged contracts were signed and fully implemented. The contracting deadline was 23 February 2011, with one exception. This exception refers to the extension of contracting deadline for TETRA II Supply Contract. Experience with TETRA II has shown that this is a rather complex project. It was therefore deemed necessary the contracting deadline for TETRA II supply contract to be initially extended by six months.

## IPA 2009 State of Play

The 2009 TAIB programme amounts to EUR 37.060.500 and is being implemented by the CFCD in the Ministry of Finance, except for the projects: 4.1 'Participation in Community Programmes and Agencies' and 4.3 'Preparatory Measures for Participation in the Lifelong Learning and Youth in Action Programmes', which will be implemented by the European Commission.

Project Implementation

The original Procurement Plan of 2011 was amended and modified on 23 February 2012, as to reflect the actual timeframe of on-going procurement and contracting activities.

In addition for ensuring the regular monitoring of the implementation of the signed Procurement Plan, CFCD Procurement and Contracting Unit on a quarterly basis updates the Procurement Plan Monitoring Sheet.

A Monitoring Plan was developed by CFCD elaborating the monitoring tools for each of the contracts to be implemented. Following the Indicative Monitoring Plan for 2009 from October 2011, the Annual Monitoring Plans for TAIB national programmes 2009 and 2010 were updated in June 2012.  Since a very few projects have been contracted, at this point the Monitoring Plan is still relatively indicative.  Once the implementation keeps a steady pace, the Monitoring plan could be used as a practical tool for monitoring.

Currently there are 37 contracts plus around 30 PPF projects foreseen in the Procurement Plan for TAIB 2009.

As regards the requests for use of PPF 2009, upon the procedure by NIPAC Office the use of Project Preparatory Facility (PPF) is closely managed and monitored by NIPAC Office and alongside with the PAO needs, PPF support has been identified for various beneficiary institutions.

In brief thus far by 1 November 2013: total amount EUR 19,6 million (which represents 55% of the available budget) is contracted (Annex 3 Register of contracts).  Out of these funds EUR 18,068 million are IPA funds.  Currently there are evaluation reports in preparation for contracting of 6 projects, in amount of EUR 10 million.  As for the PPF approximately EUR 2.4 million are contracted and EUR 0,5 million are in evaluation procedure.

Risky projects

Potential risky projects have been also identified by the CFCD where there is a real danger not to be contracted.  The list is the following:

- Service contract for technical assistance for strengthening the institutional capacities for approximation and implementation of environmental legislation in the area of water management for the Ministry of Environment and Physical Planning in the amount of EUR 1.700.000.

- Supply contract within the project fiche 3.6. Strengthening the institutional capacities for approximation and implementation of environmental legislation in the areas of water management and nature protection in amount EUR 500.000.

- Grant scheme within the project fiche 1.4. Support to Enhancement, Sustainability and the Development of an Active Civil Society in total amount of EUR 1.666.666.

- Supply contract for purchasing Centralized back-up and Disaster Recovery System for the State Statistical Office in the amount of 300.000 EUR.

- There are approx. EUR 1.000.000 which constitutes several contracts under the PPF budget line that have to be contracted till 21.12.2013.

Use of PPF

Following the developed transparent procedure for the use of PPF resources, NIPAC and CFCD took a pro-active approach in assessing the needs of beneficiary institutions of additional assistance for preparation of projects. Concerning the requests from the Project Preparation Facility, whereby NIPAC bears the responsibility of transparent distribution of funds under this fiche, NIPAC Office has drafted modus operandi and shared it with CFCD (bearing the responsibility over the procurement process) and EUD (bearing the responsibility for endorsement and ex-ante control).

This procedure is now embedded into the NIPAC revised MoP in order at a fairly early stage to address deficiencies in expertise and required support for preparation of mature projects and speeding up the tendering and contracting phase.

Projects Modification

Due to some delays with the projects’ implementation, NIPAC Office initiated procedure for modification of some project fiches. Hence, NIPAC approached the EUD on 1 June 2011 with detailed information on the requests related to several project fiche modifications.

The procedure envisages several steps in the modification process.  Thus, 11 separate procedures were launched in the period 2011-2012 which resulted in a time consuming exercise that was completed with extension of the contracting period for the whole programme and minor modifications of 5 project fiches.  All the modifications are approved by EC by end of 2012 and the contracting deadline has been extended for one year -21.12.2013 on 08.08.2012.

Finally during the period March-July 2013 there focus was put on ensuring the use of savings from the procurement process.  It has been calculated that EUR 1.058.441 are available to be spent for priorities of the Government within this component.  Hence several consultation meetings took place in the reporting period, whereas the final decision is made on 07.07.2013 where all the funds have been reallocated to project fiche 4.2. Project Preparation and Support Facility, making the necessary modifications to the respective fiche.  The approval of this modification was done on 31 July 2013.

Procurement process

The EUD on 10.09.2013 raised its concerns about the current delays and backlog in procurement of 10 to 11 procurements that are in risks.  Hence the EUD requested CFCD plans on how the loss of funds will be minimised till the end of the 2013.  The EUD in the same letter suggested the evaluation reports during the different phases of evaluation and preparation of contracts in advance that could be submitted to EUD for ex-ante control at the same time with submission of the evaluation reports.  The EUD also offered their assistance in training, advice, observers, and premises to CFCD.    Finally the EUD noted that if the evaluation reports are not finalised and submitted to EUD by mid November 2013, they can not guarantee that the contracts will be signed.

On 10.10.2013, the CAO sent a letter to DG Enlargement explaining in details that on the basis of the Evaluation Plan, there are 19 projects under TAIB 2009 that are in the tendering procedure and are foreseen to be contracted by 21.12.2013.  Nine out of 19 projects in total amount of EUR 8.2 million, have been identified as high risk, as follows:

- Support to Enhancement, Sustainability and Development of an Active Civil Society, grant scheme in the total amount of EUR 1.666.666;

- Supply of Police Digital Radio Communication System – TETRA 3, supply contract in total amount of EUR 3.800.000

- Supply contract for purchasing Centralised Back up and Disaster Recovery System in total amount of EUR 300.000;

- Strengthening of Blood Safety System supply contract in total amount of EUR 617.8000;

- Conservation and revitalisation of the Cultural-tourist site St. George-Staro Nagorichane, works contract in the total amount of EUR 600.000;

- Supervision of the Works for Conservation and revitalisation of the Cultural-tourist site St. George-Staro Nagorichane, FWC in the total amount of EUR 199.000;

- Supply of equipment for biodiversity monitoring information system and equipment for water management information system and water monitoring, in the total amount of EUR 500.000;

- Further strengthening of the Administrative capacities of the administration, supply contract in the total amount of EUR 500.000.

The mitigation measures that were undertaken by the CFCD that could contribute to the speeding up of the procurement process such as:  increasing the efficiency of the evaluation process, imposing deadlines for completion of evaluations to evaluation committee members, requesting their continuous presence (even during weekends).

The Minister also called for EUD presence and active participation of observers during the evaluation process of the tenders, optimising the time needed for ex-ante control.

On the other hand, the coordination process led by NIPAC predominantly established for meeting the contracting deadline for TAIB 2009 has managed to:

1.  Assist in the timely revision of the tendering documents that were ex-ante rejected or and suspended by EUD;

2.  The NIPAC services prepared an online application for regular update of the state of play with regards to IPA implementation which served as a basis for conducting the regular weekly meetings and preparation of regular submissions to the Government for the IPA.  However, it has come to our knowledge that the regular update is not done regularly by all IPA beneficiaries.

3.  Certain improvement is evident in the speed of revision of documents, however there is still a challenge to increase the quality of the tendering dossiers which is noticeable via the number of times that one dossier is returned from the EUD rejected or suspended.

4.   The awareness is raised about the personal accountability for implementation of IPA, as well as the need for self assessment via noting the lessons learned thus far;

5.    The relations among the national DIS structures are strengthened; there is a culture of exchanging advices, sharing experiences, open discussions about problems and seeking solutions.

6.  The relations with EUD and national DIS structures are improved, notwithstanding the need for further strengthening of the cooperation predominantly between EUD and CFCD in terms of aligning the procedures to be applied.

Factors that impeded and/or delayed the implementation or had a positive impact:

As it was the case with the IPA 2008 programme, many lessons learned have been translated into conditions for implementation. These include the allocation of sufficient staff and budget, allocation of working space, arrangement of legal requirements, etc. In the past, these issues regularly were causing delays in project implementation.

Deficiencies in project planning (preparation of Project Fiches, especially in the case of supply contracts) hampered the implementation of supply contracts, especially when the tender documentation is elaborated as an output/deliverable of a service/twinning contract.

The large number of contracts envisaged to be implemented under TAIB 2009 has lead to a huge workload in preparing tender documentation by the Operating Structure and especially the CFCD mainly due to limited expertise of the SPO/beneficiary structures and limited number of staff of CFCD. The lack of staff within CFCD remains to be considered as a high risk and as control weakness during 2013.  However, the mitigation measures were properly undertaken through regular submission of requests for employments, preparation of WLA and Recruitment Plan as per established procedures, submission of requests and proposal for amendments of the Systematization act and provision of proper training of the new comers.

Stronger involvement of End beneficiaries that are not part of the OS is crucial for timely and quality projects implementation, especially when these differ from SPO structures. CFCD and NIPAC office have developed internal procedures between SPOs and End beneficiaries whereby tasks of the later are clearly elaborated.

During the reporting period, the Operating Structure and EUD continued to work on improving the quality of procurement documents through daily communication. The CFCD elaborated Lessons learned that should contribute to minimising the EUD rejection rates on the tender documentation and improving the absorption of funds.

The main reasons for delays could be summarised the following:

- Delays in nomination of members in the respective Evaluation committees and their availability impacts delays in the tendering process. Nomination of titular and substitute could mitigate the problem;

- Delays in preparation of tendering documentations or submission of documentation by the Beneficiary institutions  jeopardises the timely execution of tendering processes and may lead to de-commitment of funds. Better use of PPF as well as building capacity of End beneficiaries is a feasible solution to the problem;

- Delays in establishment of IPA Structure within the Ministry of Culture created difficulties in the procurement of the direct grant within TAIB 2009 National Programme;

- Delays in ensuring the national co-financing needed envisaged under the specific projects is also a crucial factor;

- Delays in meeting the conditionalities also affect the tendering process and implementation of the projects. NIPAC Office closely monitors the conditionalities at the respective stages of projects’ implementation;

- Achieving the stated benchmarks/indicators is highly regarded as to better quantifying the SMART indicators, starting from MIPD. This is to be improved through the developed System of indicators (February 2012) that will be used in the programming process and further elaborated into the tender documentation and followed during project implementation;

- In addition it should be noted that limited number of CFCD staff and insufficient capacity of SPOs/beneficiary institutions for conducting regular monitoring of contracts could impose delays in the implementation, verification of expenditures and execution of payments. Similar risk factor is the insufficient staff with proper technical qualifications for administration of Management Information System (MIS) could influence the functionality of the system and processing of information.

- It should be noted that in some instances diverge instructions from EUD task managers created some confusions and thus the preparation of lessons learned paper and its communication by CFCD to SPOs and beneficiary institutions facilitated the building of ownership and unifying the approaches in projects implementation.

- Strengthening the administrative capacity is needed in the area of programming and monitoring of projects implementation.

- Projects sustainability is to some extent affected by the lack of multi-annual programming under IPA Component I.

## IPA 2010 State of Play

The 2010 Programme includes the highest number of twinning arrangements thus far.  There are nine full twinning arrangements in areas such as public administration reforms, institutional capacities for the accession negotiation process, anticorruption, freedom of movement of workers, veterinary, public revenue, customs and environment.

Projects implementation

Following the signature of the Financing Agreement the CFCD fine-tuned the draft Procurement Plan and approved it on 4 May 2012.  The contracting deadline for all the contracts is 01.12.2013.

Within this Programme there are 30 contracts envisaged and thus far only one contract has been signed that is the supply contract for the vaccines for the Food and Veterinary Agency in amount of EUR 1.180.000.

Hence due to the evident delays in the procurement process, on the second 2012 Sectoral Monitoring committee meeting, a time extension of the 2010 National Programme has been discussed and decided upon.   The full documentation for this request in terms of modification of the Financing Agreement has been prepared by NIPAC office and submitted to EUD in first quarter of 2013.

Projects modification

In the course of the first semester of 2013 NIPAC Office managed the procedure for modification of the 2010 National Programme. Those were few modifications of project fiches as follows:

1.  The Food and Veterinary Agency has requested some minor amendments to be done in the Project Fiche 3.3. “Strengthening of administrative and institutional capacity of the competent authorities regarding food safety, veterinary and phytosanitary policy”.

2. The Ministry of Information Society and Administration requested a change of final beneficiary of the project fiche 1.8. “Technical assistance to institutions in charge of implementation of the civil service and public administration reform”.

3.  The Public Revenue Office has requested some modification in the project fiche 3.4. “Improving of the Public Revenue Office (PRO) taxpayers services”.

4. The Ministry of Interior requested changes in the Project Fiche 1.1 Further Institution and Capacity Building of the Police Service in the area of border management, community policing and fight against organised crime.

5.  The Ministry of Culture has requested changes to be introduced in the Project fiche 1.4. „Revitalisation and Adaptation of Shengjul (Gjulshen) Hamam into a Cultural-Info Centre“ where certain amendments are necessitated as to additional elaborate and reflect the recent actual conditions in the field.

6. Ministry of Justice has proposed modification of the Project fiche 1.1. „Further support to independent, accountable, professional and efficiently judiciary and promotion of probation service and alternative sanctioning“

- Modification of the contracting deadline of the IPA 2010 National Programme for one additional year (01.12.2014 instead of 01.12.2013) was requested by NIPAC on 25.04.2013.

- Use of savings under the project fiche 4.1. Participation in the Union Programmes and Agencies.  Due to some leftovers from this project fiche in the amount of EUR 2 million, there are two project ideas that are decided to be financed in addition: support to regional economic development and support to agricultural sector for accreditation of new measures.

Even though, the whole package is drafted and submitted to EUD and respectfully to the European Commission, the positive feedback is still pending.  This creates tremendous discomfort of the IPA beneficiaries’ institutions in timely preparation and launching of the tendering documentations.     This concern has been repeatedly express to EUD on the weekly coordination meetings organised by NIPAC.

Risky Projects

In order to avoid the situation as for the TAIB 2009 project several conclusions have been made on the IPA coordination meeting that took place on 25.10.2013 and on 164th Government session held on 29.10.2013 that the beneficiary institutions Ministry of Labour and Social Policy, Ministry of Economy, Food and Veterinary Agency and Public Revenue Office to finalise their tendering documentation by 01.1.2013.

The coordination effort will be increased in the following period in order not to loose funds at the end of 2014.

## IPA 2011 State of play

The Financing Agreement for 2011 National Programme was signed on 20 November 2012 in the amount of EUR 33.026.859,18 out of which EUR 28.903.410.

This National Programme was programmed for the first time on the basis of sector approach and there is a difference in presentation of the areas of intervention.  Thus, there are 6 sectors and 10 sector fiches developed within these 6 sectors.

The drafting of the procurement plan for respective Programme is in its initial phase.

Furthermore, the NIPAC office in late April 2013 has launched the process of modification of the sector fiches with deadline end of May 2013.  Thus far, only one request for modification has been received, which is for the sector fiche on media and freedom of expression.    As per the previous experience any delays in the process of modification of sector fiches affects the procurement and tendering process.

The NIPAC office initiated the procedure for change of the modifications of IPA TAIB 2011 Programme, during summer 2013.

The list of the project fiches that are being prepared to be modified is the following:

## PF 4 Freedom of Expression

## PF 3 Rule of Law

3.  SF 6 Agriculture and Rural Development

4.  PF 1 Public Administration Reforms and E-Governance

5.  PF 8 Local integration of refugee, IDP and Minorities integration

6.  PF 9 Reinforcement of Administrative Capacity to meet the obligations of membership

7.  PF 2 Civil Society

8.  PF 10 Union Programmes and Agencies

The NIPAC office plans to prepare the full package for modification of the Financial Agreement by end of 2013 and officially to submit it to EUD for further consideration and approval.

## IPA 2012 state of play

The National programme for the Republic of Macedonia under the IPA-Transition and Institution Building Component for the years 2012 and 2013, has been adopted by Commission decision C(2012) 9321 of 12 December 2012.   The European Union contribution for the year 2012 is fixed at a maximum of €28,159,161. The individual contracts and agreements which implement this Agreement shall be concluded no later than three years from the date of conclusion of this Agreement and the contracts must be executed within a maximum of 2 years from the end date of contracting.

The proposed IPA National Programme (NP) 2012/2013 consists of five sector fiches and seven project fiches, supporting the following sectors. The implementation of this Programme is in its early phase.

# assessment of the management and control system of the Component I

## Existing management and control system

In the reporting period, NAO drafted the Annual Management Declaration in a form of a Statement of Assurance for this Component for the year 2012, based on the NAO’s supervision of the management and control systems throughout the financial 2012 year and in accordance with Article 27 of the IPA IR and Article 17 of the Framework Agreement. The Statement of Assurance for the IPA Component I for the year 2012 was sent to EC/DG Enlargement on 28 February 2013 (letter no. 27-10770/1).

Within its statement, NAO has informed the Commission on the following reservations:

- Turnover of staff and need for additional improvement of the administrative capacities of some of the institutions being part of the Operating Structure;

- Vacant key positions (SPOs) in the Ministry of Health and the Public Revenue Office;

- Insufficient quality of tendering documents during the preparation phase by line ministries/beneficiary institutions, which lead to rejection/suspension rates by EUD and delays in tendering;

- No internal audit carried out during 2012 in the certain IPA structures, despite the existence of established Internal Audit Units in their institutions.

Remedial actions regarding the reservation stated are as follows:

#### 1. Proper fulfilment of the working position in accordance with the required additional employments according to the WLA prepared by the Operating Structure and further reassessment by NAO/NF.  More intensive   on the job trainings, workshops, practical instructions and transfer of know-how to the newly recruited employees;

2.  Nomination of an adequate officer in the Ministry of Health, Public Revenue Office to perform the function of SPO within the respective responsibilities

3.  Adherence to PRAG and proper following of the lessons learned and EC/EUD comments on the quality of documents during the preparation of tender documents by LM/BI.  Increase on the supervision/pro active role of SPOs in order to properly implement the agreed activities for improvement of the quality of tendering documents and

4.  Proper planning and implementation of the audit as per the Annual Internal Audit Plan.  Intervention from high official if required for proper implementation of the Annual Internal Audit Plan.

Following the submission of the final audit report by Commission Services on 25 February 2013, the NAO services drafted Progress report regarding implementation of the recommendations given with the Final Audit Report by DG ELARG upon Audit Mission conducted 7-11 May 2012.  The letter is sent on 12.04.2013.

NAO has reported on meeting the findings and recommendations:

1. On the system as a whole: Management Information System, Updating and fine tuning of legislative instruments and operational manuals;

2. On organizational position of the National Fund;

3. Role of evaluation activities, reporting on system changes and programming procedures in NIPAC and NIPAC Office;

4. Staffing in CFCD;

5. Lack of finalized working procedures in the SPOs/line ministries and agencies;

6. Division of responsibilities for the implementation of the IPA as a whole;

7. Staffing in NAO office/NF as weakness in the control and management system;

8. PPF assistance requested by external entities.

The joint management follow up mission was carried out by ENLARG units B.2 and E.2 from 16th to 18th of July 2013.  The main objective was to access the actions taken by the DIS authorities to address the outstanding audit findings on IPA components I, after issuing the audit report from audit mission carried out in mid 2012.  It has to be noted that most of the conditions can be closed.  However, four issues remain open and seven new recommendations and issues of a systematic nature are included.

## The remaining findings that need to be addressed are as follows:

## Management Information System (MIS)

## Organisation position of the National Fund (NF)

## CFCD – staffing level

## Lack of finalised internal working procedures with SPOs and Beneficiary institutions

New findings of the follow up audit:

- Division of responsibilities for Implementation of IPA assistance – the responsibilities between NIPAC, NAO and PAO are not clear in the national rules and procedures.  Even though the Manual of Procedures for CFCD and NIPAC formally cover the issue, this alone is not sufficient.  The responsibilities and accountability must be included and laid down in the basic national legal act/decree and in the Implementing and Operational Agreements.

- Weaknesses in the control and management system – staffing of NAO office/NF – three year rolling WLA for NF has been addressed and a three year recruitment plan has also been prepared.

- Project Preparation Facility (PPF) – assistance requested by external entities (not accredited – outside DIS) to be managed by the closest SPO and if there is no such close entity the SPO at the SEA will perform this function.

- NAO position – a higher level position of NAO (state secretary or similar) is seen as essential requirement for the Commission (as required in the art.4 of Annex A to the Framework Agreement).

- Working procedures at CFCD – the CFCD should revise all its checklist and workflow to comply with four-eyes check (initiation and verification) at the level of managerial unit by two task managers; appropriate management supervision reflected in the checklist; quality control should be based only on risk assessment; final approval to be done by Head of CFCD.  However it is important for business continuity to clearly determine who signs in the absence of PAO.  Finally it is imperative that the CFCD is given more authority and resources and that there is sustained commitment to support their work at the highest levels of the government.

- Scope of SPO responsibilities (technical vs. financial aspects of contracts) – under the currently accredited procedures, the SPOs are also required to carry out financial verifications on invoices.  To ensure compliance with the IPA IR and to simplify the workflow, the NAO and PAO are recommended to limit the SPOs role to technical aspects of contracts only.  All financial checks should be carried out solely by the CFCD.

- Contracting Authority’s independence – to ensure selection of the evaluation committee members respecting the given criteria (no conflict of interest, adequate experience in the area of tender etc).

NAO services will officially reply to these findings in the forthcoming period, through narrative explanation of the progress made thus far and plan for mitigation of the new findings.

Also as per the IPA Component for Transition Assistance and Institution Building (IPA C I) - ANNUAL AUDIT WORK PLAN 2014 during October 2013 the Audit Authority undertook follow up of activities taken according to issued recommendation from system missions in 2011, 2012 and 2013 in IPA Structure for IPA C1 (NF, NIPAC office, CFCD and IPA Structure in Line Ministries/Beneficiary Institutions).  The follow up is organized in two phases: the first one being the desk review of the reported progress made by the auditees, and the second phase, if deemed necessary filed visits.

The findings of the Audit Authority will be provided in written report to NAO in the forthcoming period.

## Administrative capacity

Strengthening the administrative capacity of the Operating Structure has been a priority in the reporting period. The development of administrative capacity is based on the results of the Workload Analysis (WLA) and the Training Need Analysis (TNA) that are conducted on regular basis.

The need of further enhancing the capacities, expertise, knowledge and skills of IPA structures as of key importance for effective and efficient implementation of pre-accession assistance is fully acknowledged by all bodies involved with projects implementation.

Strengthening the administrative capacity was based on two premises:

- Recruitment of new staff with needed qualifications and following established transparent procedure; and

- Further development of capacities of existing staff through trainings, coaching and on-the job support.

In terms of latest changes in the DIS:

- New NIPAC was appointed on 5 March 2013 (Decision No. 41-1580/1).  The Decision has been published in the Official Journal on 13 March 2013;

- New SPO in Public Revenue Office has been appointed on 13.03.2013;

- New SPO in the Ministry of Health has been appointed on 09.05.2013;

- New SPO in Institute for Standardisation has been appointed on 27.03.2013;

- National Fund has been upgraded to a Department within the Ministry of Finance as of 01.07.2013;

- Head of NF Department has been appointed on 17.07.2013;

- New SPO in Ministry of Environment and Physical Planning has been appointed on 06.11.2013.

For all these changes, NAO has been officially informed European Commission.

### Trainings of OS staff

TNA

In the period December 2012 through March 2013, regular annual activity regarding Training Needs Assessment was conducted and completed.  The target group of this activity was the overall Operational structure of component I. The month of December 2012 was dedicated to the first phase of this activity, updating/developing the TNA questionnaire, based on the already established practice and the previously conducted TNAs for the OS of Component I.  By the end of the month the TNA Questionnaire was launched. The process of collecting of the filled in TNA Questionnaires followed in the next two months.  For the first time the SEA Training Center, produced report and analytical data of the overall activity.  This report provides data for the needs of training and capacity building activities, most needed topics and an Operational plan for addressing the same, and provides the basis for creation of Development/Operational plan for 2013.

The Development Plan was produced in the first quarter of 2013.

In the course of May 2013, the TC SAEW undertook the work on the development of form, its dissemination and collection regarding the Individual training plan of each respondent from the OS of IPA component I.  This activity was completed at the end of June 2013.  A process of analysis and feeding of the ITPs in a designed database shall follow in July 2013.

Training activities:

In the given period SEA TC, apart from regular activities related to IPA, on capacity building activities cooperated with several donors.

Notable cooperation was conducted with the Dutch assistance, the programme MATRA Patrol fro which the focal point for Macedonia is TC SEA.  Another donor that assisted in this case, the particular needs for capacity building of the SEA TC was the French assistance through l’ENA.  The same donor in cooperation and coordination with SEA also conducted training in Negations’ skills development.

In the stated period short introductory trainings-presentations on the topics of EU2020, and the translation process of acquis communautaire were organized, as well as one on IPA generic training.

An overview of these activities, conducted in the period January – June 2013, is provided in the table bellow.

| Title of trainings | Timeline | Organizer | Venue | No. of participants |
| --- | --- | --- | --- | --- |
| TNA (design, testing, launching, dissemination, collection, feeding, analysis, reporting) | December 2012 – April 2013 | SEA TC | Skopje | 201 |
| Quality, implementation and enforcement of legislation | 13-23.01.2013 | MATRA Patrol Dutch assistance | Хаг, Холандија | 3 |
| Alternative Dispute Resolution | 13-23.01 2013 | MATRA Patrol Dutch assistance | Хаг, Холандија | 4 |
| Integrity of Civil Servants | 04-13.03.2013 | MATRA Patrol Dutch assistance | Хаг, Холандија | 4 |
| Quality, Application and Enforcement of Legislation | 07-17.04 2013 | MATRA Patrol Dutch assistance | Хаг, Холандија | 3 |
| Public Finance Management | 07-17.04 2013 | MATRA Patrol Dutch assistance | The Hague Holland | 3 |
| „EU Negotiations“ | 10.04.2013 г. | SEA and ENA (French bilateral assistance) | Parliamentary Club | 22 |
| “EUROPA 2020” | 12.04.2013 г. | SEA | Training Center | 9 |
| “ЕUROPA 2020” | 18.04.2013 г. | SEA | Training Center | 7 |
| “Acquis Communautaire” | 19.04.2013 г. | SEA | Training Center | 5 |
| „Institutional support for the Training center “ | 23-25.04.2013 г. | SEA and ENA (French bilateral assistance) | Training Center | 4 |
| Individual Training plans (desing, dissemination, collection) | May – June 2013 | SEA TC | Skopje | 150 |
| “Introduction to EU and IPA“ | 19-20.06. 2013 | SEA | Training Center | 12 |

On 25 September 2013 under the contract between SEA and Auktoritas a public call was published asking for express of interest in preparation and delivery of several trainings on the Project Cycle Management.  A team of 4 trainers will be selected and deliver the trainings by end of 2013 for all the newcomers in the IPA structures.

## Monitoring

The aim of Monitoring is to provide continuous and systematic information (quantitative data) collection on progress with projects/programmes implementation to correct any deviation from the operational objectives, and thus improve the performance of the project/programme as well as facilitate subsequent evaluation. Monitoring enables the responsible bodies to timely deal with any problems, improve performance, build on successes and adapt to changing circumstances.

Some reporting and monitoring activities are undertaken by the Government in order to follow up the progress in implementation of IPA.  Hence, since 2011 on regular mi-monthly basis, there a submission on IPA issues by NIPAC office to the Government.    The template of reporting has been evolving with time and the latest template has been requested by the current NIPAC.  The idea is to follow up all IPA projects divided in 4 degrees of risk.  The current monitoring and reporting is decided to proceed on one month basis, as of 26.06.2013.

### Monitoring at Contract Level

CFCD has prepared a Detailed Monitoring Plan, based on the Indicative monitoring Plan presented to the TAIB SMC in October 2011. The Detailed Monitoring Plan is to be regularly updated, following the signature of a new contract, or findings in reports/from on the spot checks, recommendations from EC, auditors, ROM, etc.

### Monitoring at Programme Level (TAIB Sectoral Monitoring Committee)

The Programme monitoring activities by the Government are strengthen with series of meetings held on 11-15 April 2013 events organized on highest political level –the Prime Minister, the line ministers and representatives from the EUD.

Apart from the concrete conclusions for each of the IPA projects there were several general comments that are related to:

- Regular exchange of information between SEA and EUD based on the tables presented by SEA.

- All the Directorate Generals that are sending communication to respective institutions to copy the communication to NIPAC (this especially concerns DG Agriculture and Rural Development).

- EUD to present a list of risky projects from National Programme 2010 (IPA Component 1 – TAIB) as per the risk calculated totaling 21 million euro, as per the letter sent from H.E. Aivo Orav to the Prime Minister.

- SEA to inform the Government regarding the activities undertaken for Programming of IPA for the programming period 2014-2020.

- SEA to send the tables for revision to the IPA Beneficiary institutions on a bi-monthly basis.   The IPA Beneficiary institutions should revise the table within three days from submitting.  SEA to inform the Government for the advancement in IPA Implementation on a bi-monthly basis.

- All ministers whose institutions are IPA beneficiaries should not employ the IPA staff with obligations outside the scope of IPA structure, without having previous permission from the Government. If such an action appears to be a necessity, the ministers should inform the Government and the SEA with the purpose of obtaining such permission from the Government.

- All ministers should follow the deadlines for starting the procedures for procurement and implementation of projects. In this respect, SEA should follow the realization of the agreed deadlines and in cooperation with the respective minister should inform the Government for every deviation from the timeline, and the reasons for the missing the deadlines.

- EUD to give a contribution towards respecting the deadlines given in the procurement plans.

- SEA should engage involvement of representatives from CFCD and DEU in revision of documents and tender dossiers within the most risky projects.

- All ministers whose institutions are IPA beneficiaries, together with the appointment of members in the tender evaluation committees, should appoint them within 10 days, before the deadline for submission of offers ends.

- EUD to inform regarding the extension of the contracting deadline for NP 2010, instead of 1.12.2013 to be 1.12.2014.

- SEA in cooperation with Ministry of Finance to submit official letter to Mr. Stefano Sannino, Director General for Enlargement as well as a copy to the World Bank in order to include the World Bank in the implementation of the project for support of the IPARD Agency in accreditation of new measures through IPA 2010 in amount of 1.100.000 EUR by 16.04.2013.

- SEA in cooperation with the Ministry of Finance shall each two months organize coordination meeting for IPA with all of the ministers whose institutions are IPA beneficiaries and representatives of EUD.

The monitoring and coordination meetings continued to be organized and held during the summer holidays and nowadays, every single week.  The NIPAC office developed an online application for regular update of the state of play hence regular updates submissions were sent to Government sessions.

In concluding, as a result of these meetings the commitment of the Government towards effective and efficient use of IPA funds is increased, through higher level of awareness of the IPA portfolio, especially the issues and concerns of the Operating structures and the speeding up of the decision making.  Namely:

- The meetings are conducted starting from 11 July 2013.

- So far there are more than 220 conclusions.  70 % out of 220 conclusions are met timely, 10% are ongoing activities, 10 % have delays in meeting the deadlines imposed by the conclusions and 10% are suggestions towards the EUD.

- Regular preparatory documents are drafted for each session of the mIPA meetings including follow up of the conclusions; new update of the implementation of IPA projects; dossiers that CFCD has sent it to EUD and are waiting to be ex-ante controlled.  .

- Numerous discussion topics have been put on table during these meetings such as:

- Possibility for secondement of IPA structures from the line ministries into CFCD on timely basis;

- Depts. and challenges that are deriving from the offsetting procedure taken by the DG Budget;

- Discussion on the project/sector fiche/s and Financial Agreement modifications, use of PPF, programming of 2014-2020 etc.

- Monitoring is done on all the tendering and contracting phases especially for the risky projects and according to deadlines identified.

- Deadlines for evaluations of the risky file have been discussed as general rule and attention was paid to the independence of the evaluation committee members, the availability of these members and the confidentiality and impartiality of the evaluation process.

### Result Oriented Monitoring

Upon proposal from EUD, the current ROM contractor that is conducting the ROM in the country for the project from National Programmes 2007-2008, an agreement was made to include several ongoing IPA 2009 National Programme projects in the mandate of the ROM contractor.

Hence on 21 January 2013, NIPAC office met with the Deputy Team Leader from the ROM-WBT contract as to arrange the details about the forthcoming procedure.

During February 2013 an ad-hoc procedure was agreed encompassing the National ROM procedure and the contact arrangements from ROM-WBT.

The subject of ROM, under this contract will be the following DIS projects:

1.  Twinning contract for assistance to the Commission for protection of competition for state aid control

2.  Twinning contract for support to the State Statistical office for capacity building and improving compliance of statistics with EU standards

3.  Twinning contract to the National Police and Criminal Law Reform

4.  Service contract for management support to the Integrated Tariff Environment (TTE) systems

5.  Service contract for development of the Integrated Tariff Environment (ITTE) system.

In the reporting period the ROM contractor undertook three ROM missions, as follows:

| Start and End Date of Mission | Budget spec | Nature | Title |  | Planned amount in EUR |  | Nr. of ROMs | Last ROM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 21/01/2013-01/02/2013 | Over1MIL | Service | Implementation of the New Computerised Transit System (NCTS) |  | 1.550.000,00 |  | 2 | сеп.12 |
| 21/01/2013-01/02/2013 | Over1MIL | Service | Management Support to the New Computerised Transit System (NCTS) Implementation |  | 1.490.000,00 |  | 2 | сеп.12 |
| 21/01/2013-01/02/2013 | ex-post | Service | Support to more efficient, effective and modern operation and functioning of the Administrative Court |  | 1.083.500,00 |  | 2 | апр.11 |
| 21/01/2013-01/02/2013 | ex-post | Service | Further strengthening of the institutional capacities of the Academy for the Training of Judges and Prosecutors |  | 853.000,00 |  | 2 | апр.11 |
| 21/01/2013-01/02/2014 | ex-post | Service | Support to the implementation of the Roma Strategy |  | 595.800,00 |  | 2 | јул.12 |
| 18/03/2013-29/03/2013 | ex-post | Action Grants | Implementation of Juvenile Justice Reforms | 700.000,00 € |  |  | 0 |  |
| 18/03/2013-29/03/2013 | ex-post | Service | Development and implementation of agri-environment measures | 676.190,76 |  |  | 0 |  |
| 18/03/2013-29/03/2013 | ex-post | Service | Support to the Directorate for Personal Data Protection (DPDP) | 599.150,00 |  |  | 2 | мар.12 |
| 18/03/2013-29/03/2013 | ex-post | Service | Technical assistance to the Parliament | 599.999,95 |  |  | 2 | мар.12 |
| 18/03/2013-29/03/2013 | ongoing | twinning | Twinning: Assistance to the Commission for Protection of Competition for State Aid Control | 1.000.000,00 |  |  | 0 |  |
| 03/06/2013-14/06/2013 | Under1MIL | Service | Information & Communication Programme |  |  | 400.000,00 | 0 |  |
| 03/06/2013-14/06/2013 | ex-post | Service | Technical Assistance to the State Statistical Office |  |  | 1.793.280,00 | 2 | јул.11 |
| 03/06/2013-14/06/2013 | Over1MIL |  | Twinning- Support to the National Police and Criminal Law Reform |  |  | 1.080.000,00 | 0 |  |
| 03/06/2013-14/06/2014 | Over1MIL |  | Twinning: Support to the State Statistical Office for Capacity Building and Improving Compliance of Statistics with EU standards |  |  | 1.196.043,00 | 0 |  |
| 03/06/2013-14/06/2013 | ex-post | Service | Technical assistance for capacity building of the Institute of Accreditation |  |  | 597.620,00 | 0 |  |
| 16/09/2013-27/09/2013 | Over 1MlL | Service | Management support to the Integrated Tariff Environment Systems |  |  | 998.750 | 0 | n/a |
| 16/09/2013-27/09/2013 | Over 1MlL | Service | Development of the Integrated Tariff Environment Systems |  |  | 1.400.000 | 0 | n/a |
| 16/09/2013-27/09/2013 | Ex-post | Service | Technical Assistance to the Institute for Standardisation |  |  | 55.902 | 1 | March 2012 |
| 16/09/2013-27/09/2013 | Ex-post | Service | Strengthening the capacity of the Institutions to manage and implement the Operational Programmes |  |  | 1.599.710 | 2 | July 2012 |
| 16/09/2013-27/09/2013 | Over 1MlL | Service | Technical Assistance for the implementation of TETRA 3 |  |  | 798.600 | 0 | n/a |

Thus far, six projects have been subject to ROM in decentralised manner and four ROM Monitoring reports have been submitted to NIPAC.

A pilot of 9 projects has been analysed in relation to the grades given to the 6 criteria:  relevance, quality of design, efficiency, effectiveness, impact, potential sustainability graded with A –very good, B-good, C-problems and D serious deficiencies.

Out of 9 projects in the criteria:

- Relevance: 6 projects graded very good and 3 projects good.

- Quality of design: 1 project graded very good and 8 projects graded good

- Efficiency:  1 project graded very good, 5 projects graded good and 3 projects graded problems

- Effectiveness:   6 projects graded good and 3 projects graded problems

- Impact:  2 projects very good, 5 projects graded good and 1 project graded problems

- Potential sustainability: 8 projects graded good and 1 project graded problems

The problems registered are related mostly to efficiency, effectiveness and sustainability in the areas of using the project funds for meeting the project results, the use of Short term experts, the lack of personal to take on the project results, poor quality of reports especially that the Consultants are not referring the Log frame and Objectively Verifiable Indicators, lack of budget for continuation ensuring the sustainability….

The key observations are related to:

- limited impact;

- lack of staff retention;

- delay with implementation;

- poor coordination mechanisms among the beneficiary institutions;

- poor timetable planning;

- limited visibility of projects;

- poor backstopping facility support by Contractors.

## Evaluations

The interim evaluation activities have been dependent on the procurement of an expertise via Project Preparation Facility 2009.  After the first unsuccessful tender, the Terms of Reference have been redrafted and sent to EU Delegation for ex-ante approval.  The evaluation of offers was done from 16-23 August 2013 and the contract was signed in September 2013.  While preparing for the kick off meeting, the SEA sent all the necessary documentation to the Contractor who informed the Contracting Authority that the Team Leader has resigned due to medical reasons.  The Contractor sent new proposal for Team Leader and the proposals were evaluated in November 2013.  The start of the project is still pending.

# Programme Publicity and Visibility

The activities related to publicity and visibility in the reporting period is related to the training of the national administration via the French Bilateral cooperation.  Hence two events have been organised as follows:

## How to create a great audience event” on 5 & 6th of March 2013;

## IPA Funds and social media” (28-29th of May 2013)

Some communication and visibility activities were undertaken during the Europe’s day festivities where NIPAC and his team paid visits to many municipalities together with the EUD and Ambassador Aivo Orav.  The idea was to visit IPA projects in implementation and sharing information on IPA possibilities and opportunities.

More intensive activities in this area have been initiated by NIPAC, during team building that has been organized in Berovo on 16-18 June 2013.  Following this initiative, SEA proposed to the Government to approve the General Strategy on communication for IPA.  This Strategy was discussed and approved on 149th Government session held on 14.08.2013, where as NIPAC is envisaged to act as an initiator and head institution in publishing relevant news about IPA.  The communication concept and communication and visibility ideas eventually were drafted in one PPF 2009 project that is being prepared and is expected to be contracted by 21.12.2013.

Also, in the reporting period SEA web site was revised and new and updated information on IPA were published.  Finally there is a current discussion on the ways to amend the Rules of Procedure of the TAIB Sectoral Monitoring Committee in order to ensure more transparency of the held sessions and availability of relevant data to the public.

This year the Parliament of the Republic of Macedonia expressed their interest for control and monitoring of IPA for which several sessions (11 and 26 July and 7-9 October) have been organized and held in the period July-October 2013 as per the 2010 Law on Assembly (more specifically the Articles 20-23).    The organizer of these hearings was the Parliament’s Commission on European Affairs in cooperation with the Parliamentary Institute.

Finally on 12-13.10.2013 a Regional conference on Parliamentary oversight of IPA funds took place, organized by Network of Parliamentary committees for economy  and finance of the Western Balkans and Westminster Foundation for Democracy.

# Cooperation with Civil Society Organisations

The participation of the CSOs will continue to be ensured as per Article 83 paragraph 3 of the IPA Implementing Regulation. The CSO representatives will be invited before TAIB SMC meeting taking place for preparatory purposes.

The active participation of the CSO will be also ensured during consultation process for finalisation of the Country Strategy Paper for IPA 2014-2020 and the annual programming exercise for 2014.  The concept for long term consultations is being prepared, after a meeting between NIPAC office and CSO representatives that took place on 27.06.2013.

A presentation by NIPAC and EUD of the Country Strategy Paper took place on 26.09.2013 whereas a great number of CSO in Macedonia participated and expressed their readiness to assist the Government in designing and future use of IPA 2.

Also, in the context, and following the previous consultations and discussions on the concept behind the Country Strategy Paper for the Republic of Macedonia, the EU Delegation sent on 4.10.2013 to the civil society representatives,  the core part of the document (Country Strategy Paper, Section IV) "EU Assistance in the period 2014-2020" for comments and reviews.

The feedback was expected to be sent by 18th of October 2013.

In the reporting period, NIPAC office drafted a public call for selecting CSO in the IPA 2 working groups.  The draft call was shared with the EUD in order to consolidate the final call.  However, the publication is put on hold due to finalisation of the number and type of sectors to be supported by IPA 2.

# Overview of the upcoming period:

- The timely procurement of the outstanding contracts from IPA 2009 National Programmes remains high priority, due to the contracting deadline 21 December 2013.

- The speed up of the procurements envisaged within the 2010 and 2011 National Programmes.

- Preparatory procurement activities for the National Programme 2012 to be initiated.

- Implementation of the contract and conducting of regular monitoring activities over the contracts signed and project implemented.

- The implementation of the PPF project on Interim evaluation is expected by last quarter of 2013.

- National authorities will work in further strengthening of the functioning of the sound financial management via lessons learned and mitigation of the findings of the last audit reports by the IPA Audit Authority and the DG Enlargement auditors.

Council Regulation (EC, Euratom) No 1605/2002 of 25 June 2002 on the Financial Regulation applicable to the general budget of the European Communities (OJ L 248, 16.9.2002, p. 1), as last amended by Council Regulation (EC, Euratom) 1995/2006 of 13 December 2006 (OJ L 390, 30.12.2006, p. 1).

Commission Regulation (EC, Euratom) No 2342/2002 of 23 December 2002 laying down detailed rules for the implementation of Council Regulation (EC, Euroatom) No 1605/2002 (OJ L 357, 31.12.2002, p. 1), as last amended by Commission Regulation No 478/2007 of 23 April 2007 (OJ L 111, 28.4.2007, p. 13).

NIPAC requested modification of the Financing Agreement in order to extend the contracting deadline for one additional year.  The approval process with the Commission services is ongoing.

Annex 4 – Procurement Plan for IPA 2010