ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Secretariat for European Affairs

## Country background

The Stabilisation and Association Agreement (SAA) between the Republic of North Macedonia and the European Union entered into force in April 2004 and continues to be implemented. Since 2009, the Commission has continuously recommended to the Council to open accession negotiations with North Macedonia, a candidate country since 2005. Based on the progress achieved and the conditions having been met, the European Council endorsed the Council’s decision to open accession negotiations with North Macedonia in March 2021. Overall, the country has continued to maintain a steady and determined pace in advancing EU reforms, focusing on the fundamentals. Pending bilateral issues between Bulgaria and North Macedonia need to be resolved as a matter of priority. The authorities in North Macedonia continued to demonstrate publicly their commitment to advance on their EU path. The delays in the official launch of accession negotiations are having a negative impact on the credibility of the EU.

Media is recognized as one of the key stakeholders in the strategy for information and communication to the public about the process of EU integration of the country. Reporting about the EU and the accession path requires special skills and knowledge of the EU, its key institutions, their competencies and procedures, the decision-making process as well as the responsibilities of national and sub-national institutions. The activities described in this Terms of Reference (ToR) build upon the activities already implemented by the EC Support for Progress of North Macedonia Project through the Secretariat for European Affairs.

## Current situation in the sector

Both Deputy Prime Minister and the National IPA Coordinator office play crucial role in EUSAIR implementation, primarily based on their responsibilities for coordination of disbursement of available IPA funds, as one of the main identified sources of funding for the Strategy. This is becoming even more evident with the introduction of the “embedding process”, i.e. the assessment of possibilities for alignment of funding through inclusion of macro-regional priorities in mainstream programmes.

The EU Strategy for the Adriatic and Ionian Region (EUSAIR) is a macro-regional strategy adopted by the European Commission and endorsed by the European Council in 2014. The Strategy was jointly developed by the Commission and the Adriatic-Ionian Region countries and stakeholders, which agreed to work together on the areas of common interest for the benefit of each country and the whole region. The EUSAIR covers ten countries: four EU Member States (Croatia, Greece, Italy, and Slovenia) and six non-EU countries (Albania, Bosnia and Herzegovina, Montenegro, North Macedonia, San Marino, Serbia). As North Macedonia continues its EU integration process, different levels, contribute to the achievement of economic, social and territorial cohesion of the macro regions. Macro-regional strategies serve as open and dynamic platforms for strategic networking, as well as for coordinating common policies and activities that transcend national borders. North Macedonia became member of this project in November 2021.

# OBJECTIVES & EXPECTED OUTPUTS

A comprehensive visibility and communication plan will be developed in accordance with the requirements for EU-financed external actions. Higher emphasis within the plan will be given on applying visibility and communication tools of digital nature, not excluding however usage of the more traditional ones as well.

## Overall objective

The overall objective (Impact) to which this action contributes is:

- The overall objective of the intervention is to communicate the benefits of the participation of North Macedonia in the EUSAIR Strategy in terms of regional development and regional cooperation with the participating countries.

## Specific objective(s)

- The specific objectives of this contract are as follows:

- To raise awareness on the Strategy among various governmental and nongovernmental stakeholders at both national and local level in order to contribute to the EUSAIR communication visibility activities, with a specific emphasis on digital communication.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- The selected contractor will plan and develop the most effective approach and methodology and carry out the subsequent activities for the successful completion of the intervention;

- Developing and implementing detailed communication strategy;

- Develop a detailed action plan with the proposed time frame, topics covered, tools used, and implementation methodology in coordination with the project;

- Provide the concept for the events, including the suggested topics, formats, and dates for the organization;

- Secure media presence at all events – informational sessions/conferences at local level (1 per planning region and 1 international, 9 in total);

- Production of 9 short videos with duration of 120 to 160 seconds (and subtitles in Macedonian, Albanian and English); Graphic services for up to 26 designs for the social media pitches, 26 info graphics, and content for the web portal and other external communication channels (all in Macedonian, Albanian and English); Provide content and writing support of at least 26 press releases, 26 social media pitches, 12 speeches (in Macedonian, English, or Albanian as required);

- Preparation and distribution of press packs and hand-outs;

- Design and printing 500: Notebooks A5, Pens, Folders in accordance with EU visibility guidelines;

- Design and printing 2 Banners;

- Prepare and send media invites and information after event with photos or video through the social media network;

- Schedule 3 interviews and/or TV appearances of representatives of EUSAIR experts or National coordinator within the SEA;

- Develop a crisis communication plan for the work of the project that will include possible scenarios and adjustments of communication activities for the period of implementation of activities;

- Conduct a comparative analysis of the communication activities of similar project within EUSAIR. Based on the finding of the comparative analysis, provide recommendations for best communication practices to be adapted to project context.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Key assumptions for achieving the results include:

- SEA follows and supports established EUSAIR strategy and its pillars;

- SEA organises informational sessions/conferences at local level;

- Partner countries amicably share info and speakers for EUSAIR flagships and other events and news

- The Contractor remains committed to its obligations under the Agreement with a clear and full understanding of the contract objectives and purposes.

- Continuous communication and provision of information between the Project Team and the Contractor;

- Functional and effective co-operation between Contracting Authority and the selected Contractor.

## Risks

The main risk which can undermine project effectiveness and efficiency are:

- Insufficient support by SEA due to institutional changes;

- Insufficient support for EUSAIR strategy and its pillars by partner countries;

- Insufficient support by the centres for development of planning regions in organizing informational sessions/conferences at local level.

# SCOPE OF THE WORK

## General

### Description of the assignment

The contractor will proactively contribute in developing and implementing detailed communication strategy in accordance with the action plan with editorial content (stories, photos, advocacy images, audios, videos, info graphics, etc.) related to promotion of Project activities in conjunction with the project staff, and adapt them for media pitching, social media, and enabling posting daily/weekly to respective channels by implementing organizations. The contractor will produce a web and social media plan (including calendar) for the content themes and all upcoming coverage schedules according to the calendar approved by the implementing organizations. The contractor will prepare social media packs for promotion of the activities and share them with stakeholders. Additionally, the company will actively engage with online audiences through social media channels, republishing social media posts in close cooperation with Project staff and SEA coordinator.

### Geographical area to be covered

The Project’s activities are related to the implementation of EUSAIR in the Republic of North Macedonia and its 8 planning regions.

### Target groups

Target groups are:

- Local government units,

- Business sector,

- Educational institutions,

- Civil society sector and

- Other public institutions.

## Specific work

The following tasks will have to be undertaken by the selected company:

- Developing and implementing detailed communication strategy/action plan - to attract wider interests and raise public awareness related to the importance of the EU integration process in terms of regional cooperation/ funding and boost the visibility by clarifying to the public the impact of major concepts in the EUSAIR pillars.

- Production of 9 short videos with duration of 120 to 160 seconds (and subtitles in Macedonian, Albanian and English). They will be produced in full HD resolution including pre and post production services, development of scenarios, recording and video and sound editing and graphic design. The draft version of the produced videos will be approved by Project coordinator and National Coordinator in SEA.

- Graphic design services for up to 26 designs for the social media pitches, 26 info graphics, and content for the web portal and other external communication channels (all in Macedonian, Albanian and English). The draft designs and PR texts will be approved by Project coordinator and national coordinator in SEA.

- Provide PR support of at least 26 press releases, 26 social media pitches, 12 speeches (in Macedonian, English, or Albanian as required). The draft designs and PR texts will be approved by Project coordinator and national coordinator in SEA.

- Printing 500: Notebooks A5, Pens, Folders in accordance with EU visibility guidelines. Two banners for the events will be also designed and printed by the company.  The draft designs will be approved by Project coordinator and national coordinator in SEA.

- Inception, interim and final reports.

- Writing of different kinds of contents/information for SEA website in Macedonian, Albanian and English as needed.

- Preparation of social media editorials (key messages with photos/videos/animations or similar) in Macedonian, Albanian and English based on EUSAIR inputs (data, events, reports, publications, etc.)

- Preparation, implementation, monitoring and evaluation of social media advertising

- Support for design of promotional material and its production as needed

- The PR consulting agency will work closely with the National EUSAIR coordinator and EUSAIR project team.

## Project management

### Responsible body

The Contracting Authority for the project shall be SEA. As such it is responsible for developing this ToR and the tendering documentation for the required service, as well as for inviting selected Company to submit a bid, in accordance to this ToR, and will make the selection of the best candidate. The Contracting Authority will be responsible for providing project related information to the Contractor for performance of the tasks, as well as organize translation of social media posts in Macedonian/Albanian/English language.

### Management structure

The Project “EU support to implementation of the EU Strategy for the Adriatic and Ionian Region (EUSAIR) in North Macedonia” is implemented by SEA, which will have the overall responsibility.

### Facilities to be provided by the contracting authority and/or other parties

No facilities will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

Company premises.

The Project’s activities such as informational sessions/conferences at local level (1 per planning region, 8 regions in total) will be held in various cities of the Republic of North Macedonia.

## Start date & period of implementation of tasks

The intended start date is 27/02/2023 and the period of implementation of the contract will be 12 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organizations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are listed and they must submit CVs and statements of exclusivity and availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Senior Media Expert

Qualifications and skills:

- The candidate should have relevant university degree (i.e. social science, communication, public relations, journalism, marketing or related degrees preferably with a post-graduate degree;

General professional experience:

- Proven working experience in PR, communication, (social) media marketing and visibility on projects and EU- related matters of at least 5 years;

- Excellent communication and interpersonal skills, able to involve diverse stakeholders, and to achieve constructive outcomes;

- Demonstrated social networking experience and social analytics tools knowledge;

- Positive attitude, detail and customer oriented with good multitasking and organizational ability;

- Excellent written and oral skills in English and Macedonian. Albanian will be consider a plus

- Specific professional experience: Experience in public relations, communication and visibility, social media contents production and management

The expert must be independent and free from conflicts of interest in the responsibilities they take on.

Qualifications and Background

- Minimum five years of professional experience in communications, public relations, journalism, marketing or a related field, working with public institutions, projects and international institutions in the EU related fields

- Creativity, originality, punctuality, high level of organization and efficiency. Capability and proven experience crafting high impact content in various formats (press releases, content for websites, video, blog, social media posts, audio, etc., storytelling, ability to spot a newsworthy story, etc.) targeting different audience segments regarding the single project;

### Other experts, support staff & backstopping

- The team must consist of at least two team members – experts. Each team member has a minimum 3 years of professional experience relevant for the ToR. Each team member has proven expertise in realization of campaigns in at least 3 EU funded projects.

- At least one team member has proven expertise in realization of campaigns engaging government institutions.

- At least one team member has excellent digital skills in graphic design,

- Excellent writing, editing (photo/video/text), and presentation skills

- Knowledge of (online) marketing tools and good understanding of digital marketing and social media channels (different experts if needed);

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation of a reasonable standard and space for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular, it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English language in one original and through e-mail to the Project office for the duration of this Contract copes:

- Inception Report of maximum 10 pages to be produced after 2 weeks, from the start of implementation. In the report the contractor shall describe e.g., initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report. Accepted inception report must be provided along with the corresponding invoice

- Interim Reports of maximum 10 pages to be produced after 3, 6 and 9 months from the start of implementation of the project. Interim reports will comprise information on completed activities: designs, press releases, banners, videos, info graphics, social media pitches, speeches, social media posts. Accepted interim report must be provided along with the corresponding invoice.

- Those reports shall be submitted no later than 15 days after the period of implementation of appointed dates.

- Final report will be prepared 20 days after the period of implementation. The report shall contain a sufficiently detailed description of the realized activities: designs, press releases, banners, videos, info graphics, social media pitches, speeches, social media posts etc. The detailed produced documents/outputs will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice

## Submission and approval of reports

The report referred to above must be submitted to the project coordinator identified in the contract. The project coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Prepared project progress reports

## Special requirements

N.A.