ACTION PLAN 2026 – 2027

FOR THE IMPLEMENTATION OF

THE SMART SPECIALISATION STRATEGY

OF THE REPUBLIC OF NORTH MACEDONIA

S3-MK 2024-2027

JUNE 2026

# LIST OF ABBREVIATIONS

AQHE  		Agency for Quality in Higher Education

AFIEP		              Agency for Foreign Investments and Export Promotion of the Republic of North Macedonia

HEI    		              Higer Education Institutions

SOIP		              State Ofiice of Industrial Property

SSO			State Statistical Office

DIH			Digital Innovation Hub

DTIDZ		              Directorate for Technological Industiral Development Zones

EDIH			European Digital Innovation Hub

ЕDP		              EDP Enterpreneurial Discovery Process

EBRD			European Bank for Reconstruction and Development

EEN			Enterprise Europe Network

ЕIT RIS HUB	              European Institute of Innovation and Technology Community Regional Innovation Scheme Hub

ETF		              European Training Foundation

JRC			Joint Research Centre

IPA 			Instrument for Pre-Accession Assistance

RD&I			Research Development and Innovation

PRI			Public Research Institution

PI			Public Institution

OPGRNM		Office of the President of the Government of the Republic of North Macedonia

TTO			Technology Transfer Office

MBA			Macedonian Banking Association

MDT			Ministry of Digital Transformation

MEL			Ministry of Economy and Labour

MOEPP		Ministry of Environment and Physical Planning

MAFWE		Ministry of Agriculture, Forestry and Water Economy

MES			Ministry of Education and Science

MSPDY		Ministry of Social Policy Demographics and Youth

MF			Ministry of Finance

NBRNM		National Bank of the Republic of North Macedonia

BSO			Business Support Organisations

DBNM		              Development Bank of North Macedonia

RCC			Regional Cooperation Council

ECNM		              Economic Chamber of North Macedonia

TRIPs		              Thematic Research and Innovation Platforms

AEC		              Adult Education Centre

CVET		              Centre for Vocational Education and Training

BED                                Bureau for Educational Development

INOVA                            Agency for Innovation, Scientific and Technological Development and Enterpreneurship

MEMMR                        Ministry of Energy, Mining and Mineral Resources

SMEs                               Small and Medium Enterprises

| # PRIORITY AREAS : Smart agriculture and food with higer added value; ICT sector; Sustainable materials and smart buildings; Electro Mechanical Industry – Industry 4.0; Energy for the future; Tourism |  |  |  | LINK TO THE NATIONAL DEVELOPMENT STRATEGY 2024-2044: 5.1. STRATEGIC AREA: Sustainable, innovative and competitive economy Key goal: Economy based on Knowledge, Innovation and Digitalization |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGIC OBJECTIVE 1: CREATE FUNDATIONS FOR SCIENTIFIC EXCELLENCE IN S3 PRIORITY DOMAINS |  |  |  | Impact indicator: name of the indicator related to the Strategic objective - Improved scientific excellence and international competitiveness in S3 domains - Improved capacity of the research system to attract competitive international R&I funding in S3 priority domains Measured by: % increase in internationally peer-reviewed scientific publications in S3 domains % increase in successful participation of organisations from S3 domains in Horizon Europe and other international R&I programmes |  |  |  |  |
| Specific objecitve 1.1: To enhance scientific research capacity in S3 priority domains by strengthening human resources, improving accessibility and use of research infrastructure, and supporting demand-driven research aligned with business needs |  |  |  | Outcome indicator: Name of the indicator related to the specific objective - Increased number of highly qualified researchers in S3 domains - Improved quality and internationalization of research activities (3) - Increased volume of demand-driven research - Stronger science-industry collaboration in S3 domains |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| М1. Strenghtening human capacities for scientific research acitivity | А1 Funding scholarships for doctoral studies, international research stays and co-mentoring arrangements provided by international experts in S3 domains | Lead institution MES Institutions involved JRC | Q4 2026 |  | Q4 2027 | 24.800.000 MKD | State Budget of the Republic of North Macedonia | Number of PhD scholarships funded (5) Number of international research stays supported (5) Number of co-mentoring arrangements established (3) |
| М2. Improved accessibility and visibility of research infrastructure to the business sector | А2 Mapping of laboratories and services offered to companies from S3 domains | Lead institution MES Institutions involved HEI, PRI, companies | Q4 2026 |  | Q3 2027 | No financial implications |  | 1 publicly available catalogue/ database created Number of laboratories mapped Number of laboratory services identified Improved accessibility of research infrastructure Increased use of research infrastructure by companies Number of granted research project applications co-developed with the private sector (15) Number of project applications involving private sector partners |
| М3. Strenghten research collaboration | А3 funding of demand-driven research related to S3 domains with a focus on green and digital transition | Lead institution MES Institutions involved MEL, INOVA (in cooperation with universities, research institutes, business support organisations and the private sector)) | Q4 2026 |  | Q3 2027 | 18.600.000 MKD | State Budget of the Republic of North Macedonia | Number of approved applications for research projects developed in cooperation with the private sector (15) Increased number of project applications involving private sector partners Increased volume of demand-driven research |
| PRIORITY AREAS : Smart agriculture and food with higer added value; ICT sector; Sustainable materials and smart buildings; Electro Mechanical Industry – Industry 4.0; Energy for the future; Tourism |  |  |  | LINKAGE WITH THE NATIONAL DEVELOPMENT STRATEGY 2024–2044 5.1 Strategic Area: Sustainable, Innovative and Competitive Economy Objective: A knowledge-based, innovation-driven and digitalised economy Priority: An ecosystem that supports entrepreneurship and start-ups. |  |  |  |  |
| Strategic Objective 2 (General Objective 2): ENHANCING THE INNOVATION ECOSYSTEM |  |  |  | Impact Indicators (linked to the General Objective): Increased effectiveness of the national innovation ecosystem within the S3 priority domains. Improved performance of innovation actors in translating knowledge into market-oriented solutions. Measured by: Percentage increase in innovation-active enterprises within the S3 priority domains. Percentage increase in collaborative innovation projects involving research organisations, intermediary organisations and companies. |  |  |  |  |
| Specific Objective 2.1: Developing the institutional infrastructure and platforms for innovation, knowledge transfer and technology transfer |  |  |  | Outcome Indicators (linked to the Specific Objective): Preconditions established for advancing to the next stage in the establishment of the National Science and Technology Park (NSTP). Improved access to innovation and technology transfer services. |  |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M4. Preparation of steps for the establishment of the National Science and Technology Park (NSTP) | Action A4: Preparation of a feasibility study for the establishment of the National Science and Technology Park (NSTP) | Lead institution: INOVA Participating institutions: MES, MEL, MDT | Q3 2026 |  | Q3 2027 | 18.600.000 MKD | State Budget of the Republic of North Macedonia / Donors | One feasibility study completed |
| M5. Establishment of Innovation Centers/Technology Centers/Centers of Excellence/TTO | A5 Creating support centers for S3 domains | Leading institution MES Institutions involved INOVA , MAFWE, MEMMR, МЕL, MDT | Q3 2026 |  | Q4 2027 | 124.000.000 MKD | State Budget of the Republic of North Macedonia / Donors | 2 innovation centers created in the S3 domains |
| Specific objective 2.2: Improving research, development and innovation in small and medium-sized enterprises (SMEs) in cooperation with academic institutions, in line with the S3 domains |  |  |  | Outcome indicator: Name of the indicator linked to the specific objective - Increased RDI activity in SMEs - Improved access to external knowledge and expertise - Improved participation of SMEs and institutions in EU programmes related to S3 domains - Increased market uptake of innovative products and services - Increased commercialisation of RDI results through cooperation between SMEs and academic institutions |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M6. Providing non-financial/technical support to SMEs operating in the sectors of the S3 domains to implement research, development and innovation (RDI) in their operations | A6 Awarding innovation vouchers to SMEs for the procurement of services from external knowledge providers for the purpose of improving or innovating products or processes in accordance with the S3 domains | Lead institution: INOVA Institutions involved | Q3 2026 |  | Q4 2027 | 12.400.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Increased coverage of criteria for vouchers awarded Number of SMEs supported (20) Increased coverage of engaged external knowledge providers |
|  | A7 Technical support to key stakeholders (state institutions, universities, BSOs, research organizations, etc.) for the preparation of applications for participation in EU programs | Lead institution: INOVA Institutions involved: | Q3 2026 |  | Q4 2027 | 4.960.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Increased coverage of supported SMEs and institutions Number of applications prepared/submitted (20) |
| M7. Commercialization of innovation grants/ grants/loans/cost reimbursement for development of own products/market-close innovations | A8 Implementation of calls for awarding co-financed grants for the commercialization of innovations | Lead institution: INOVA Institutions involved | Q3 2026 |  | Q3 2027 | 62.000.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Number of calls published (2) Number of grants awarded (30) |
|  | A9 Grants for commercialization of innovations resulting from academia-business collaboration in RDI (research, development and innovation) | Lead institution: INOVA Institutions involved MES, MEL | Q3 2026 |  | Q4 2027 | 37.200.000 MKD | State Budget of the Republic of North Macedonia / Donor support | Number of Grants Awarded (10) Increased coverage of supported Academia-Business Partnerships |
| Specific objective 2.3: Supporting the development of innovative start up companies in S3 domains |  |  |  | Outcome indicator: Name of the indicator linked to the specific objective - Increased awareness and influx of innovative startups - Increased development of innovative startups - Improved market entry readiness - Improved efficiency and targeting of startup support instruments - Increased participation in European innovation programmes - Improved innovation capacity and growth of startups |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M8. Support for startups | A10 Organization of awareness-raising activities and events (hackathons and intensive trainings (bootcamps)) | Lead institution: INOVA Institutions involved: | Q3 2026 |  | Q3 2027 | 6.200.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Number of events organized (4) Number of participants – 100 potential startups |
|  | A11 Awarding co-financed grants in the S3 priority domains for startups and spin-off companies for innovative projects | Lead institution: INOVA Institutions involved: | Q3 2026 |  | Q4 2027 | 18.600.000 MKD | State Budget of the Republic of North Macedonia | Number of Grants Awarded (20) Increased Coverage of Supported Startups/Spin-Off Companies |
|  | A12 Conducting an impact assessment of the co-financing grant scheme for start-ups and spin-off companies. | Lead institution: INOVA Institutions involved: | Q3 2026 |  | Q3 2027 | 1.240.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Impact assessment report prepared (1) |
|  | A13 Co-financing of development/participation of companies (from priority S3 sectors) in EIT/EIC programs | Lead institution: INOVA Institutions involved: | Q4 2026 |  | Q4 2027 | 12.400.000 MKD | State Budget of the Republic of North Macedonia | Number of supported startups (3) Increased coverage of prepared/submitted applications |
| M9. Pre-acceleration and acceleration services | A14 Providing technical/consulting pre-acceleration and acceleration services for startups/spin-off companies | Lead institution: EDIH Institutions involved: INOVA, HEI | Q3 2026 |  | Q3 2027 | 3.720.000 MKD | State Budget of the Republic of North Macedonia | Number of supported startups / spin-off companies (20) Number of sessions / consulting services provided (10) |
| Specific objective 2.4: Raising awareness and establishing networks for S3 |  |  |  | Outcome indicator: Name of the indicator related to the specific objective - RIS of the year- Award - Adopted operational/planning document for networking to improve cooperation with relevant partners and stakeholders from the region and the EU |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M10 Annual Award for Best S3 Innovative Company | A15 Organization of an annual event for the awarding of the “Best S3 Innovative Company Award” | Lead institution: INOVA Institutions involved: | Q1 2027 |  | Q3 2027 | 2.480.000 MKD | State Budget of the Republic of North Macedonia | Organized Award Event (1) Methodology and Criteria for Selection of Companies Aligned with International Practices (‘”RIS of the Year”) |
| M11 Promotion of EU funding opportunities for S3 | A16 Providing information on existing funding opportunities from EU programs | Lead institution: EEN Institutions involved: INOVA, MES, MDT, МЕL, MOEPP | Q3 2026 |  | Q3 2027 | There are no financial implications. |  | Online one-stop-shop for relevant information on financing opportunities |
| M12 Strengthening network cooperation | A17 Development of an operational/planning document for networking to improve cooperation with relevant partners and stakeholders from the region and the EU | Lead institution: MES Institutions involved: OPGRNM, INOVA, МЕL | Q4 2026 |  | Q4 2027 | There are no financial implications. |  | Developed operational/planning document as a prerequisite for developing a network connectivity strategy |

| PRIORITY AREAS : Smart agriculture and food with higer added value; ICT sector; Sustainable materials and smart buildings; Electro Mechanical Industry – Industry 4.0; Energy for the future; Tourism | LINKAGE WITH THE NATIONAL DEVELOPMENT STRATEGY 2024–2044 5.1 Strategic Area: Sustainable, Innovative and Competitive Economy Objective: A knowledge-based, innovation-driven and digitally enabled economy Priority: An economic growth model driven by smart specialisation and the green transition. |
| --- | --- |
| Strategic Objective 3 (Overall Objective 3): Enhancing the Competitiveness and Green Transition of the Business Sector | Impact Indicator (linked to the Overall Objective): Visible growth in the number of small and medium-sized enterprises (SMEs) investing in the green and digital transition. |
| Specific objective 3.1: Increased access to finance for companies in S3 domains based on green and digital transformation | Outcome indicator: Name of the indicator related to the specific objective - Improved innovation capacity of small and medium-sized enterprises - Increased adoption of green and digital business practices - Improved access to finance for green and digital transformation - GBF Project Increased investments in environmentally sustainable business activities - Visible growth of companies that have created technology development and research units |

| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M13. Improved access to advanced business support and development services | A18 Provide regulatory access to vouchers and technical assistance cooperation that enable increased innovation by small and medium-sized enterprises and green business activities | Lead institution INOVA Institutions involved EDIH, MEL | Q3 2026 | Q4 2027 | 31.000.000 MKD | State Budget of the Republic of North Macedonia | Number of SMEs supported through technical assistance for innovation/green/digital transition (50) Number of SMEs introduced standards and certificates (30) |
| M14 Increasing the total volume of (private) investments by improving access to finance – loans/co-financing for green and digital investments | A19 Expansion of the banking loan portfolio for the green and digital transition | Leading institution NBRNM Вклучени институции MBA, DBNM | Q3 2026 | Q4 2027 | There are no financial implications |  | Number of SMEs financed through green/digital credit lines for projects related to energy efficiency, digital solutions/circular/green business activities (100) Number of new credit lines available for companies investing in green and digital activities (2) |
|  | A20 Implementation of financial support (co-grants) for small and medium-sized enterprises investing in green business activities | Lead institution INOVA Institutions involved | Q3 2026 | Q3 2027 | 1.550.000.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Number of SMEs receiving co-grants (50) Total amount of co-financed green investments (186,000,000 MKD) value of financial contribution from the private sector in the implementation of the projects |
|  | A21 Support for companies investing in expanding research and development based on green and digital transformation through the Law on Financial Support for Investments | Lead institution MEL Institutions involved | Q3 2026 | Q4 2027 | 5.084.000 MKD | State Budget of the Republic of North Macedonia | Increased coverage of supported projects for competitiveness, green and digital transformation |

| PRIORITY AREAS : Smart agriculture and food with higer added value; ICT sector; Sustainable materials and smart buildings; Electro Mechanical Industry – Industry 4.0; Energy for the future; Tourism | RELATIONSHIP WITH THE NATIONAL DEVELOPMENT STRATEGY 2024-2044: 5.1. STRATEGIC AREA: Sustainable, innovative and competitive economy Objective: Economy based on knowledge, innovation and digitalization |
| --- | --- |
| Strategic Goal 4 (Overall Goal 4): DEVELOPING HUMAN CAPITAL AND SKILLS FOR INNOVATION, GREEN AND DIGITAL TRANSFORMATION | Impact indicator: Name of the indicator related to the general objective - Share of employees applying newly acquired skills in their workplace within the Smart Specialisation (S3) priority domains. |
| Specific Objective 4.1: Enhancing the relevance of academic and secondary education programmes for the Smart Specialisation (S3) priority domains. | Outcome Indicators (linked to the Specific Objective): -Enhanced relevance of higher education programmes to the Smart Specialisation (S3) priority domains. -Increased student interest in study programmes related to the Smart Specialisation (S3) priority domains. -Current and future skills needs identified through evidence-based analysis. -Strengthened green and digital skills at the secondary education level. |

| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M15. Introducing new multidisciplinary study programmes with enhanced practical components and a focus on innovation, the green transition and the digital transition. | A22. Developing and updating higher education curricula for multidisciplinary study programmes aligned with the needs of the private sector. | Lead institution MES Institutions involved AQHE | Q3 2026 | Q4 2027 | There are no financial implications | There are no financial implications | Progress in the development of new and the revision of existing multidisciplinary higher education study programmes. Increased number of higher education study programmes developed in cooperation with private sector stakeholders. |
|  | A23. Promoting the adopted higher education study programmes / curricula | Lead institution MES Institutions involved HEI | Q3 2026 | Q4 2027 | 620.000 MKD | State Budget of the Republic of North Macedonia | Number of promotional events organised (10). Increased enrolment of students in newly introduced or updated study programmes. |
| M16. Skills for the Future | A24. Mapping skills needs for the Smart Specialisation (S3) priority domains | Lead institution MES Institutions involved ETF | Q1 2027 | Q4 2027 | 620.000 MKD | Donors | Mapping completed and published |
| M17. Introduction of new curricula for vocational education and training/general secondary education with a focus on sustainability and digitalization | A25 Developing new curricula for secondary education | Lead institution MES Institutions involved CVET, MES- BED | Q3 2026 | Q4 2027 | There are no financial implications |  | Increased coverage of newly adopted/updated secondary education curricula Visible growth in student interest in enrolling in adopted programs |

| Specific objective 4.2: Improving the skills and knowledge of employees in S3 companies |  |  |  | Outcome indicator: Name of the indicator related to the specific objective - Training programs are aligned with the real skills needs of companies S3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M18 Specialized training to improve the development of companies' skills | A26 Preparation of training programs for companies and their verification | Lead institution AEC Institutions involved | Q3 2026 |  | Q4 2027 | 930.000 MKD | Private sector | Number of training programs developed and validated with companies (5) Increased coverage of companies consulted during program development |
|  | A27 Implementation of specialized training to improve the development of companies' skills | Lead institution AEC Institutions involved МЕL, BSO, HEI, chambers of commerce | Q3 2026 |  | Q4 2027 | 3.100.000 MKD | State Budget of the Republic of North Macedonia | Number of employees involved in training (100) Increased coverage of companies participating in training Number of trainings organized (10) |

| # PRIORITY AREAS : Smart agriculture and food with higer added value; ICT sector; Sustainable materials and smart buildings; Electro Mechanical Industry – Industry 4.0; Energy for the future; Tourism |  |  |  | RELATIONSHIP WITH THE NATIONAL DEVELOPMENT STRATEGY 2024-2044: 5.1. STRATEGIC AREA: Sustainable, innovative and competitive economy Objective: Economy based on knowledge, innovation and digitalization |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Goal 5(Overall Goal 5): DIGITAL TRANSFORMATION OF BUSINESSES |  |  |  |  | Impact indicator: Name of indicator related to the general objective Increased digital maturity and adoption of ICT solutions in S3 companies Measured by: % of companies in S3 domains that use digital solutions to improve business processes, productivity or services |  |  |  |  |
| Specific objective 5.1: Supporting the digitalization of companies through ICT tools and practices |  |  |  |  | Outcome indicator: Name of the indicator related to the specific objective Increased adoption of digital tools in S3 companies Improved access to digital services and support for dual transition |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M19. Digital transformation of companies by improving relevant infrastructure and types of services | A28 Co-financing of grants for customized/adapted digital solutions for companies operating in priority sectors S3 (except IT sector) by stimulating the use of established support infrastructure | Lead institution INOVA Вклучени институции MDT, EDIH | Q2 2026 |  |  | Q3 2027 | 31.000.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Number of companies receiving co-financing for digital transformation of their operations (50) |
|  | A29 Co-financing the creation of digital innovation centers that support companies and the public sector in the dual transition and improve the service they offer | Lead institution МDТ Institutions involved INOVA, EDIH | Q3 2026 |  |  | Q3 2027 | 31.000.000 MKD | State Budget of the Republic of North Macedonia/ international organizations/donor support | Number of established digital innovation hubs (1) Number of companies and public sector entities served by these hubs (50) Number of digital support services and solutions developed/offered (3) |
| # PRIORITY AREAS : Smart agriculture and food with higer added value; ICT sector; Sustainable materials and smart buildings; Electro Mechanical Industry – Industry 4.0; Energy for the future; Tourism |  |  |  | LINKAGE WITH THE NATIONAL DEVELOPMENT STRATEGY 2024–2044 5.1 Strategic Area: Sustainable, Innovative and Competitive Economy Objective: A knowledge-based, innovation-driven and digitalised economy. |  |  |  |  |  |
| Strategic Objective 6 (Overall Objective 6): (CROSS-CUTTING OBJECTIVE) ENSURING CONTINUOUS DIALOGUE ON S3 AND GOOD GOVERNANCE |  |  |  |  | Impact Indicators (linked to the Overall Objective): Effective and transparent governance of Smart Specialisation (S3), enabling coordinated implementation, stakeholder engagement and evidence-based decision-making. Measured by: Regular monitoring reports on the implementation of Smart Specialisation (S3) and policy adjustments informed by S3 monitoring and the Entrepreneurial Discovery Process (EDP).. |  |  |  |  |
| Specific Objective 6.1: Establishing the Smart Specialisation (S3) governance structure. |  |  |  |  | Outcome Indicators (linked to the Specific Objective): -Strengthened stakeholder engagement and continuous dialogue within the Entrepreneurial Discovery Process (EDP). -Improved coordination among institutions involved in the implementation of Smart Specialisation (S3). -Centralised coordination of the implementation of the Smart Specialisation Strategy. -Availability of reliable data for monitoring the implementation and results of Smart Specialisation (S3). -Improved institutional capacity for evidence-based policy-making. |  |  |  |  |
| Measure | Activity | Lead institution Other institutions | Activity start date (quarter) |  |  | Planned date of implementation (quarter) | Estimated financial resources required | Funding source | Result indicator (related to the measure/ activity) |
| M20. Establishing a governance structure to support the implementation of and dialogue on Smart Specialisation (S3) in North Macedonia | A30. Establishing a formal governance structure comprising all directly and indirectly involved stakeholders to oversee the implementation and monitoring of the Smart Specialisation (S3) Strategy and Action Plan. | Lead institution OPGRNM Institutions involved МЕL, МES, HEI, chambers of commerce, Innovation support institutions | Q1 2026 |  |  | Q4 2027 | There are no financial implications |  | Operational Working Group established. Council for Innovation, Scientific and Technological Development and Entrepreneurship established (Yes). Number of S3 coordination and dialogue meetings held annually (3). |
|  | A31. Establishing an S3 Unit within the Ministry of Education and Science (MES). | Lead institution MES Institutions involved | Q3 2026 |  |  | Q4 2026 | There are no financial implications |  | National Smart Specialisation (S3) Office established (Yes). |
| M21. Establishing a Monitoring and Evaluation System | A32. Developing a Monitoring and Evaluation System | Lead institution OPGRNM Institutions involved MES | Q3 2026 |  |  | Q4 2027 | 3.100.000 MKD | International organizations/donor support / IPA | Monitoring and Evaluation Framework for Smart Specialisation (S3) developed and adopted (Yes). Expanded coverage of indicators defined and integrated into the Smart Specialisation (S3) monitoring and evaluation system. |
|  | A33. Building capacity for monitoring and evaluation | Lead institution MES Institutions involved | Q3 2026 |  |  | Q4 2027 | 620.000 MKD | International organizations/donor support / IPA | Number of training sessions delivered (5). Expanded coverage of staff trained in data collection, reporting and analysis. |

Vouchers for business consulting services for:

Green transition /For example: zero waste in production processes, measuring and reducing greenhouse gas emissions, implementing circular economy concepts and/or reporting services according to ESG practices. Digital transition / Vouchers for business consulting services and digital maturity assessment / Certification according to international standards / Implementation of new business models /For example: implementation of the 5P principles (People, Planet, Profit, Purpose, Partnership). Lean Six Sigma (process improvement methodology)