DRAFT - ACTION PLAN

FOR IMPLEMENTATION OF THE

PFM REFORM PROGRAMME FOR 2026

2026

| PILLAR: I - Economic Analysis, Macroeconomic and Fiscal Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Tax revenue forecasting and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  | Target FY 2026 |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| i) There is a narrower discrepancy between planned and realized amounts in total and individual tax revenues, suggesting improved forecasting | Deviation in total revenues and revenue composition between planned and actual amounts, as used in PEFA PI3* as part of SIGMA*. Grades based on the Program: A, B, C, D (highest grade is A and lowest is D) *https://www.pefa.org/resources/calculation-sheet-revenue-composition-outturn-pi-32-november-2018 *https://www.sigmaweb.org/ |  |  |  | Score B |  | Score B |  |  |  | Score A |  |  |
| ii) Enhanced public awareness of tax expenditures and other tax indicators | Reports on tax expenditures are prepared and submitted as part of the Final Account of the Budget of the Republic of North Macedonia and a report on other tax indicators is prepared |  |  |  | Annual report on tax expenditures prepared and submitted as part of the Final Account of the Budget of the Republic of North Macedonia; Completed training for the preparation of a tax indicatos report on: -VAT– GAP; -C-efficiency; |  | Annual report on tax expenditures prepared and submitted as part of the Final Account of the Budget of the Republic of North Macedonia; Prepared tax indicators report on: - VAT – GAP; - C-efficiency; Completed training for the preparation of a tax indicators report on: - Tax buoyancy and tax elasticity ratio - Effective marginal tax rates (EMTR), and - Effective Average Tax Rates (EATRs) |  |  |  | Annual report on tax expenditures prepared and submitted as part of the Final Account of the Budget of the Republic of North Macedonia; Prepared tax indicators report on: - VAT – GAP; - C-efficiency; -Tax buoyancy and tax elasticity ratio - Effective marginal tax rates (EMTR) and - Effective average tax rates (EATRs) |  |  |
| iii) Increased capabilities for MoF employees for application of tax models, forecasting, and revenue monitoring | Employees is fully trained for application of revenue forecasting tax models, monitoring tax revenue, revenue monitoring and estimating tax expenditures |  |  |  | Regular annual employee training on the application of tax models |  | Regular annual employee training on the application of tax models |  |  |  | Regular annual employee training on the application of tax models |  |  |
| MEASURE 1: Improvig reporting on tax expenditures and other tax indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |
| Preparation of reports | Number of submitted reports and conducted trainings for preparation of the reports |  |  | 1 Annual tax expenditures report prepared and submitted as part of the Final Account of the Budget of the Republic of Notrth Macedonia Conducted 2 trainings for preparation of report for tax indicators (VAT-GAP and C-Efficiency) |  |  |  | 1 Annual tax expenditures report prepared and submitted as part of the Final Account of the Budget of the Republic of Notrth Macedonia; Prepared 1 report on tax indicators (VAT – GAP; C-Efficiency;) Conducted 4 trainings for preparation of report for tax indicators (Coefficients for tax buoyancy and tax elasticity estimated еffective marginal tax rates (EMTRs) and effective average tax rates (EATRs)) |  |  |  | 1 Annual tax expenditures report prepared and submitted as part of the Final Account of the Budget of the Republic of Notrth Macedonia; Prepared 1 report on tax indicators (VAT – GAP; C-Efficiency; Coefficients for tax buoyancy and tax elasticity estimated еffective marginal tax rates (EMTRs) and effective average tax rates (EATRs);) |  |
| Deliverables in 2026: | - Training of employees in the Department of Public Revenue and Tax and Customs Policy at the Ministry of Finance - Prepared Annual Tax Expenditures and signed protocols for data sharing with the PRO and CA |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1. Implementation of training on preparation of annual tax expenditures and preparation of protocols for data sharing with the PRO and CA Office |  | Q1/26 | Q4/26 | MoF |  | PRO and CA |  |  |  |  |  |  | IMF |
| 2. Preparation of VAT gap Report - employee training - application guide |  | Q3/26 | Q4/26 | MoF |  | PRO and CA |  |  | EUR 40,000 for 2026 (budgeted ammount for activity 1,2 &3) |  |  |  | WB |
| 3.Preparation of C-Efficiency Report - employee training - application guide |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEASURE 2: Enhancing the capacity for application on tax models |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |
| Enhancing capacity of employees in the Public Revenue and Tax and Customs Policy Department in the Ministry of Finance for the application of tax models | Number of conducted tailor-made training of employees |  |  | Implemented 3 trainings of the employees for the application of tax models (CIT, PIT and VAT), with extensions with a module for tax expenditures; Implemented 2 trainings for Power BI |  |  |  | Implemented 4 training trainings of the employees for the application of tax models (CIT, PIT, VAT and Excise) implemented, with extensions with a module for tax expenditures; Conntinious training for Power BI |  |  |  | Implemented regular annual employees training in tax modeling with extensions with a module for tax expenditures, and using the Power BI tool Tax models fully implemented, with extensions with a module for tax expenditures, and using the Power BI tool |  |
|  | Number of tax models fully operational; new modules for tax expenditures developed and Power BI tool installed |  |  | 3 Tax models (CIT, PIT, VAT) implemented, with extensions with a module for tax expenditures Power BI tool installed |  |  |  | 4 Tax models implemented (CIT, PIT, VAT and Excise), with extensions with a module for tax expenditures |  |  |  | Tax models fully implemented, with extensions with a module for tax expenditures, and using the Power BI tool |  |
| Deliverables in 2026: | - Training of employees of the Public Revenue and Tax and Customs Policy Department in the Ministry of Finance on the application of tax models and prepared manualsfor the application of the appropriate models for PIT, CIT and VAT |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1.Tax model for PIT updating and supplementing with extensions with a tax expenditure module - Training of employees |  | Q1/26 | Q4/26 | MoF |  | PRO and CA |  |  | EUR 90,000 for 2026 (budgeted ammount for activity 1,2,3 & 4) |  |  |  | WB |
| 2.Tax model for CIT updating and supplementing with extensions with a tax expenditure module - Training of employees - application guide for tax model |  | Q1/26 | Q4/26 |  |  |  |  |  |  |  |  |  |  |
| 3.Tax model for VAT updating and supplementing with extensions with a tax expenditure module - Training of employees |  | Q1/26 | Q4/26 |  |  |  |  |  |  |  |  |  |  |
| 4. Power BI training conducted: - Training of employees - application guide |  | Q1/26 | Q4/26 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 130.000 |

| PILLAR I: Economic Analysis, Macroeconomic and Fiscal Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Economic analysis and Macroeconomic forecasting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| Impact assessment of certain economic policies, reforms or measures and carrying out of additional economic analyses | •Deviation between realised and forecasted GDP •Deviation between actual and budgeted expenditures for specified risk-prone expenditures |  |  |  |  |  |  | Number of conducted trainings and workshops on the assessment of the impact of structural policies using existing and new tools |  |  |  |  |  |  |  |  |  |  |  | Number of preparered economic analyses and impact assessments on labour market developments, informal economy, economy's productivity and competitiveness, etc |  |  |  | / |  |  |
| Improved quality and coverage of projections for macroeconomic indicators |  |  |  |  |  |  |  | Development of new tools for macroeconomic planning and forecasting as well as policy analyses: - Developed macro-fiscal structural model - Developed module for climate impact assessment within the macro-fiscal structural model |  |  |  |  |  |  |  |  |  |  |  | Developed action plan for development of a CGE model |  |  |  | Carrying out initial activities included in the action plan for development of a CGE model |  |  |
| Increased scope of fiscal risks assessment and analyses |  |  |  |  |  |  |  | - Revised Plan of Activities to Strengthen Capacity for Assessment and Fiscal Risks Analyses - Institutional framework for fiscal risks improved |  |  |  |  |  |  |  |  |  |  |  | Realized plan of activities to strengthen capacity for assessment and analysis of fiscal risks |  |  |  | / |  |  |
| MEASURE 1: Capacity building for economic analyses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| To strengthen the capacities of the beneficiaries for economic analyses in order to provide policy makers information on the expected results of the proposed economic measures, including through introduction of additional macro fiscal toolkits | Assessment of the impact of certain economic policies, reforms or measures and implementation of additional economic analyses |  |  |  |  |  |  | Number of conducted trainings and workshops on the assessment of the impact of structural policies using existing and new tools |  |  |  |  |  |  |  |  |  |  |  | Number of preparered economic analyses and impact assessments on labour market developments, informal economy, economy's productivity and competitiveness, etc. |  |  |  | / |  |  |
| Deliverables in 2026: | - Trainings of employees in the Ministry of Finance for the analysis of macroeconomic data - Developing a tool model for assessing the impact of economic policies and reforms with a financial programming model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |
|  |  |  |  | START qq/yy |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |
| 1. Increasing the scope of economic analyses. Continuation of the development of a new tool to improve analyses of the economic trends including: labor market developments, the informal economy, the assessment of the productivity and the competitiveness of the economy, etc. |  |  |  | Q1/25 |  | Q4/26 |  |  |  |  | MоF (MPD, DT, DBF, DPD) |  |  | / |  |  |  |  | EUR 70.000 for 2026 |  |  |  |  |  |  | External financing Swiss State Secretariat for Economic Affairs (SECO) |
| 2. Economic policy impact assessment. Continuation of the development of a new tool to improve assessment of the impact from certain economic policies, reforms or measures. |  |  |  | Q1/25 |  | Q4/26 |  |  |  |  | MоF MPD, DT, DBF, DPD) |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |
| MEASURE 2: Developing new macroeconomic models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| Strengthening the capacity of the Ministry of Finance for macroeconomic forecasting and analyses, including by development of new econometric models. | New macroeconomic models in the preparation of budget documents and the Program for Economic Reforms |  |  |  |  |  |  | New tools (short-term and macro-fiscal structural models) for forecasting and analysis: - Developed macro-fiscal structural model and conducted trainings and workshops - Conducted activities for the development of a module for the impact of climate change within the macrostructural model and conducted training and workshops. |  |  |  |  |  |  |  |  |  |  |  | Developed action plan for development of a CGE model |  |  |  | Carrying out initial activities included in the action plan for development of a CGE model |  |  |
| Deliverables in 2026: | - New macroeconomic models in the preparation of budget documents and the Program for Economic Reforms - Developing a macro-fiscal structural model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |
|  |  |  |  | START qq/yy |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |
| 1.Developing macroeconomic forecasting tools: - Macro –fiscal structural model to be developed |  |  |  | Q1/25 |  | Q4/26 |  |  |  |  | MоF (MPD, DT, DBF, DPD) |  |  | Parliament-BO &PI); Fiscal Councl |  |  |  |  | EUR 70.000 for 2026 |  |  |  |  |  |  | Eur 7.100.000 m.e. for World Bank project ‘Strengthening fiscal governance in the Western Balkans 2023-26’ (World Bank) under the EU TF on strengthening the fiscal governance in the Western Balkans. |
| MEASURE 3: Fiscal Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| To strengthen the institutional architecture of beneficiaries for fiscal risks assessment in order to provide timely information on potential threats to the country's fiscal position and an integrated approach to managing these risks | Comprehensive reporting (Fiscal Risks chapter in the Fiscal Strategy) on: liabilities of central and local governments; PPP associated risks; summary of risks identified by the biggest SoEs; comparison of macro-fiscal forecast scenarios; and risks related legal cases |  |  |  |  |  |  | - Revised Plan of Activities to Strengthen Capacity for Assessment and Fiscal Risks Analyses - Institutional framework for fiscal risks improved |  |  |  |  |  |  |  |  |  |  |  | Realized plan of activities to strengthen capacity for assessment and analysis of fiscal risks |  |  |  |  |  |  |
| Deliverables in 2026: | - Trainings of employees in the Ministry of Finance for fiscal risks analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |
|  |  |  |  | START qq/yy |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |
| 1. Implementation of a plan with activities to strengthen the capacities for fiscal risks analyses in line with FAD/IMF recommendations |  |  |  | Q1/25 |  | Q3/27 |  |  |  |  | MoF (MPD, DBF, DT, DPD, LD) |  |  | / |  |  |  |  | EUR 70.000 for 2026 |  |  |  |  |  |  | IMF missions on Fiscal Risks/EU |
| 2. Development of a Fiscal Risk Registry and promotion of Institutional Framework according to the best regional and EU practices |  |  |  | Q1/25 |  | Q4/27 |  |  |  |  | MoF (MPD, DBF, DT, DPD, LD) |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | 210,000 |
| PILLAR 1: Economic Analysis, Macroeconomic and Fiscal Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 3: Strengthening Debt management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  | Target FY 2028 |  |  |  |
| Strengthened public debt management in the medium and long term | Increased grade for the indicator 6.4.1 – Quality of public debt management in the SIGMA report |  |  |  |  |  |  | / |  |  |  |  |  |  |  | / |  |  |  |  |  |  | Improvement of the sub indicator in the SIGMA report for government debt risk mitigation |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  |  |  | Target FY 2028 |
| More efficient public debt management by optimizing risks which public debt portfolio is susceptible to. | Number of external debt orders paid electronically |  |  |  |  |  |  | 100% of external debt orders to be realized electronically |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  | / |
|  | Increased number of employees responsible for public debt management |  |  |  |  |  |  | 13 employees for public debt management |  |  |  |  |  |  |  |  | 15 employees for public debt management |  |  |  |  |  |  |  |  | 17 employees for public debt management |
|  | Procedure for Quarterly debt reconciliation with foreign creditors |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  | / |
| Deliverables in 2026: | - 100% of external debt orders to be realized electronically - 2 new employments in PDMD - Adopted procedure for Quarterly debt reconciliation with foreign creditors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |
|  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |
| 1. Introducing e-banking with NBRNM for external debt repayment |  |  |  | 2025 |  |  | 2026 |  |  | Ministry of Finance |  |  | NBRNM |  |  |  |  |  | / |  |  |  |  |  |  | / |
| 2. Strengthening public debt management capacities |  |  |  | 2025 |  |  | 2028 |  |  | Ministry of Finance |  |  | Agency for administration |  |  |  |  |  | EUR 14,200 |  |  |  |  |  |  | National Budget |
| 3. Reconciling the debt stock with the creditors |  |  |  | 2024 |  |  | 2026 |  |  | Ministry of Finance |  |  | Multilateral, bilateral and private creditors |  |  |  |  |  | / |  |  |  |  |  |  | / |
| MEASURE 2: Increasing public debt transparency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  |  |  | Target FY 2028 |
| Transparent presentation of public debt in line with international methodologies and standards | Publication of general government debt in accordance with the Maastricht criterion |  |  |  |  |  |  | The general government debt is harmonized with the Maastricht criterion |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  | / |
| Deliverables in 2026: | - Draft version of the Annual Borrowing Plan - Prepared draft amendments to the Law on Public Debt in order to harmonize the definition of general government debt with the Law on Budgets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |
|  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |
| 1. Amendments to the Law on Public Debt in order to align it with the definition of general government debt in accordance with the Organic Budget Law |  |  |  | 2025 |  |  | 2026 |  |  | MoF |  |  | EU, World bank |  |  |  |  |  | / |  |  |  |  |  |  | / |
| 2. Incorporating debt data in the Budget document |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  | / |  |  |  |  |  | / |  |  |  |  |  |  | / |
| 3. Publication of the Annual Borrowing Plan |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  | World Bank |  |  |  |  |  | EUR 10.000 |  |  |  |  |  |  | Missions implemented through the World bank - Government Debt and Risk Management Program (GDRM Program) – 3rd phase |
| 4. Improving Debt Reporting |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  | World bank |  |  |  |  |  | / |  |  |  |  |  |  | / |
| MEASURE 3: Introduction new debt instruments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  |  |  | Target FY 2028 |
| Expanding investors’ database | Diversification of debt instruments |  |  |  |  |  |  | Issuances of the Development Bond will be defined during the monitoring process |  |  |  |  |  |  |  |  | Issuances of the Development Bond will be defined during the monitoring process |  |  |  |  |  |  |  |  | Issuances of the Development Bond for citizens will be defined during the monitoring process |
| Deliverables in 2026: | - New issuances of Citizen bonds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |
|  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |
| 1. Issuing Development Bond for Citizens |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  | Citizens |  |  |  |  |  | / |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | EUR 24,200 |
| PILLAR: II: Revenue Mobilisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 1: Tax and Customs Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  | Target FY 2028 |  |  |  |  |  |
| Legislation in the area of taxation and customs harmonized with the Union acquis, standards and best practices and with the country tax policy strategic framework | Progress made toward fulfilment of the EU accession criteria (steady progress in the respective Chapters 16 and 29) |  |  |  |  |  |  | Ch.29: Good level of preparation Good progress Ch.16: Moderately prepared Some progress |  |  |  |  |  |  | Ch.29: Good level of preparation Very Good progress Ch.16: Good level of preparation Good progress |  |  |  |  |  | Ch.29: Good level of preparation Very Good progress Ch.16: Good level of preparation Good progress |  |  |  |  |  |
| MEASURE 1: Improved revenue legislation framework, harmonized with the EU acquis and best practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  | Target FY 2028 |  |  |  |  |
| Objective is to improve and harmonize legislation in line with the relevant EU acquis and the best practices in the area of tax and customs legislation | Number of legislative acts (regarding Ch.16 And Ch.29) |  |  |  |  |  |  | Not less than 1 legislative act |  |  |  |  |  |  | Not less than 2 legislative act |  |  |  |  |  |  | Not less than 3 legislative act |  |  |  |  |
| Deliverables in 2026: | - Prepared gap analyses and drafted new legal acts or amendments to the existing national tax and customs legislation (laws and by-laws) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |
|  |  |  | START qq/yy |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |  |
| 1. Gap analysis of the national tax legislation (laws and by-laws) compared to the EU legislation and best practices. |  |  | K1/26 |  | 2028 |  |  |  | MoF – Public Revenues and Tax and Customs Policy Department |  |  | PRO and CA |  |  |  |  |  | EUR 250,000 (budgeted amount for both activities 1 & 2) |  |  |  |  |  |  | Financial GAP |  |
| 2. New legal acts and/or amendments to the existing national tax legislation (laws and by-laws) drafted in line with the EU legislation and best practices |  |  | K1/26 |  | 2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Gap analysis of the national customs legislation (laws and by-laws) compared to the EU legislation and best practices. |  |  | K1/26 |  | 2028 |  |  |  |  |  |  | CA |  |  |  |  |  | EUR 250,000 (amount for both activities 3 & 4) |  |  |  |  |  |  | Financial GAP |  |
| 4. New legal acts and/or amendments to the existing national customs legislation (laws and by-laws) drafted in line with the EU legislation and best practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | EUR 500,000 |  |

| PILLAR II: Revenue Mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  | Target FY 2026 |  |  |  |  |  | Target FY 2027 |  | Target FY 2028 |  |
| Improved stability, efficiency and quality of the revenue collection system (IT system) | % percentage of digitized tax services |  |  | 92% |  |  |  |  |  | 95% |  | 100% |  |
| More effective and efficient management of the overdue tax debt | improved rate of tax payment on time (VAT) |  |  | Rate on number of timely payments – 70% Rate on amount of timely payments - - 80% |  |  |  |  |  | Rate on number of timely payments – 80% Rate on amount of timely payments - 85% |  | Rate on number of timely payments – 90% Rate on amount of timely payments - 90% |  |
|  | Improved age structure of the tax debt (VAT) - reduced share of the debt older than 12 months in the total tax debt |  |  | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 63% |  |  |  |  |  | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 56% |  | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 50% |  |
| Fully established systematic process for managing tax compliance risks | Increased number of taxpayers who voluntarily comply |  |  | Percentage of timely submitted returns and taxes payment compared to the previous year |  |  |  |  |  | Percentage of timely submitted returns and taxes payment compared to the previous year |  | Percentage of timely submitted returns and taxes payment compared to the previous year |  |
| MEASURE 1: Strengthen administrative capacity for better revenue collection and tax compliance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2026 |  | Target FY 2027 |  |  |  |  | Target FY 2028 |
| Improve tax revenue services, including tax collection and compliance, and overall establish a model for a professional service to taxpayers, recognizable for its best practices and quality standards | Increasing the amount of the established tax guarantee |  |  |  |  | Increase the amount of the established tax guarantee by 10% compared to 2025 |  | Increase the amount of the established tax guarantee by 5% compared to 2026 |  |  |  |  | Increase the amount of the established tax guarantee by 5% compared to 2027 |
|  | Increasing the collection of tax debt based on an established tax guarantee |  |  |  |  | Increase in the amount of debt collected based on the established tax guarantee by 10% compared to 2025 |  | Increase in the amount of debt collected based on the established tax guarantee by 10% compared to 2026 |  |  |  |  | Increase in the amount of debt collected based on the established tax guarantee by 5% compared to 2027 |
|  | Value of collectible core tax arrears in FY end in percent of total core tax revenue collection for FY |  |  |  |  | VAT debt / VAT income ratio 14% |  | VAT debt / VAT income ratio 12% |  |  |  |  | VAT debt / VAT income ratio 10% |
|  | Increase in the amount of additionally determined tax with audit compared to the previous year |  |  |  |  | Additional tax assessed per audit program increased per 5% compared to the results from the previous year |  | Additional tax assessed per audit program increased per 5% compared to the results from the previous year |  |  |  |  | Additional tax assessed per audit program increased per 5% compared to the results from the previous year |
| Deliverables in 2026: | - Implemented measures and activities to strengthen "social" awareness of the tax responsibility of the founders and managers of companies and inter-institutional compliance in practicing the mechanisms for this responsibility - Proposal for changes and additions to the Law on Tax Procedure (which are not related to the redesign of business processes) harmonized with the Ministry of Finance and launched in the adoption procedure - Established and functional Tax Enforcement Center. - Successful implementation of procured hardware, software, and other equipment for the modernization and security enhancement of the PRO’s IT infrastructure, including the equipping of a secondary location to ensure the continuity of IT systems and electronic services for taxpayers and third parties. - Compliance Improvement Plan – Informal Economy. - Compliance Improvement Plan for specific taxpayer segments. - Risk Mitigation Plan for risks identified in the Risk Register. |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1.More effective and efficient management of overdue tax debt |  | 2025 | 2028 |  | PRO |  | / |  | 73,500 |  |  |  | National Budget |
| 2.Improving the Compliance risk management |  |  |  |  |  |  |  |  | / |  |  |  | / |
| MEASURE 2: Digital transformation of the PRO with the establishment of an Tax Information System (TIS) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2026 |  | Target FY 2027 |  |  |  |  | Target FY 2028 |
| The purpose of the measure is to build the capacity of the tax administration to administer tax revenues and contributions by strengthening administrative resources, more effective and efficient management of overdue tax debt and compliance risk management | Number of institutions with which the Tax Information System exchanges information |  |  |  |  | 27 |  | 28 |  |  | at least 30 |  |  |
| Deliverables in 2025: | - Functional e-Invoice system, launched in accordance with legal and regulatory frameworks. - Prerequisites secured for the commencement of implementation in 2026, following the completion of public procurement and the selection of an appropriate contractor |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1.Completion of the remaining modules of the Tax Information System |  | 2025 | 2028 |  | PRO |  |  |  | 4,983,740 |  |  |  | National Budget |
| 2.Ensuring IS security (Information System) and smooth functioning of the integrated Tax Information System |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  | 5,057,240 EUR |

| PILLAR II: Revenue mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 3: Customs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  | Target FY 2026 |  | Target FY 2027 |  |  | Target FY 2028 |  |  |
| Availability of innovative equipment and training of staff for detection and control for the purpose of: control without disturbance, detection of hidden objects on persons, radiation detection, sampling and analysis of samples, manual search | Percentage of staff employed in the corresponding units for customs control are trained to use the new equipment |  |  |  |  | 40% of staff employed in the corresponding units for customs control are trained to use the new equipmentof |  | 70% of staff employed in the corresponding units for customs control are trained to use the new equipmentof |  |  | 70% of staff employed in the corresponding units for customs control are trained to use the new equipmentof |  |  |
| Introduction of a complete paperless environment in the customs procedure, through the implementation of electronic systems from the e-Customs program, i.e. the Multiannual Strategic Plan of the EU (MASP), compatible with the systems and procedures in the European Union; preparation for interconnection and interoperability with EU systems and implementation of systems compliant with EU systems (which may be established prior to EU accession) and staffing with appropriate hardware for those systems | Implemented at least two (2) new IT systems / modules from the EU Multiannual Strategic Plan (MASP) at national level on appropriate hardware |  |  |  |  | / |  | 2 |  |  | / |  |  |
| MEASURE 1: Strengthening joint control mechanisms and capacities in order to combat illegal trade and organized crime |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| The purpose of the measure is to suppress illegal trade and organized crime, protect the legal economy, ensure safety and security, protect the health and safety of citizens and protect the environment. | Percentage of staff employed in the corresponding units for customs control trained to use the new equipment |  |  | 30% (Upon delivery of equipment in 2026) |  |  |  |  | 70% |  |  | 70% |  |
| The purpose of the measure is to suppress illegal trade and organized crime, protect the legal economy, ensure safety and security, protect the health and safety of citizens and protect the environment. | Conducted appropriate professional trainings for the employees in the operational services for control and prosecution for fight against illicit trade and crime (number of events) |  |  | 2 (Upon delivery of equipment in 2026) |  |  |  |  | 5 |  |  | 5 |  |
| Deliverables in 2026: | - Signed contracts for the procurement of the equipment in 2025 (IPA 3) |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Equipping with modern and reliable control equipment and appropriate training for employees, in order to protect financial and economic interests, guarantee the safety and security of citizens, environmental protection and protection from unfair and illicit trade |  | 2024 | 2028 |  | Customs Administration |  | EU - and its institutions, UN, Bilateral Cooperation, relevant domestic institutions |  |  | 2,000,000 |  |  | IPA3 |
| MEASURE 2: Modernization of customs services and their digitalization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| By achieving this goal through modernization and continuation of the digitalization process, and at the same time by following the recommendations for harmonization and association with the EU, the system of public finances, fiscal discipline and efficiency in the management and use of public resources will be strengthened, transparency will be promoted and efficient services and economic development will be provided | Average yearly technical availability of the new customs IT systems for interconnectivity with the EU systems |  |  | 95% |  |  |  |  | 95% |  |  | 95% |  |
|  | Conducted appropriate professional trainings for the employees of the Customs Administration and the economic operators for implementation of systems (number of events) |  |  | 15 |  |  |  |  | 15 |  |  | 20 |  |
| Deliverables in 2026: | - Contracts signed for two EU related IT systems (IPA3) - Contract signed for procurement of Hardware (IPA 3) - Project “The Establishment of Risk Management and Customs Data Warehouse System” completed - Project of implementation of NCTS 5 completed (national budget) - Tender for the NCTS 6 (upgarade of NCTS 6) published (national budget – Reform Agenda) |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Implementation of modern systems in order to comply with the Multiannual Strategic Plan of the EU (MASP), integration with European systems and procurement of appropriate hardware |  | 2024 | 2028 |  | Customs Administration |  | EU |  |  | EUR 1.000.000 (National Budget) +4.000.000 (Korea) + 1.000.000 IPA 3 |  |  | IPA 3 and Government of, Reform Agenda |
| MEASURE 3: Adequate monitoring of excise good sand collection of excise duties |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| The goal of this measure is through introduction of procedures and instruments for appropriate monitoring of excise goods, to combat against illicit trade in tobacco products and to increase collection of excise duties. Adequate monitoring of excise goods is important due to the increased volume of trade in such goods, the harm to health (especially found in tobacco products), registered tax evasion, illicit trade in excise goods as a source of financing for organized crime. | Preparation of a legal framework for implementing the TRACK&TRACE system |  |  | / |  |  |  |  | / |  |  | High preparation for implementing the TRACK&TRACE system |  |
| Deliverables in 2026: | - Preparing necessary Protocols between concerned institutions |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1 Establishing a system for marking and tracking tobacco products (cigarettes) through the TRACK&TRACE system |  | 2024 | 2028 |  | Customs Administration |  | / |  |  | / |  |  | / |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 8,000,000 |

| PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Budget Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes |  |  |  | Priority indicators |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  | Target FY 2028 |  |  |
| Adopted Fiscal Strategy |  |  |  | Reduction in the budget deficit as a % compared to the previous year |  |  | -3.5% of GDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -3% of GDP |  |  |  |  |  | -3% of GDP |  |  |
| MEASURE 1: Improving medium-term planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  |  | Measure indicator: |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  | Target FY 20267 |  |  |  |  |  |  | Target FY 2028 |  |  |
| Improving medium-term planning |  |  |  | Share of total expenditure in GDP |  |  |  |  |  |  |  |  | 39.0% of GDP |  |  |  |  |  |  |  |  |  |  | 38.5% of GDP |  |  |  |  |  |  | 38.7% of GDP |  |  |
| ACTIVITY |  |  |  |  |  |  |  |  | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |  |  |
| 1. Medium-Term Fiscal Strategy based on a sectoral approach and with established medium-term expenditure limits |  |  |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  |  | Ministry of Finance/Budget Department |  |  |  |  |  | Budget users |  | / |  |  |  |  |  |  | / |  |  |
| Deliverables in 2026: |  |  |  |  | - Improved Fiscal Strategy through appropriate design of performance indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEASURE 2: Improving sectoral approach of budget planning and development and implementation of bylaws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  |  | Measure indicator: |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  | Target FY 2028 |  |  |
| Improving sectoral approach of budget planning and development and implementation of bylaws |  |  |  | Number of First level of budget users and main budget users |  |  |  |  |  |  |  |  | Around 50 |  |  |  |  |  |  |  |  |  |  | Less than 50 |  |  |  |  |  |  | Less than 50 |  |  |
| Deliverables in 2026: |  |  |  | - Analysis and activities for preparing a new Budget format with the application of new classifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  |  |  |  |  | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |  |  |
| 1. Preparing and implementing OBL bylaws |  |  |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  |  | Ministry of Finance |  |  |  |  |  | Budget users |  | EUR 200,000 |  |  |  |  |  |  | US Treasury |  |  |
| 2. Preparing and implementing several types of classifications - administrative/organizational, economic, program, functional classifications, as well as classification of sources of financing |  |  |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  |  | Ministry of Finance/Budget Department |  |  |  |  |  | Budget users |  | EUR 150,000 |  |  |  |  |  |  | US Treasury |  |  |
| 3. Strengthening of capacities, training of employees of the MoF and budget beneficiaries |  |  |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  |  | Ministry of Finance/Budget Department |  |  |  |  |  | Budget users |  | EUR 225,000 |  |  |  |  |  |  | US Treasury |  |  |
| MEASURE 3: Introducing performance based budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  |  | Measure indicator: |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |  |  | Target FY 2028 |  |  |
| Developing of multi-year indicators |  |  |  | Share of capital in total expenditures |  |  |  |  |  |  |  |  | 12.5% |  |  |  |  |  |  |  |  |  |  | 12,6% |  |  |  |  |  |  | 13.2% |  |  |
| Deliverables in 2026: |  |  |  | - Budget according to the OBL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  |  |  |  |  | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |  |  |
| 1. Developing of multi-year indicators for measuring the success in the implementation of budget policies |  |  |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  |  | Ministry of Finance and Government |  |  |  |  |  | Budget users/PE/JSC/LSGu |  | EUR 25,000 |  |  |  |  |  |  | US Treasury |  |  |
| 2. Preparation of procedures for monitoring the impact of performance indicators on sectoral policies |  |  |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  |  | Ministry of Finance and Government |  |  |  |  |  | Budget users/PE/JSC/LSGu |  |  |  |  |  |  |  |  |  |  |  |
| MEASURE 4: Spending review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  | Measure indicator: |  |  |  |  |  |  |  |  | Target FY 2025 |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |  |  | Target FY 2028 |  |  |  |
| Fiscal consolidation |  | Share of current in total expenditures in GDP |  |  |  |  |  |  |  |  | 34.5% |  |  |  |  |  |  |  | 34.1% |  |  |  |  | 33.7% |  |  |  |  |  | 33.5% |  |  |  |
| Deliverables in 2026: |  | - Fiscal consolidation and reduction of the budget deficit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  |  | TIMEFRAME |  |  |  |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | START qq/yy |  |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  | SOURCE |  |  |  |
| 1. Build capacity at the MoF and line ministries for conducting Spending Reviews on a regular base |  |  |  |  |  | 2025 |  |  |  | 2028 |  |  |  |  | Ministry of Finance and Government |  |  |  |  |  | Budget users/PE/JSC/LSGu |  |  | EUR 20,000 |  |  |  |  |  | IMF and WB |  |  |  |
| 2. Prepare and adopt methodology with defining criteria and procedures for conducting Spending review. |  |  |  |  |  | 2025 |  |  |  | 2028 |  |  |  |  | Ministry of Finance and Government |  |  |  |  |  | Budget users/PE/JSC/LSGu |  |  | EUR 20,000 |  |  |  |  |  |  |  |  |  |
| 3. Spending review as a basis for appropriate budgeting for the next mid-term period |  |  |  |  |  | 2025 |  |  |  | 2028 |  |  |  |  | Ministry of Finance and Government |  |  |  |  |  | Budget users/PE/JSC/LSGu |  |  | EUR 20,000 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | EUR 660,000 |
| PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 2: Strengthened Public Investment Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes |  | Priority indicators |  |  |  |  |  |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  |  | Target FY 2027 |  |  |  |  | Target FY 2028 |  |  |  |  |
| Efficient and effective planning, selection, budgeting and implementation of major public investment projects |  | PEFA score for indicator PI - 11.Public Investment Management 11.1. Economic analysis of investment projects 11.2. Investment project selection 11.3. Investment project costing 11.4. Investment project monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  | / |  |  |  |  | PEFA Score PI-11: >C 11.1) >C 11.2) >C 11.3) >C 11.4) >C |  |  |  |  |
| MEASURE 1: Efficient coordination and development of public investment management processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  | Measure indicator: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |  | Target FY 2028 |  |  |  |  |
| Established structured and comprehensive approach to decision making for public investment projects |  | 1) Staff capacity of the PIM Department in the MoF 2) Supporting legal framework for PIM adopted |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1) 80% of planned staff engaged 2) Number of new acts adopted/amended |  |  |  |  | 1) 90% of planned staff engaged 2) Number of new acts adopted/amended |  |  |  |  | 1) 100% of planned staff engaged 2) Number of new acts adopted/amended |  |  |  |  |
| Deliverables in 2026: |  | - Manual for PIM processes - Staffing of PIM department (11 employees) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |
|  |  |  |  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  | SOURCE |  |  |  |
| 1.Strengthen the supporting legal framework for PIM |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  | MoF Government |  |  |  |  |  | External expertise (WB/IMF/EU) |  |  |  |  |  |  | 5,000 |  | External funding |  |  |  |
| 2.Strengthen the institutional capacity of the MoF in the PIM system |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  |  |  |  | External expertise (WB/IMF/EU) |  |  |  |  |  |  | 30,000 10,000 |  | National Budget External funding |  |  |  |
| MEASURE 2: Established single pipeline of appraised capital public investment projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  | Measure indicator: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |  | Target FY 2028 |  |  |  |  |
| Capital spending is allocated to the most productive sectors and projects by a comprehensive, unified, and medium-term perspective to capital budgeting, as well as objective criteria and competitive procedures for selecting particular investment projects. |  | Single pipleline of appraised and prioritized public investment projects established |  |  |  |  |  |  |  |  |  |  |  |  |  |  | All budget users at central and local level prepare and submit to the Ministry of Finance project concept notes for new public investment projects in accordance with the PIM Decree Number of trainings for MoF and BU/SoE/LSGUs staff organised |  |  |  |  | Developed single pipeline of appraised and prioritized capital public investment projects Number of trainings for MoF and BU/SoE/LSGUs staff organised |  |  |  |  | Developed single pipeline of appraised and prioritized capital public investment projects Number of trainings for MoF and BU/SoE/LSGUs staff organised |  |  |  |  |
| Deliverables in 2026: |  | - Guidelines (methodology) for feasibility study - Standard criteria for project selection/ prioritization - Trainings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |
|  |  |  |  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  | SOURCE |  |  |  |
| 1. Establish standard criteria for project selection/ prioritization |  |  |  |  |  |  | 2025 |  |  | 2026 |  |  | MoF, Government |  |  |  |  |  | External expertise (WB/EU)) |  |  |  |  |  |  | 5,000 |  | External funding |  |  |  |
| 2. Provide training to MoF professionals on project appraisal and review of preinvestment studies |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  |  |  |  | External expertise (WB/IMF/EU) |  |  |  |  |  |  | 20,000 |  | External funding |  |  |  |
| 3. Provide training for employees of budget users PE, JSC/ LSGUs, for the preparation, assessment and selection of projects |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  |  |  |  | BU/SoEs/ LSGUs External expertise (WB/EU) |  |  |  |  |  |  | 15,000 |  | External funding |  |  |  |
| MEASURE 3: Efficient and effective monitoring of capital investments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  | Measure indicator: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |  | Target FY 2028 |  |  |  |  |
| Improved project monitoring and reporting arrangements for major public investment projects thus ensuring value for money. |  | - Created database of public investment projects from which to select budget candidates and monitor financial implementation of projects 2) Number of monitoring reports for the public investment portfolio prepared |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1) / 2) 2 |  |  |  |  | 1) / 2) 2 |  |  |  |  | 1) / 2) 2 |  |  |  |  |
| Deliverables in 2026: |  | - Verified project monitoring reports from public entities - Reports on monitoring the national investment portfolio at the central level; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  |  |  | TIMEFRAME |  |  |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |
|  |  |  |  |  |  |  | START qq/yy |  |  | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  | SOURCE |  |  |  |
| 1. Introduce procedures for risk-based centralized monitoring |  |  |  |  |  |  | 2025 |  |  | 2028 |  |  | MoF |  |  |  |  |  | External expertise (WB/ IMF/EU) BU/SoE/LSGUs |  |  |  |  |  |  | 15,000 |  | External funding |  |  |  |
| 2. Introducing a formal requirement for ex-post review of completed projects |  |  |  |  |  |  | 2026 |  |  | 2028 |  |  | MoF |  |  |  |  |  | External expertise (WB/ IMF/EU) BU/SoE/LSGUs |  |  |  |  |  |  | 20.000 |  | External funding |  |  |  |
| 3. Develop a web based IT systemfor PIM |  |  |  |  |  |  | 2025 |  |  | 2025 |  |  | MoF |  |  |  |  |  | External expertise (IMF) |  |  |  |  |  |  | 150,000 |  | External funding |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  | EUR 270,000 |  |  |  |

| PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 3: Strengthen the accounting of budgets and budget users |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  |  |  | Target FY 2026 |  |  | Target FY 2027 | Target FY 2028 |
| Harmonized legal framework of accounting of budgets and budget users with the new Budgets Law | Аdoptig new law and by-laws for accounting of budgets and budget users |  |  |  |  |  |  | Analysis of the existing legal framework for accounting of budgets and budget users for compliance with the new Budgets Law |  |  | Analysis of the existing legal framework for accounting of budgets and budget users for compliance with the new Budgets Law | Аdopted new law and by-laws for accounting of budgets and budget users |
| MEASURE 1: Harmonization of the legal framework for accounting of budgets and budget users with the new Budgets Law |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  | Target FY 2027 |  | Target FY 2028 |
| Improving the financial reporting of budgets and budget users through implementation of the regulatory framework for ​​ accounting of budgets and budget users | Harmonized legal framework of accounting of budgets and budget users with the new Budgets Law |  |  |  |  |  |  | Analysis of the existing legal framework for accounting of budgets and budget users for compliance with the new Budgets Law |  | Analysis of the existing legal framework for accounting of budgets and budget users for compliance with the new Budgets Law |  | Аdopted new law and by-laws for accounting of budgets and budget users |
| Deliverables in 2026: | - Detecting the need for adopting a new regulatory framework for budget accounting and budget users |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |
|  |  |  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  | SOURCE |
| 1. Revision of the existing legal framework and detecting the need for the adoption of a new regulation for accounting of budgets and budget users |  |  |  | January 2026 | December 2027 |  | MoF |  | / | / |  | / |
| 2. Revision of the existing by laws and detecting the need for the adoption of a new bylaws for accounting of budgets and budget users |  |  |  | January 2026 | December 2027 |  | MoF |  | / | / |  | / |
| MEASURE 2: Strengthening the accounting system of budgets and budget users by building of capacities of accountants employed in the public sector |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  |  |  | Target FY 2026 |  | Target FY 2027 |  | Target FY 2028 |
| Improved financial reporting of budgets and budget users through training of accountants employed in the public sector for legal framework of ​​accounting of budgets and budget users | Percentage of accountants employed in the public sector who will attent appropriate training for legal framework of ​​accounting of budgets and budget users in order to ensure better financial reporting |  |  |  |  |  |  | 30% of accountants employed in the public sector who will attent appropriate training for legal framework of ​​accounting of budgets and budget users |  | 50% of accountants employed in the public sector who will attent appropriate training for legal framework of ​​accounting of budgets and budget users |  | 100 % of accountants employed in the public sector who will attent appropriate training for legal framework of ​​accounting of budgets and budget users |
| Deliverables in 2026: | - Implementation of the first training for accountants employed in the public sector |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |
|  |  |  | START qq/yy |  | END qq/yy |  |  |  |  | BUDGET |  | SOURCE |
| - Training for accountants employed in the public for to the legal framework for accounting of budgets and budget users |  |  | June 2025 |  | December 2028 | MoF |  |  | / | / |  | / |
| - Training for accountants employed in the public sector for to the bylaws for accounting of budgets and budget users |  |  | June 2025 |  | December 2028 | MoF |  |  | / | / |  | / |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  | EUR 0 |

| ## PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 4: PFM at Local Level |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Stable and responsible financial operations and strengthened financial discipline, better transparency and accountability at the local level | Percentage of increased municipal revenues |  |  |  |  | 92% |  |  | 93,5% |  |  | 95% |
|  | Percentage of municipalities that have published financial documents on their websites (annual, semi-annual and quarterly) |  |  |  |  | 85% |  |  | 87% |  |  | 90% |
| MEASURE 1: Improving fiscal capacity and increasing municipal revenues |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  | Target FY 2028 |
| Strengthening the capacities of municipalities through the adoption of a new LSGU financing law and its by-laws, better mid-term budget planning | New law on financing of local self-government units |  |  |  | / |  |  | New law on financing of local self-government units |  |  |  | / |
|  | By-laws of the new Law on financing of local self-government units |  |  |  | / |  |  | Adopted new by- laws |  |  |  | / |
|  | Medium-term budget planning |  |  |  | All municipalities have medium-term budget planning |  |  | All municipalities have medium-term budget planning |  |  |  | All municipalities have medium-term budget planning |
|  | Number of trained employees in municipalities |  |  |  | 81 |  |  | 81 |  |  |  | 81 |
| Deliverables in 2026: | - Municipality employees (number): 81 |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  |  | SOURCE |  |
| 4. Number of trained employees in municipalities |  | Q1/26 | Q4/28 | Ministry of Finance |  |  | Municipalities | 2.000 |  |  | National budget |  |
| MEASURE 2: Financial discipline, better transparency and accountability of local government |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  | Target FY 2028 |
| Rationalization of operations and reduction of unnecessary expenses, regular servicing of obligations, betтer financial discipline, transparency and accountability, preparation of procedures for declaring financial instability. | Adopted procedures for financial instability of municipalities |  |  |  | / |  |  | Established procedures for financial instability of municipalities |  | / |  |  |
|  | Number of municipalities out of the total number of municipalities (81) that have published financial documents (annual, semi-annual and quarterly reports) on their websites |  |  |  | 75 |  |  | 79 |  | 81 |  |  |
| Deliverables in 2026: | - 75 municipalities publish financial data |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  |  | SOURCE |  |
| 1. Preparation of a procedure for financial instability of municipalities |  | Q1/27 | Q4/27 | Ministry of Finance |  |  | Municipalities | / |  |  | / |  |
| 2. Monitoring the transparency of municipalities |  | Q1/25 | Q4/28 | Ministry of Finance |  |  | Municipalities | / |  |  | / |  |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  | EUR 2,000 |

| PILLAR: IV PUBLIC PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Public Procurement Policy |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  | Target FY 2028 |  |
| Improved public procurement processес | percentage of one bid tenders |  |  |  |  | ≤29% |  |  | ≤28% |  | ≤ 27% |  |
|  | percentage of cancelled procedures |  |  |  |  | ≤18,5% |  |  | ≤18% |  | ≤ 18 % |  |
| MEASURE 1: Improving the cooperation among the key institutions in the public procurement system |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  | Target FY 2028 |  |  |
| Timely identification of gaps and irregular implementation of PPL, aiming to prevent irregularities and support duly and uniform implementation of the law | Held working meetings |  |  |  | Held at least 2 meetings |  |  | Held at least 2 meetings |  | Held at least 2 meetings |  |  |
| Deliverables in 2026: | - 2 working meetings held |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1.Regular communication and coordination of Advisory group of the key institutions in the procurement system |  | Q1/2024 | Q4/2028 | PPB |  |  | SAC, SAO, CPC, SCPC, MEMMR | / |  |  |  | / |
| MEASURE 2: Improved implementation of the Law on Public Procurement |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  | Target FY 2028 |  |  |
| Utilization of the opportunities introduced by LPP aiming to secure efficiency, economy and competitiveness in public procurement. | Use of e-auctions in Tenders |  |  |  | Max. 40% |  |  | Max. 35% |  | Max. 30% |  |  |
|  | Use of E-market system |  |  |  | Min. 800 |  |  | Min. 900 |  | Min. 1000 |  |  |
|  | Use of MEAT in value |  |  |  | Min. 20% |  |  | Min. 25% |  | Min. 25% |  |  |
| Deliverables in 2026: | - Realization of the activities outlined in the Action plan for increase of use of E-Market in 2026 |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1.Development of guides and tools for support of contracting authorities in improved implementation of the Law on Public Procurement |  | Q4/2025 | Q4/2026 | PPB |  |  | GoRNM | / |  |  |  | / |
| MEASURE 3: Introducing new system for education within PPB |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  | Target FY 2028 |  |  |
| Improve the knowledge and skills of public procurement officers | Established new system for education within PPB |  |  |  | / |  |  | Established new system for education within PPB |  | 15 organized trainings according new established system for education within PPB |  |  |
| Deliverables in 2026: | - Analysis of electronic tools for education; Adopted Amendment to the Public Procurement Law related to education in public procurement |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1. Analysing the possibilities for introducing new e - tools for education |  | Q1/2026 | Q4/2026 | PPB |  |  | MF | / |  |  |  | / |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  | EUR 0 |

| PILLAR: IV Public Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Public Private Partnership and Concessions on goods of general interest |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  |  | Target FY 2026 |  | Target FY 2027 |  |  | Target FY 2028 |  |  |
| Unification and digitalization of the process of awarding contracts for establishing public-private partnership, increased transparency and efficiency in the implementation of the new Law on Public-Private Partnership and strengthening and developing the capacities of the Ministry of energy, mining and mineral resources for consistent realization of competencies according to law. | 1)Number of concluded agreements for establishing a public-private partnership 2) Effective and consistent implementation of the obligations of the contracting parties in accordance with the agreements for establishment of public-private partnership. |  |  |  |  | Adoption of the Law on Public Private Partnership by the Assembly of the Republic of Macedonia and commencement of its implementation through the establishment of the Single Electronic System for Public Private Partnership |  | 1) Potential increase in the number of concluded public-private partnership agreements by 20% compared to the number of concluded agreements in the year as a basis for monitoring. 2) Potential decrease by 85% in concluded public-private partnership agreements in which certain legal obstacles to implementation have arisen, compared to the percentage of concluded agreements in the year as a basis for monitoring. |  |  | 1) Potential increase in the number of concluded public-private partnership agreements by 60% compared to the previous year. 2) Potential decrease by 90% in concluded public-private partnership agreements in which certain legal obstacles to implementation arose, compared to the previous year. |  |  |
| MEASURE 1: Establishment of the Unique Electronic System Public Private Partnership System (UESPPP) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| Ensuring greater transparency in the awarding and implementation of public-private partnership agreements, ie unifying and sublimating the entire process for their awarding through the establishment of a Unified Electronic Public-Private Partnership system as the only digital database of public-private partnership agreements will generate the Register of awarded contracts for establishing a public-private partnership. | Ensuring greater transparency in the awarding and implementation of public-private partnership contracts, i.e. unifying and sublimating the entire process for their awarding through the establishment of a Single Electronic System for Public-Private Partnership as a single digital database for public-private partnership contracts, which will generate the Register of Awarded Contracts for the Establishment of Public-Private Partnership. |  |  | Establishment of the SESPPP and start of implementation of the software solution for establishing the SESPPP and the Register of awarded contracts for establishing public private partnership. |  |  |  |  | 1) 50% of public-private partnership contracts, the progress of which in implementation is regularly reported in the system within the deadlines provided for by law. 2) Reduction by 10% of initiated procedures for awarding a contract for establishing a public-private partnership, which have not been completed, in relation to the percentage of initiated but not completed procedures in the year as a basis for monitoring. |  |  | 1) 70% of public-private partnership agreements, the progress of which in implementation is regularly reported in the system within the deadlines provided for by law. 2) Reduction by 5% of initiated procedures for awarding a contract for establishing a public-private partnership, which have not been completed, compared to the previous year. |  |
| Deliverables in 2026: | - A Draft Law on Public Private Partnership has been prepared, after which the preparations for the selection of an IT company for the establishment of SESPPP will begin. |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Providing financial resources - donors/budget for the procurement of an IT company for the development of the EESJPP and the Register of awarded contracts for the establishment of a public private partnership. |  | 2027 | 2028 |  | MEMMR |  | MoF |  |  | N/A |  |  | N/A |
| MEASURE 2: Completing the legal and regulatory framework in the field of public-private partnership and Concession on goods of general interest |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| Adoption of the by-laws that will arise from the Law on Public-Private Partnership | Adoption of the by-laws by the Minister of Energy, Mining and Mineral Resources and their publication in the Official Gazette of the Republic of Macedonia |  |  | Preparation of 12 by-laws that stipulate in more detail the rules for: Register of awarded contracts for establishing public-private partnership, SESPPP, Feasibility study, PPP contracts, planning notification, etc. |  |  |  |  | Publication in the Official Gazette of the Republic of Macedonia of 12 by-laws that stipulate in more detail the rules for: Register of awarded contracts for establishing public-private partnership, SESPPP, Feasibility study, PPP contracts, planning notification, etc |  |  | Implementation of the bylaws |  |
| Deliverables in 2026: | The procedure for preparing the Draft By-Laws has been initiated. |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Preparation and adoption of 12 by-laws that will arise from the Law on Public Private Partnership |  | 2026 | 2027 |  | MEMMR |  | Working group for preparation of the bylaws Technical assistance of donors or arrangement of consultants. |  |  | EUR 22,000 |  |  | Financial gap |
| 2.Establishment of the consolidated Register of all concession agreements in accordance with the Law on Budgets. |  | 2026 | 2027 |  | MoF |  | / |  |  | / |  |  | / |
| MEASURE 3: Strengthening and developing the capacities of the Ministry of Energy, Mining and Mineral Resources in the area of ​​public-private partnership |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| Strengthened human resources capacities of the Ministry of Energy, Mining and Mineral Resources as the competent authority in the field of public-private partnership and concessions | Establishment of a Department for Public Private Partnership and Concessions and its staffing - increasing the capacity and efficiency of the Ministry of Energy, Mining and Mineral Resources as the competent authority in the field of public private partnership and concessions |  |  | Employment of 3 new civil servants – approved by the Ministry of Finance in proportion to the real employment needs in the Ministry of Energy, Mining and Mineral Resources as the competent authority in the field of public-private partnership and concessions and their training in the field of public-private partnership. |  |  |  |  | Employment of 3 new civil servants – approved by the Ministry of Finance in proportion to the real employment needs in the Ministry of Energy, Mining and Mineral Resources as the competent authority in the field of public-private partnership and concessions and their training in the field of public-private partnership |  |  | Development and improvement of the capacities of employees in the Ministry of Energy, Mining and Mineral Resources as the competent authority in the field of public-private partnership and concessions |  |
| Deliverables in 2026: | - The procedure for establishing a Department for Public Private Partnership and Concessions within the Ministry of Energy, Mining and Mineral Resources and staffing it with professional staff has been initiated. |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Establishing a Department for Public Private Partnership and Concessions within the Ministry of Energy, Mining and Mineral Resources as a competent authority in the field of public private partnership and concessions and staffing it with new employees and their professional training and development in order to ensure consistent implementation of the law in this area. |  | 2026 | 2027 |  | MEMMR |  | MoF |  |  | 192,000 eur |  |  | National Budget |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 214,000 |

| PILLAR V: Public finance digitalisation and continuous learning |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Implementation of an Integrated Financial Management Information System (IFMIS) |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  | Target FY 2026 |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Improved operational efficiency and transparency through IFMIS in line with the new OBL. | The required time for the processing of payments through IFMIS and Treasury Single Account interface was reduced |  | / |  |  | / |  |  | 5 days for entities to submit invoices to Treasury +1 day for payment processing by Treasury |
|  | Comprehensiveness of publicly published general government reporting |  | IFMIS bidding process is launched |  |  | IFMIS development is completed and the pilot implementation includes testing of reporting improvements |  |  | IFMIS is fully operational Regulatory agencies, and PEs are included as part of the budget execution reports through the new IFMIS, in line with new PE Registry. |
|  | Open Budget Index Score (transparency) increased |  | / |  |  | / |  |  | 61 out of 100 (2028) |
| MEASURE 1: Development of IFMIS as an integrated centralized web-based system |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  | Target FY 2026 |  |  | Target FY 2027 |  |  | Target FY 2028 |
| #### Development of new IFMIS application software and relevant GovTech solutions to operationalize the new OBL, as well as the new/enhanced PFM processes. | New IFMIS is operational |  | New IFMIS is being developed |  |  | The development of the IFMIS modules has been completed, and pilot testing of the developed modules is currently being conducted. |  |  | IFMIS is used in the preparation and execution of the central government budget |
| Deliverables in 2026: | - The IFMIS Solution Provider has been chosen, marking the initiation of the development phase for IFMIS modules |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |
|  |  | START qq/yy |  | END qq/yy |  |  |  | BUDGET | SOURCE |
| 1.Selection of IFMIS Solution Provider |  | 2026 |  | 2026 | Ministry of Finance |  | BETAPFMI PIU | N/A | / |
| 2.Development of IFMIS modules and installation of hardware system and interfaces |  | 2026 |  | 2027 | Ministry of Finance |  | BETAPFMI PIU | N/A | / |
| MEASURE 2: Expansion of MoF ICT infrastructure (in line with whole-of-government approach) to host new IFMIS |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  | Target FY 2026 |  |  | Target FY 2027 |  |  | Target FY 2028 |
| New IFMIS will be a centralized web-based shared platform to support decentralized operations (online/offline) countrywide. This measure involves the expansion of the Ministry of Finance's (MoF) Information and Communication Technology (ICT) infrastructure, aligning with a comprehensive government-wide strategy, with primary objective to accommodate the implementation of the new IFMIS. | Strengthening the capacity of MoF ICT infrastructure to support the implementation of new IFMIS |  | New data warehouse developed |  |  | / |  |  | Improved availability of the MDS and DRC |
| Deliverables in 2026: | New data warehouse developed |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |
|  |  | START qq/yy |  | END qq/yy |  |  |  | BUDGET | SOURCE |
| 1. Enhancement of the existing data centers and network connectivity |  | 2026 |  | 2028 | Ministry of Finance |  | BETAPFMI PIU | N/A | / |
| 2. Establishment of the secure backup network connections |  | 2026 |  | 2028 | Ministry of Finance |  | BETAPFMI PIU | N/A |  |
|  |  |  |  |  |  | TOTAL: |  |  | 0 |

| PILLAR V : Public finance digitalisation and continuous learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Public Finance Academy (Learning organisation) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| To provide continuous education for public administration in the field of public finance management. | Number of successfully completed trainings in accordance with the Annual Training Program and ad hoc trainings. |  |  | 20 realized trainings |  |  |  |  | 30 realized trainings |  |  |  | 50 realized trainings |  |  |
| MEASURE 1: Digital presence of the Public Finance Academy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  | Target FY 2028 |  |  |
| The digital presence aims to inform, establish, build trust, inspire and increase the reach and impact of the Academy. This encourages the e-learning process and supports the professional development of officials in the field of public finance in a simpler and more accessible way. | Established online platform |  |  | Established online platform |  |  |  |  | / |  |  |  | / |  |  |
|  | Developed video tutorials and guidelines |  |  | / Developed video tutorials and guidelines |  |  |  |  | / |  |  |  | / |  |  |
|  | Organized and implemented online trainings |  |  | realized 2 trainings |  |  |  |  | realized 4 trainings |  |  |  | realized 6 trainings |  |  |
|  | Number of published blogs and articles on topics in the field of public finance |  |  | 8 |  |  |  |  | 12 |  |  |  | 20 |  |  |
| Deliverables in 2026: | - Established online platform, - Developed video tutorials and guidelines, - Published blogs and articles on topics in the field of public finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  | TIMEFRAME |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |
|  |  |  |  |  | START qq/yy | END qq/yy |  | RESPONSIBLE INSTITUTION |  |  |  | BUDGET | SOURCE |  |  |
| 1. Developing an online platform |  |  |  |  | Q2/26 | Q4/26 |  | MoF |  | Donators |  | 47,000 EUR | Financial Gap |  |  |
| 2. Development of video tutorials and guidelines |  |  |  |  | Q2/26 | Q4/26 |  | MoF |  | Donators |  | 1,000 EUR | National Budget |  |  |
| 4.Social Media Presence for Increased Transparency and Education in Public Finance |  |  |  |  | Q1/25 | Q4/28 |  | MoF |  | / |  | 0 | / |  |  |
| Measure 3: Community engagement and outreach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  | Measure indicator: |  |  |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  | Target FY 2028 |
| The objective of community engagement and outreach is to foster inclusive participation, build public trust, and enhance the transparency and accountability in public finances. |  | Developed Communication Strategy |  |  |  |  | / |  |  |  | / |  |  | / |
|  |  | Conducted end-of-year meeting „All Together“ |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 |
| Deliverables in 2026: |  | - Developed media campaigne and promotional materials - Conducted end-of-year meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  |  | RESPONSIBLE INSTITUTION | OTHER INSTITUTIONS INVOLVED |  |  |  | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Anual meeting: „All Unite “ |  | Q4/25 | Q4/28 |  |  | MoF | Partners, trainers, participants, donors |  |  |  | 2,000 EUR |  |  | National Budget |
| Measure 4: Sustainable Finance in the public sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  | Measure indicator: |  |  |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  | Target FY 2028 |  |
| Sustainable public sector finance refers to the integration of environmental, social, and governance (ESG) principles into public financial policies. Its aim is to achieve long-term fiscal stability while promoting sustainable development goals. |  | Conducted Trainer of Trainers Trainings for employees of the Public Finance Academy |  |  |  |  | realized 1 training |  |  |  | realized 1 training |  |  | realized 1 training |  |
|  |  | Organization of trainings in the field of sustainable finance |  |  |  |  | realized 1 training |  |  |  | realized 2 training |  |  | realized 3 training |  |
| Deliverables in 2026: |  | - Delivered ToT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  |  |  | RESPONSIBLE INSTITUTION | OTHER INSTITUTIONS INVOLVED |  |  |  | PLANNED INPUTS |  |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |  |
| Training of Trainers for employees of the Public Finance Academy |  | Q1/25 | Q4/28 |  |  | MoF | donators |  |  |  | 4,000 EUR |  |  | Financial Gap |  |
| Organization of trainings in the field of sustainable finance |  | Q4/26 | К4/28 |  |  | MoF | Partners and collaborators |  |  |  | 1,000 EUR |  |  | National Budget |  |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | 55.000 EUR |  |

| PILLAR: VI - Public Internal Financial Control |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Financial Management and Control |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  | Target FY 2026 |  | Target FY 2027 | Target FY 2028 |
| Prepared procedures for key financial management elements | Percentage of institutions that have applied the guidelines for risk management in their operations |  |  |  | 60 |  | 65 | 70 |
|  | Percentage of institutions that have delegated authorities and responsibilities for financial management and control |  |  |  | 60 |  | 70 | 80 |
|  | Percentage of implemented recommendations given during quality checks |  |  |  | 60 |  | 70 | 80 |
| MEASURE 1: Creating the conditions for improvement of a system of financial management based on risk management |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2026 |  | Target FY 2027 | Target FY 2028 |
| Establishment of a comprehensive system of controls based on risk management, which guarantees the reasonable use of public funds by applying the principle of managerial accountability. | Prepared Simplified guideline for risk management process |  |  |  | Trainings 2 |  | Traininigs 2 | Trainings 2 |
|  | Prepared practical guideline for managerial accountability |  |  |  | Trainings 2 |  | Trainings 2 | Trainings 2 |
|  | Strengthen the capacities of CHU |  |  |  | Employed a total of 11 people Trainings 4 |  | Employed a total of 12 people Trainings 4 | Employed a total of 13 people Trainings 4 |
| Deliverables in 2026: | - Organized trainings for specific areas of financial management and control - Strengthened the CHU capacities (human resources/trainings/pilot quality checks) |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |
|  |  | START qq/yy | END qq/yy |  |  |  | BUDGET | SOURCE |
| 1. Strengthen the capacity of the CHU to monitor and report on the functioning of the overall internal control system |  | Q1/25 | Q4/28 | MоF |  | / | 32,000 | National Budget |
| 2. Preparation of the methodology for specific Financial Management and Control issues |  | Q1/25 | Q4/28 | MоF |  | / | 10,000 | National Budget |
|  |  |  |  |  |  |  | TOTAL: | EUR 42,000 |

| PILLAR: VI - Public Internal Financial Control |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2 : Internal audit |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Strengthened internal audit units that operate in line with the standards and that contributes to achievement of the goals of the public sector institutions | Number of internal auditors in the ministries |  | 60 |  |  |  | 65 |  |  | 80 |
|  | percentage of implemented recommendations given during quality checks |  | 60 |  |  |  | 70 |  |  | 80 |
|  | Percentage of certificated internal auditors |  | 60 |  |  |  | 70 |  |  | 80 |
|  | Percentage of implemented recommendations |  | 72 |  |  |  | 76 |  |  | 80 |
| MEASURE 1: Strengthening the quality of work of the internal audit units in the ministries |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Strengthening the quality of work of the internal audit units at the Ministries for the purpose of supporting the performance of their new tasks and duties as parent budget users. | Organized trainings for internal auditors; | 6 |  |  |  |  | 7 |  |  | 8 |
|  | Organized certification of internal auditors. | 2 |  |  |  |  | 2 |  |  | 2 |
|  | Strengthen the capacities of CHU | Employed a total of 11 Trainings 4 |  |  |  |  | Employed a total of 12 people Trainings 4 |  |  | Employed a total of 13 people Trainings 4 |
| Deliverables in 2026: | - Trainings for internal auditors - Certification of internal auditors. - Strengthened the CHU capacities (human resources/trainings/pilot quality checks) |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |
|  |  |  |  | START qq/yy | END qq/yy |  |  |  | BUDGET | SOURCE |
| 1. Improving of Human Resources capacities of Internal Audit Units in the Ministries through adequate staffing and Continuous Professional Development at the internal auditors |  |  |  | Q1/25 | Q4/28 | MF |  | Ministries | 20,000 | National budget |
| 2. Strengthening CHU’s capacities for checking the quality of operations of the internal audit units |  |  |  | Q1/25 | Q4/28 | MF |  | / | 32,000 | National budget |
| MEASURE 2: Improving the abilities to carry out performance and IT internal audits in the public sector institutions |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Increasing the number of conducted performance audits and IT audits which will contribute to improving the work of central-level institutions | Prepared Guideline for performance internal audits | 2 |  |  |  |  | 2 |  |  | 2 |
|  | Prepared Guideline for IT internal audits | 2 |  |  |  |  | 2 |  |  | 2 |
|  | Increased number of conducted performance audits and IT audits | 14 |  |  |  |  | 16 |  |  | 18 |
| Deliverables in 2026: | - Organized training for specific types of internal audit |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |
|  |  |  |  | START qq/yy | END qq/yy |  |  |  | BUDGET | SOURCE |
| 1.Preparation and promotion methodology for specific type of internal audits |  |  |  | Q1/25 | Q4/25 | MoF |  | / | / | / |
|  |  |  |  |  |  |  | TOTAL: |  |  | EUR 52,000 |

| PILLAR VII: External audit and parliamentary oversight |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: External Audit |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  | Target FY 2026 |  | Target FY 2027 |  |  | Target FY 2028 |
| Reduced tax evasion and increased fiscal discipline / increasing revenues in the Budget of RNM | Established amount of funds that have not been paid in the Budget of RNM |  |  | ≥ 11,000 euros |  | ≥ 9,000 euros |  |  | ≥ 7000 euros |
| Reduced tax evasion and increased fiscal discipline/increased revenues in the budgets of LSG and the City of Skopje | Established amount of funds that have not been paid into the Budget of the municipalities and the city of Skopje |  |  | ≥ 6,000 euros |  | ≥ 4,000 euros |  |  | ≥ 2,000 euros |
| Adhered principles when awarding public procurement contracts | Established amount of funds during the awarding of contracts for public procurement where irregularities were identified with the audits; |  |  | ≥ 7,500 euros |  | ≥ 7.300 euros |  |  | ≥7.000 euros |
| Scope of audits of LGUs and the City of Skopje, PE at the central and local level and trade companies in state ownership | Number of covered audits of LGUs and the City of Skopje, PE at the central and local level and trade companies in state ownership |  |  | ≥ 15 |  | ≥ 16 |  |  | ≥ 17 |
| MEASURE 1: Strengthen the legal framework for external audit |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  | Target FY 2027 |  |  | Target FY 2028 |
| Strengthen the constitutional, financial and operational independence of the SAO | Adopted amendments to the Constitution of RNM regulation of the SAO as a constitutional category |  |  | / |  | / |  |  | Adopted amendments to the Constitution of RNM for the regulation of SAO as a constitutional category |
|  | A new State Audit Law aims to strengthen the financial and operational independence of the SAO has been approved and adopted by the RNM Assembly |  |  | A new draft Law on State Audit to strengthen the financial and operational independence of the SAO has been approved and adopted by the RNM Assembly |  | / |  |  | / |
| Deliverables in 2026: | - Approved draft amendment to the Constitution of the RNM for SAO regulation as a constitutional category to be submitted by the authorized proposer of the constitutional amendment to the Assembly of the RNM for adoption; - A new draft State Audit Law aims to strengthen the financial and operational independence of the SAO to be approved and submitted to the RNM Assembly for adoption; - Proposals for by-laws based on the improved legal framework |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  | BUDGET |  | SOURCE |
| 1. Approval of constitutional changes to achieve constitutional independence of the SAO in accordance with the principles, standards and guidelines of INTOSAI |  | Q1/2022 | Q4/2028 |  | Authorized proposer of the constitutional amendment; Assembly of RNM |  | 7,000 |  | External funding NDI and others |
| 2. Approval of external audit legal framework aimed at strengthening financial and operational independence of SAO in line with INTOSAI principles, standards and guidelines |  | Q1/2022 | Q4/2025 |  | Ministry of Finance, Government of RNM and Assembly of RNM |  | 14,000 |  | External funding NDI and others |
| MEASURE 2: Strengthening the institutional capacity and human resource capacities of the SAO |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2026 |  | Target FY 2027 |  |  | Target FY 2028 |
| Implementation of SAO Development Strategy 2023-2027 SAO Annual report on performed audits and operations | Percentage of implementation of SAO Development 2023-2027 |  |  | Percentage of implementation of the activities determined in the Strategy for the Development of SAO 2023 - 2027 - -80% |  | Percentage of implementation of the activities determined in the Strategy for the Development of SAO 2023 - 2027 - -100% |  | Percentage of implementation of the Strategy for the Development of SAO 2023 - 2027- 100% |  |
| Audit scope of total public expenditures SAO Annual report on performed audits and operations | Percentage of audit scope of total public expenditures |  |  | ≥61% |  | ≥61.5% |  | ≥62% |  |
| Results from stakeholder surveys on the added value of the SAO | Perception of stakeholders on SAO added value |  |  | Stakeholders' perception of the added value of SAO-82% |  | Stakeholders' perception of the added value of SAO-83% |  | Stakeholders' perception of the added value of SAO-85% |  |
| Deliverables in 2026: | -Analysis with recommendations for improving the audit process on the Annual Account of the Budget of the Republic of North Macedonia; -New or improved methodological acts and tools on topics relevant to the responsible management and use of public funds for audits of sustainable development goals, audits of financial statements prepared on an accrual basis, audits of value for money (Value for Money), audits of LSGU, audit of public enterprises and state-owned companies, audit of financial statements of the Core budget, audit of Reform and Growth Facility, real time audits, forensic audit, ESG reporting and audit, in line the INTOSAI standards and IFRS Standards and best practises and etc. -Conducted performance audits in relevant areas of government policy and audits on certain topics of importance for the responsible management and use of public funds (audit of EU funds, audits of sustainable development goals, audit of financial statements prepared on an accrual basis, audit of values for money (Value for money), audits of LGUs, gender equality audit, audits in the areas determined in the National Development Strategy of the Republic of North Macedonia, audit of Reform and Growth Facility, etc.); -Conducted training (study visits, conferences, seminars, workshops) according to SAO Annual plan for continuous profesional development for 2025; -Trainings, and workshops for strengthen cooperation with stakeholders and anticorruption bodies; -Using modern auditing tools, methodologies, techniques, and development of software tools for reclassification of financial statements/software tools for auditing financial statements prepared on an accrual basis; -Use of modern equipment and improved working conditions -Using visualization (infographics, video presentations, flyers) to present the results of the audit to the public. -New channels for communication with stakeholders (the Assembly, the Government, the Ministry of Finance, the Public Prosecutor's Office, the Ministry of Internal Affairs, the State Commission for the Prevention of Corruption, the entities subject to audit, the public); -Using digital tools to achieve efficient cooperation and communication with parliamentary bodies to support the work of the RNM Assembly; -Conducting peer review according to the International standards of INTOSAI; -New forms for monitoring and presenting the implementation of audit recommendations |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  | BUDGET |  | SOURCE |
| 1. Implementation of adopted new and improved SAO strategic, planning and methodological acts of the SAO and adoption of new methodological acts |  | К1/2025 | К4/2028 | SAO |  |  | 100,000 |  | External funding WFD, NDI, UNDP, UnWomen and others |
| 2. Strengthen the capacity to conduct audits |  | К1/2025 | К4/2028 | SAO |  |  | National budget 214,500 + donors 706,400 920,900 |  | Domestic funding and External funding ЕU, World Bank, SIGMA WFD, NDI, UNDP, UnWomen and others |
| 3. Increasing the visibility of the SAO and communication with the stakeholders |  | К1/2025 | К4/2028 | SAO | Stakeholders (Assembly, Government, Ministry of Finance, Public Prosecutor's Office, Ministry of Interior, State Commission for Prevention of Corruption, audited entities, the public). |  | 200,000 |  | External funding ЕU, World Bank, SIGMA WFD, NDI, UNDP, UnWomen and others |
|  |  |  |  |  |  |  | TOTAL: |  | EUR 1.241.900 |

| PILLAR VII: External Audit and Parliamentary Oversight |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Parliamentary Oversight |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  | Target FY 2028 |
| Enhanced effects of audit. | Percentage of external audit recommendations for which corrective measures have been taken. |  |  |  | ≥74% |  |  | ≥76% |  |  |  | ≥78% |
| MEASURE 1: Establishing a mechanism for reviewing the audit reports and the measures taken following the recommendations given in the audit reports in the RNM Assembly |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Strengthening institutional mechanism for reviewing audit reports by the Assembly of RNM. | Number of audit reports reviewed by the Assembly. |  |  |  |  | Number of audit reports reviewed by the Assembly. ≥4 |  |  | Number of audit reports reviewed by the Assembly. ≥4 |  |  | Number of audit reports reviewed by the Assembly. ≥5 |
| Deliverables in 2026: | - Final procedures of the SAO for preparing and submitting audit reports and other documents to the RNM Assembly; - Proposal - procedures for manner of reviewing audit reports (from receipt of audit reports and other documents to adoption conclusions and monitoring implementation of audit recommendations) in the RNM Assembly. |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1.Implementation of concluded Memorandum of Cooperation between the Assembly and the SAO. |  | К4/2022 | К4/2028 | SAO |  |  | RNM Assembly |  |  | / |  | / |
| 2.Preparation of final/proposal procedures in the SAO and the Assembly for submission and review of audit reports and other documents. |  | К2/2022 | К4/2028 | SAO |  |  | RNM Assembly |  |  | 9,200 |  | External financing NDI, WFD, UNDP and others |
| MEASURE 2: Strengthening the institutional capacities for reviewing audit reports in the Assembly of RNM |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  | Target FY 2028 |
| Strengthened institutional capacities for reviewing the audit reports in the Assembly of RNM. | Number of MPs trained on the role of the SAO. |  |  |  |  | Number of MPs trained on the role of the SAO – 15. |  |  | Number of MPs trained on the role of the SAO – 20. |  | Number of MPs trained on the role of the SAO – 25. |  |
| Deliverables in 2026: | - A training plan for MPs in the Committee on Financing and Budget and other MPs who participate in the committees and employees of the RNM Assembly Service to facilitate the understanding of audit reports and preparation for discussion on audit reports; - Conducting trainings in accordance with the Training Plan for MPs and employees of the Service in order to understand the audit reports and to prepare for the debate on the audit reports (through study visits, workshops, case studies, debate simulations); - Activities to strengthen cooperation with the Committee on Financing and Budget, the Parliamentary Institute and the Parliamentary Budget Office of the Assembly of the RNM |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Preparation of a Training Plan for MPs and employees of the RNM Assembly Service inorder to facilitate the understanding of the audit reports and preparation for a debate on the audit reports. |  | К4/2025 | К4/2028 | SAO |  |  | RNM Assembly |  |  | 2,200 |  | External financing NDI, WFD, UNDP and others |
| 2. Conducting trainings in accordance with the Training Plan for the Members of Parliament and employees of the RNM Assembly Service in order to facilitate the understanding of the audit reports and preparation for the debate on the audit reports. |  | К4/2025 | К4/2028 | SAO |  |  | RNM Assembly |  |  | 28,000 |  | External financing NDI, WFD, UNDP and others |
| 3.Implementation of activities for strengthening cooperation with Committee on Financing and Budget, Parliamentary Institute and the Parliamentary budget office of the RNM Assembly. |  | К2/2023 | К4/2028 | SAO |  |  | Committee on Financing and Budget, Parliamentary Institute and Parliamentary Budget Office of the Assembly of RNM |  |  | 24,000 |  | External financing NDI, WFD, UNDP and others |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  | EUR 63,400 |

| Pillars | Priority | Budget |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | National budget | Donor funds | Financial gap | Total |
|  |  | in EUR | in EUR | in EUR | in EUR |
| I Economic Analysis, Macroeconomic and Fiscal Framework | 1.Tax Revenue forecasting and reporting | 0 | 130,000 | 0 | 130,000 |
|  | 2.Economic analysis and Macroeconomic forecasting | 0 | 210,000 | 0 | 210,000 |
|  | 3.Strengthening Debt Management | 14,200 | 10,000 | 0 | 24,200 |
| II Revenue Mobilization | 1.Tax and Customs Policy | 0 |  | 500,000 | 500,000 |
|  | 2.Tax Administration | 5,057.240 | 0 | 0 | 5,057.240 |
|  | 3.Customs | 1,000,000 | 7,000.000 | 0 | 8,000.000 |
| III Planning and Budget | 1.Budget Planning | 0 | 660,000 | 0 | 660,000 |
|  | 2.Strengthened Public Investment Management | 30,000 | 240,000 | 0 | 270,000 |
|  | 3. Strengthen the accounting of budgets and budget users | 0 | 0 | 0 | 0 |
|  | 4. PFM at Local Level | 2,000 | 0 | 0 | 2,000 |
| IV Public procurement | 1.Public Procurement Policy | 0 | 0 | 0 | 0 |
|  | 2. Public Private Partnership and Concessions on goods of general interest | 192,000 | 0 | 22,000 | 214,000 |
| V Public finance digitalisation and continuous learning | 1. Implementation of an Integrated Financial Management Information System (IFMIS) | 0 | 0 | 0 | 0 |
|  | 2. Public Finance Academy (Learning organisation) | 4,000 | 0 | 51,000 | 55,000 |
| VI Public Internal Financial Control | 1.Financial Management and Control | 42,000 | 0 | 0 | 42,000 |
|  | 2.Internal Audit | 52,000 | 0 | 0 | 52,000 |
| VII External audit and parliamentary oversight | 1.External audit | 214,500 | 1.027,400 | 0 | 1,241.900 |
|  | 2.Parliamentary Oversight | 0 | 63,400 | 0 | 63,400 |
| Total |  | 6,607.940 | 9,340.800 | 573,000 | 16,521.740 |