PRIMARY EDUCATION IMPROVEMENT PROJECT (PEIP)

Terms of Reference

for

DATA COLLECTION FOR MEASURING THE QUALITY OF TEACHING PRACTICES IN PRIMARY EDUCATION

- BACKGROUND OF THE PROJECT

The Primary Education Improvement Project (PEIP) development objective is to improve conditions for learning in primary education in North Macedonia.

The Project would support the Government of North Macedonia’s initiatives geared to:

- improve learning environment at the primary level;

- increase number of primary education teachers with proven professional practice in two core teacher professional competencies i.e. teaching and learning and creating a stimulating learning environment;

- improve quality of teaching practices; and

- implement school improvement plans that use performance data and monitoring tools for improving student learning.

The Ministry of Education and Science (MOES) is the main implementing agency of the Project in close cooperation with the National Examination Center (NEC), Bureau for Development of Education (BDE) and State Educational Inspectorate (SEI). Projects direct beneficiaries include primary education students, but focused support will be given those who are vulnerable (Roma, girls, students disproportionally affected by the closure of schools due to the COVID-19 pandemic) which are expected to benefit from improved learning and physical environment in the schools as well as from better-trained teachers. Primary education teachers, school principals, and MPSTs will benefit from more efficient professional development and career advancement, teaching adds, and grant program to implement their school improvement plans. The project activities are targeted toward building the foundation of a modern and efficient primary education system that is orienting all parts of the system toward learning.

Although better teaching practices are needed to tackle the learning crisis, most education systems in low- and middle-income countries do not regularly monitor them, either because they do not recognize the importance of such practices, or do not know how to monitor them. The reality is exacerbated by a prevalence of ineffective professional development programs, which tend to be theory-based and rarely monitor or provide actionable guidance for teachers to improve their practice. Even when teacher practices are monitored, the tools used to capture them fall short on several accounts, as they: (i) measure either the occurrence or quality of a given practice; (ii) do not explicitly focus on teachers’ efforts to develop students’ socioemotional skills; (iii) use tools designed for other contexts, which can be culturally irrelevant, costly, and difficult to implement; and (iv) use tools that are neither evidence-based nor meet basic reliability criteria.

Teach was developed to address these challenges. First, Teach is the first tool to holistically measure what happens in the classroom. It does so by considering not just time spent on learning but, more importantly, the quality of teacher practices. Secondly, Teach captures practices that nurture children’s cognitive and – for the first time – socioemotional skills. Third, Teach was developed with low-and middle-income countries in mind, and includes the use of local video footage to contextualize the training. Finally, Teach includes a toolkit that facilitates data collection, analysis, and validation of Teach scores.

To implement Teach, an observer training is conducted by local Implementors to ensure all observers are reliable on the tool. Without a reliability protocol in place, even experienced education professionals struggle to distinguish between effective and ineffective teachers. The reliability training includes an overview of how and why Teach was created, an in-depth understanding of the Teach framework and behaviors, videos to practice coding, a field visit to code a live observation, and a reliability exam. Observers that do not passed the reliability exam will not be able to go to the field. Those that passed the exam will then be sent out to schools to collect data on classroom observations using the Teach tool. Observers are individuals that sit-in on a class and observe two, 15-minute segments of the lesson. At the end of each segment, the observers use the Teach rubric to score the teacher based on a set of behaviors outlined in the tool.

2. OVERALL OBJECTIVE OF THE ASSIGNMENT

The overall objective of this assignment is to capture institutional quality in North Macedonia classrooms using the TEACH tool (in-class observation tool), with the goal of providing information on the quality of teacher’s practices in primary education. This tool will provide evidence to improve competencies of school staff through (a) implementation of professional standards and (b) modernization of in-service professional development programs. MoEs is going to hire an international certified TEACH expert that will lead the in-country training and master coding process. The TEACH expert will also manage the project and guide the survey company through the observation and data collection process.

3. SPECIFIC OBJECTIVE/PURPOSE OF THE ASSIGNMENT

The specific objective of this assignment is to select a survey firm that will implement the TEACH tool in the field (baseline and follow-up data collection) in a sample of 35 selected primary schools. The responsibilities of the survey firm include i) recruiting and training 2 field supervisors; ii) recruiting and training 7-10 observers to pilot the instruments, conduct the fieldwork, code and support data cleaning. iii) supervising and coordinating logistics for observers and field supervisors to conduct observations in 35 schools for the baseline survey in 2022 [estimated period 1-31 March 2022] and for the follow-up survey in 2025 [estimated period 1-30 October 2025]  . The survey firm will manage these tasks, which will have agreed quality standards associated with them, as outlined by an English speaking Teach expert hired separately by the Client.

4. SCOPE OF WORK

In close coordination with the relevant stakeholders (BDE, MoES) and under the supervision of a TEACH Expert, the survey firm will conduct in-class observations using the TEACH observation tool, data collection, data coding, entry and cleaning for the purpose of observing and assessing the quality of teaching practices in the Republic of North Macedonia on two occasions, once as a baseline and once as a follow up survey. Team members have to undergo training facilitated by a TEACH expert provided by the Client and pass an exam that certifies them for in-class observation and coding in accordance with the TEACH tool requirements. In completing the work the firm must take into consideration that the languages of instruction in primary schools are Macedonian, Albanian, Turkish, Bosnian and Serbian.

More specifically the survey firm will be responsible for the following tasks:

Stage 1: Preparatory Work (same for baseline and follow-up survey)

- Create an observer training plan, which specifies a recruitment timeline and training logistics, in coordination with the Teach expert.

- Develop the survey implementation plan, which includes the field plan, field protocol, and data management plan.

- Procure a sufficient number of high definition video cameras, tablets, and related equipment for data collection.

- Recruit a videographer, collect video footage from 3 classrooms, edit the videos into 15-minute segments chosen by the Teach expert, transcribe in Macedonian and translate into English, and embed English transcription into video as subtitles

- Coordinate full training logistics for observers to participate in a 4-day training and 1 day for the Reliability Exam.

- Translating and printing materials where applicable

Stage 2: Fieldwork (same for baseline and follow-up survey)

- Teach will be used to collect data at 35 randomly selected primary schools. Fieldwork will tentatively be conducted for the baseline survey in March 2022 [4 weeks] and for the follow-up survey in October 2025 [4 weeks] .

- Two observers are required per school to complete all necessary activities. For each school, two observers will use Teach to observe two full-length classrooms. Each full-length observation will consist of two, 15-minute segments. After the observers observe one full-length classroom together, they will proceed to observe one additional full-length classroom independently. In total, the two observers will each observe two full-length classrooms (one of which will be conducted together). Each school survey is expected to last a full day.

- Use SurveyCTO to collect the data. SurveyCTO makes it possible to input Teach scores digitally, which minimizes error and expedites the data collection process.

Stage 3: Final Datasets (same for baseline and follow-up survey)

Once the data is collected with a tablet or phone, it is exported from SurveyCTO as an Excel file. This file is perfectly aligned with the pre-created do-files provided by the Teach expert, which will automatically label the data and deliver the final STATA database.

5. OVERVIEW OF TASKS

The following tasks/activities will be undertaken by the survey firm:

Staffing

- Recruit 8-10 observers to conduct classroom observations

- Recruit 2 experienced field supervisor(s) to oversee classroom observations, ensure data quality assurance, and manage communications with the MOES and Teach expert.

- Recruit 1 videographer to collect and edit practice and exam video footage

Logistics

- Provide training venue and full logistics for observers to participate in the training, including simultaneous interpretation services if needed.

- Coordinate logistics for observers to visit the schools designated in the sample, including approval for classroom observations and video recording.

- Organize and provide logistical support (transport, per-diem, etc.) to observers and field supervisor(s) as data is being collected.

- Translating, and printing materials where applicable

Sampling

- Select 2 teachers to observe from each school in the sample;

- Comply with all the sampling requirements; including the agreed approach to teacher selection. The sample will be agreed with MOES and the Teach expert and will include maximum 35 schools.

Data Collection and Data Management

- Implement and oversee all fieldwork.

- Ensure the data collected by observers meet the specifications agreed upon by the MOES team by ensuring the field supervisors monitor observers to ask follow-up questions and cross-check reliability.

  - PAPI: Prepare and deliver clean STATA datasets to the MOES; also provide all scanned classroom observation forms, neatly organized in a digital folder. This STATA database must include the School name, Teacher name, municipality, town, village, and any other details relevant to the sample.

  - CAPI: use SurveyCTO application to collect and deliver clean STATA datasets to the MOES.

6. SCHEDULE OF DELIVERABLES AND EXPECTED OUTPUTS

The survey firm’s output is expected to consist of, but is not restricted to, the following deliverables:

1. BASELINE SURVEY DELIVERABLES:

a. Inception report for baseline survey:

This report should outline all the preparatory work for the baseline survey including training report and the list of observers that passed the Teach reliability exam.

b. Baseline survey fieldwork report:

This report should include a report on the process of the data collection, a  database of all observational data including scanned forms (data will be entered twice to ensure there are no mistakes and the Teach protocol shall be followed to ensure the variables are labeled correctly in the dataset).

c. Final clean datasets for the baseline survey:

- If not using the Teach computer assisted software, clean dataset in STATA format with unique identifiers for all facilities and individuals (schools and teachers) observed; must contain variable and value labels constructed from the provided STATA do file.

- Organized classroom observation forms;

2. FOLLOW-UP SURVEY DELIVERABLES:

a. Inception report for follow-up survey:

This report should outline all the preparatory work for the baseline survey including training report and the list of observers that passed the Teach reliability exam.

b. Follow-up survey fieldwork report:

This report should include a report on the process of the data collection, a  database of all observational data including scanned forms (data will be entered twice to ensure there are no mistakes and the Teach protocol shall be followed to ensure the variables are labeled correctly in the dataset).

c. Final clean datasets for the follow-up survey:

- If not using the Teach computer assisted software, clean dataset in STATA format with unique identifiers for all facilities and individuals (schools and teachers) observed; must contain variable and value labels constructed from the provided STATA do file.

- Organized classroom observation forms;

Timing and Structure of Payments

The survey firm will be paid in six installments according to the following schedule:

            - 10% upon submission of Inception report for the baseline survey;

            - 20% upon submission of Baseline survey fieldwork report;

            - 20% upon submission of Final clean datasets for the baseline survey

            - 10% upon submission of Inception report for the follow-up survey;

            - 20% upon submission of Follow-up survey fieldwork report;

            - 20% upon submission of Final clean datasets for the follow-up survey

The survey firm shall be at the MOES disposal for subsequent dissemination and strategic advising with all other interested stakeholders.

7.  FIRM QUALIFICATIONS:

- The firm should be in the business of data collection for at least 5 years.

- The firm should have specific similar experience on at least 3 large scale surveys in the public service delivery sector in North Macedonia conducted over the past 10 years.

- The firm should have an established network of experienced enumerators, supervisors and data processors.

8. STAFF QUALIFICATIONS

A. Skills and competencies of key staff:

Team Leader (one staff member)

- Bachelor’s degree;

- Minimum 5 years’ previous experience in managing teams, supervising and coordinating all technical aspects of a contract;

- Expertise in research methodology;

- In depth knowledge of questionnaire construction and sample design;

- Experience in organization and overseeing administrative and logistical support;

- Excellent knowledge of monitoring and evaluation;

- Excellent drafting and reporting skills;

- Oral and written fluency in English and Macedonian.

Field Supervisor(s) (at least 2 staff members)

- Bachelor’s degree

- Minimum 5 years’ previous experience conducting large facility level surveys or classroom observations in the public service delivery sectors.

- Knowledge of the varying cultural context/sensitivities throughout North Macedonia.

- Understanding of the North Macedonia education sector.

- Previous experience with classroom observation tools shall be considered an advantage.

- Proficient in data entry and organization.

- Oral and written fluency in English and Macedonian.

- Strong project management skills and attention to detail.

B. Skills and competencies of support staff:

Observers (at least 8 staff members)

- Bachelor’s degree.

- Passage of the Teach reliability exam.

- Oral and written fluency in English and Macedonian.

- Previous experience with classroom observation tools (preferred).

Videographer (1 staff member)

- Minimum 5 years’ previous professional experience in recording and editing videos, and embedding subtitles

- Oral and written fluency in English and Macedonian.

9. PERIOD OF CONSULTANCY

The consultancy will run from February 2022 to February 2026.

10. INTELLECTUAL PROPERTY

The Ministry of Education and Science shall, solely and exclusively, own all rights in and to any work created in connection with this assignment/contract, including all data, documents, information, copyrights, patents, trademarks, trade secrets, or other proprietary rights in and to the work. The survey firm is not allowed to post or publish (electronically or in print) any project-related information without the explicit permission of the Ministry of Education and Science.

https://www.worldbank.org/en/topic/education/brief/teach-helping-countries-track-and-improve-teaching-quality