ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	3

1.5.	Related programmes and other donor activities	4

2.	OBJECTIVES & EXPECTED OUTPUTS	5

2.1.	Overall objective	5

2.2.	Specific objective(s)	5

2.3.	Expected outputs to be achieved by the contractor	5

3.	ASSUMPTIONS & RISKS	6

3.1.	Assumptions underlying the project	6

3.2.	Risks	6

4.	SCOPE OF THE WORK	6

4.1.	General	6

4.2.	Specific work	7

4.3.	Project management	8

5.	LOGISTICS AND TIMING	8

5.1.	Location	8

5.2.	Start date & period of implementation of tasks	8

6.	REQUIREMENTS	9

6.1.	Personnel	9

6.2.	Office accommodation	9

6.3.	Facilities to be provided by the contractor	9

6.4.	Equipment	9

7.	REPORTS	10

7.1.	Reporting requirements	10

7.2.	Submission and approval of reports	10

8.	MONITORING AND EVALUATION	10

8.1.	Definition of indicators	10

8.2.	Special requirements	10

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

The Contracting Authority (CA) is the Ministry of Sport of the Republic of North Macedonia, Skopje

- 1.3. Country background

North Macedonia is a Southeast European country with a growing focus on public health, education, and youth inclusion. In recent years, efforts have been made to increase physical activity, especially through educational reforms. However, there is still a lack of systematic national-level data, low engagement in organized sport, gender disparities in participation, and limited infrastructure in rural and underserved areas. While enthusiasm for sport is high, participation is often informal and not sustained...

- 1.4. Current situation in the sector

Despite successful implementation of EWoS in past years, physical activity levels remain low. The effects of the COVID-19 pandemic, increased screen time, and a lack of local strategies have reduced participation in organized sports. EWoS IMPACT responds by promoting inclusive, accessible sport opportunities and fostering social and physical engagement across all demographics.

The Ministry of Sport and the National Coordinating Body (NCB) are developing and piloting a National Strategy for Recreational Sport and Health, focusing on:

- Structured after-school programs

- Inclusive access for people with disabilities and marginalized communities

- Community-based sport infrastructure

- Capacity-building of coaches, teachers, and volunteers

- Cross-sectoral partnerships with municipalities, schools, and NGOs

The NCB is implementing nationwide data collection (2024–2026) through questionnaires in schools, analysis of participation trends, and evidence-based planning to increase physical activity by 5% on a national level.

- 1.5. Related programmes and other donor activities

The project aligns with EU initiatives on youth, inclusion, and sport. It complements:

- National education reform to increase physical education in schools

- Public health campaigns supported by the Ministry of Health

- EU-funded projects focused on inclusion and well-being

- Local and regional donor-supported sport infrastructure and youth initiatives

Past EWoS cycles (2022–2023) laid the foundation for municipal partnerships and community activation. In 2024 and 2025, the focus is on scaling up with stronger local ownership, data collection, and the introduction of the national recreational sport strategy across 25 pilot municipalities.

## Concept for BeActive EWoS IMPACT

EWoS IMPACT stands for Inclusion, Movement, Physical Education, Aspiration, Communities, and Teamwork. The concept is built on the belief that sport has the power to unite, inspire, and improve well-being—especially in times of growing digital dependency and social disconnection.

Key elements of the concept include:

- Providing opportunities for youth and marginalized communities to participate in structured sport programs

- Reducing screen time through movement-based engagement in schools and communities

- Promoting teamwork, resilience, and leadership through inclusive games and recreational challenges

- Encouraging social inclusion regardless of age, gender, ability, or background

- Supporting mental and physical health through movement, collaboration, and creative play

- Empowering women and girls, cultural minorities, and people with disabilities

By 2025, the goal is to establish a national framework that sustains local action. This will be achieved through:

- Data collection and research

- Media campaigns promoting physical activity

- Policy integration and institutional support

- Community mobilization and training of local actors

- Creating networks of sport implementors from local to national level

EWoS IMPACT will ensure that sport becomes a driver of inclusion, health, and opportunity for all citizens of North Macedonia.

# 2. OBJECTIVES & EXPECTED OUTPUTS

### 2.1. Overall Objective

The overall objective (Impact) to which this action contributes is:

PROCUREMENT OF TECHNICAL SUPPORT RENTAL (SOUND AND LIGHTING EQUIPMENT) FOR EUROPEAN WEEK OF SPORT - EWOS IMPACT (INCLUSION, MOVEMENT, PHYSICAL EDUCATION, ASPIRATION, COMMUNITIES AND TEAMWORK.

### 2.2. Specific Objective(s)

The implementation of the present contract will support the Contracting Authority in the process of implementing the diverse and elaborated work programme of project European week of sport - EWoS IMPACT (Inclusion, Movement, Physical education, Aspiration, Communities and Teamwork, by providing well-organized, quality and timely services related to Procurement of technical support rental (sound and lighting equipment), the services shall be provided in the scope of the entire contract duration at any given time by a preliminary request of the Contracting Authority to the contractor. The Contracting authority is to assign the required technical equipment needed for the project events and the  deliverables referring to the consulting company. The contractors must ensure that actions that are wholly or partially funded by the European Union (EU) incorporate information and communication activities designed to raise the awareness of specific or general audiences of the reasons for the action and the EU support for the action in the country or region concerned, as well as the results and the im-pact of this support.

The position where the technical equipment need to be positioned shall be agreed with the Project Coordinator and approved by the Contracting Authority.

### 2.3. Expected Outputs to Be Achieved by the Contractor

The expected outputs from the contract are to be delivered the following technical support rental (sound and lighting equipment) for implementation of the European week of the sport. In detail the quantity and type of the technical support rental (sound and lighting equipment) are given in separate document – Technical Specifications.

The contractor is expected to contribute to the delivery of the following key outputs under the supervision of the National Coordinating Body (NCB):

Sound system

Stage construction

Stage (podium)

LED screen

Electrical extenders

Power generator

Lighting equipment

DJ desk and equipment

Wireless microphones

Technical team

Portable speakers

Cables and adapters

Awards podium

Walkie-talkies

Video camera with operator

# 3. ASSUMPTIONS & RISKS

Assumptions underlying the project

The encountered assumptions behind the Project, matter of interest of these Terms of Reference are listed as follows:

–	Excellent, timely and smooth communication and cooperation between all involved relevant stakeholders and counterparts;

–	Support and commitment of all relevant governmental institutions and of all international stakeholders;

–	Stable political and social environment;

–	Adequate human and financial resources are made available to ensure proper execution of the Contract;

–	National budget resources available;

–	The contracts are managed correctly.

Risks

The Contractor shall ensure that risks are identified, recorded and regularly submitted to the Contracting Authority for consideration. A risk management cycle must be included in the Annex III - Organization and Methodology of the Tender, clearly specifying who, how and when will deal with risks and take the necessary decisions at different management levels.

The following are key risks to be taken into account:

- Risks occur in case the assumptions listed above (Section 3.1) are not met during the project preparation and implementation;

- Lack of support staff needed for project realization;

- Lack of cooperation between involved parties

# 4. SCOPE OF THE WORK

## General

    - Description of the assignment

In the frame of this Project, the Ministry of Sport shall implement several different types of contracts in order to achieve the Project objective.

Regarding the rules that should be followed during the implementation of these contracts, it is clearly defined that the PRAG rules (A Practical Guide to Contract Procedure for European Union External Actions)  shall be followed during the implementation i.e. depending of the threshold of the contract a particular PRAG procedure will be followed.

Ministry of Sport is to assign the technical support rental (sound and lighting equipment) required for the project European week of sport - EWoS IMPACT (Inclusion, Movement, Physical education, Aspiration, Communities and Teamwork, by providing well-organized, quality and timely services related to Procurement of technical support rental (sound and lighting equipment), the services shall be provided in the scope of the entire contract duration at any given time by a preliminary request of the Contracting Authority to the contractor. The Contracting authority is to assign the printed materials and sport equipment need for the project events and the  deliverables referring to the consulting company. The contractors must ensure that actions that are wholly or partial-ly funded by the European Union (EU) incorporate information and communication activities designed to raise the awareness of specific or general audiences of the reasons for the action and the EU support for the action in the country or region concerned, as well as the results and the impact of this support.

initiative

### Specific Work

### A clear and detailed list of the tasks to be undertaken in order to achieve the contract results are given in separate document Technical Specifications, that is in part D of the tender dossier. Project Management

### Responsible body

The Contracting Authority will be the Ministry of Sport and execution supported through the National Coordination Body (NCB) which will be responsible for all administrative and procedural aspects of the tendering process, contracting matters and financial management, including payment of project activities.

- Project Planning and Reporting:

  - Support the development of a detailed project plan, including tasks, timelines, and resources required for timely implementation of the contract, in line with the requirements for the project .

  - Prepare monthly internal progress reports and final narrative reports.

  - Participate in regular project meetings,

- Quality Assurance and Risk Mitigation:

  - Identify risks (e.g., low stakeholder engagement, logistical delays) and assist in implementing mitigation strategies.

  - Maintain flexibility to adjust plans based on real-time feedback and evolving needs.

- Team Coordination and Logistics:

  - Collaborate closely with other team members within the NCB and external contractors.

  - Contribute to smooth information flow between national and local stakeholders.

  - Coordinate local project implementation teams and track task completion.

By contributing to all stages of the project life cycle, the Contractor ensures the successful and sustainable achievement of EWoS IMPACT objectives in line with national health and sport priorities.

# LOGISTICS AND TIMING

## Location

The implementation of the EWoS IMPACT project will be carried out across the territory of the Republic of North Macedonia, with national coordination led by the Ministry of Sport located in Skopje, and execution supported through the National Coordination Body (NCB) in collaboration with:

- 25 selected municipalities during the pilot phase (September–December 2024)

- All municipalities nationwide during the main implementation phase (September 2025–May 2026)

### 5.2. Start Date & Period of Implementation of Tasks

Start Date:

- The intended start date is September 2025 and the period of implementation of the contract will be 2 months from this date.

# REQUIREMENTS

## 6.1 Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organizations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

All personnel must demonstrate relevant qualifications and experience in project coordination, communication, community development, event management, or technical fields as appropriate. Fluency in Macedonian is required, while knowledge of Albanian and English is considered an asset. All staff must be available during the full project implementation period.

#### 6.2. Office Accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contractor.

#### 6.3. Facilities to be Provided by the Contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion. The contractor is responsible to ensure all necessary supplies, documentation, logistical support etc for the success of the contract. Please note that global price contract do not entail reimbursable/incidental expenditure.

#### 6.4. Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

To ensure effective monitoring, evaluation, and accountability, the contractor (economic operator) shall be responsible for submitting two core reports over the duration of the project:

- Interim Report

  - Submission timeline: By the end of Month 1

  - Format: A narrative report accompanied by annexes (photos, materials, media, etc.), financial documentation, and updated logframes or indicators tracking tools.

- Final Report

  - Submission timeline: 10 days before end date of contract

  - Scope: The final report shall provide a comprehensive summary of the entire project lifecycle, including:

    - Overview of all activities implemented

  - Format: Final narrative report with annexes (photos, designs, digital materials, stakeholder statements), financial closing report, full data overview (Google Analytics, surveys, event reports), and final evaluation tools/results.

Additional reporting may be requested by the contracting authority in the form of:

- Activity summaries before/after major events or milestones

- Visibility materials and media reach reports

- Ad hoc progress notes or briefs on request by the Ministry of Sport or the European Commission

All reports must adhere to the EU visibility guidelines and be submitted in English and/or Macedonian depending on the target audience, with key financial tables available in both.

#### 7.2. Submission and Approval of Reports

- All reports must be submitted by the contractor (economic operator) to the contracting authority, which is the Ministry of Sport, through the National Coordinating Body (NCB).

- Reports must be submitted in electronic format (PDF) and uploaded to the shared project drive, with printed copies delivered only upon request in compliance with the project's sustainability practices.

- The interim report will be reviewed and approved by the contracting authority within 30 days of receipt. Feedback or requests for revision must be addressed by the contractor within 10 working days of notification.

- The final report will be reviewed and approved within 45 days of receipt, and may include a final evaluation meeting involving all key stakeholders, including municipalities, sport federations, and private sector representatives.

- Only upon approval of each report, corresponding financial disbursements or contract obligations shall be considered fulfilled. Approval is contingent on the completeness, quality, and accuracy of the reports and supporting evidence.

# MONITORING AND EVALUATION

### Definition of Indicators

Suitable and objectively quantifiable indicators will be proposed in the technical offer and agreed upon during project inception. These indicators will be tailored to the nature and scope of the European Week of Sport (EWoS IMPACT) and aligned with its objectives and deliverables.

Suitable and objectively quantifiable indicators will be proposed in the technical offer.

Indicators to be proposed in the offer will be based on required outputs and may take the nature of: descriptive indicators; performance indicators; qualitative indicators; quantitative indicators etc.:

The following indicators shall confirm the successful achievement of the project results:

-  Timely deliverables of the required technical equipment,

### Special Requirements

All monitoring and evaluation actions will follow the Communication and Visibility Manual for European Union External Actions, as outlined in the EU’s official documentation.

Contractors and economic operators must comply with the following special requirements:

- Visibility of EU Funding
All project-related communication and dissemination activities must clearly state EU financial support. This includes:

  - The EU logo

  - The project title

  - The disclaimer:

"This project is funded by the European Union."

  - Where applicable:

"The project is co-funded by the EU through the Erasmus+ Programme."

- Branding on All Materials and Events
All visibility materials (printed, digital, audio-visual) and organized events must feature appropriate EU branding and disclaimers. These materials include: posters, banners, brochures, videos, presentations, T-shirts, and giveaways.

- Media and Public Events
Any public event (e.g., community sports festivals, national opening/closing ceremonies, workshops, round tables, etc.) must clearly indicate that it is part of an EU-funded initiative. Participants, media representatives, and stakeholders must be informed that the activities are financed by the European Union.

- Coordination and Approval
Before initiating any information, communication, or visibility activity, contractors and implementing partners must contact the National Coordinating Body (NCB) for approval and guidance. The Ministry of Sport serves as the contracting authority responsible for monitoring compliance with visibility standards.

- Environmental Sustainability in Communication
All required equipment  is prefereable to be  in environmentally sustainable way—limited in quantity, digitally accessible where possible.

- Reporting and Monitoring Tools
Contractors shall use open-source tools such as Google Analytics to monitor communication outreach. Reports on reach, participation, and visibility will be included in the interim and final reports and evaluated against KPIs set out in the project plan.

Failure to comply with these requirements may result in the need to revise and re-produce materials or event deliverables at the contractor’s own expense.

* * *