Monitoring and Reporting system Just Transition Process

Monitoring and Reporting system Just Transition Process

# Stakeholder engagement

Stakeholder engagement is critical for ensuring an inclusive, transparent, and collaborative transition process. The engagement framework for the 2025 plan includes key mechanisms for effective participation.

| Stakeholder | Mechanism | Frequency | Intensity |
| --- | --- | --- | --- |
| Government entities: JTWG, JTC; TSU | Coordination meetings | Monthly | High |
| Local communities | Community consultative forums | Quarterly | Medium |
| Civil society & NGOs | Thematic roundtables | Bi-annual | Medium |
| International Partners (MDBs and DPs) | Coordination meetings | Quarterly | High |
| Private Sector | Investment Forum Sessions | Bi- annual | Medium |
| All stakeholders annual conference | Conference – AJTIP report and next AJTIP planning | Annual | Medium |

The process includes hosting an annual Stakeholder Conference as a large-scale event aimed at evaluating implementation progress, sharing success stories and lessons learned, and encouraging collaboration and partnerships.

### Proposed FreQUENCY for stakeholder reporting

| Frequency | Structure and sections in the report | Responsible party/Audience |
| --- | --- | --- |
| Monthly progress | Activities completed, Challenges encountered, Next steps, and Budget utilization | MoEMMR JTWG, |
| Quarterly stakeholder brief | Updates on key projects, Stakeholder contributions, and Investment progress | MoEMMR (to JTC) International partners JTWG JTC |
| Annual Implementation Report | Overview of achievements, Gaps identified, Financial summary, and Recommendations for the next year. | MoEMMR International partners JTC |

# Monitoring and Evaluation Framework

The Just Transition Annual implementation process adopts a monitoring and reporting mechanism to ensure accountability, tracks progress, identifies gaps, and adjusts strategies during the implementation of the Just Transition Plan. The mechanism includes:

| Components of the Mechanism | Monitoring Tools | Reporting Frequency | Responsible Entities |
| --- | --- | --- | --- |
| Data collection Regularly gather quantitative and qualitative data on key performance indicators (KPIs) | Dashboard A platform tracking real-time progress against KPIs. | Monthly progress reports supported by each working group Monthly reports Updates for use by MoEMMR, JTC and working group review. | JTWG Collect data, monitor progress, and draft monthly updates for thematic areas. for thematic area monitoring and data collection. |
| Progress monitoring Assess the status of each action area based on agreed milestones and timelines | Field visits On-site assessments to verify progress and identify implementation challenges. | Quarterly progress reports supported by each working group Quarterly reports Detailed updates submitted to the JTC. | MoEMMR Consolidates progress reports and ensures alignment with strategic goals. Compiling reports and presenting updates to the JTC and the JTWG. |
| Stakeholder feedback Collect input from communities, private sector, and institutions involved in the plan | Consultations Engage stakeholders for feedback on impact and outcomes. | Annual stakeholder review meeting Annual reports Comprehensive review for stakeholders and public dissemination. |  |
| Performance Evaluation: Compare actual results against planned targets and analyze deviations | Audit reports Third-party verification of results and financial expenditures, if existing |  |  |
| Reporting Summarize findings in structured reports for decision-making bodies. |  |  |  |

Key Performance Indicators (KPIs):

| Area | Indicator | Target 2025 | Data Source |
| --- | --- | --- | --- |
| Renewable energy | MW of constructed capacity by ESM | 30 MW | Ministry of Energy, Mining and Mineral Resources, MEPSO, ERC |
| Workforce development | Number of workers trained | 480 | ESM |
| Economic diversification | Private investment secured (€) | € 2 million | IFIs, Commercial banks, Chambers of commerce, Investment Forum, FITR, TIDZ |
| Community Inclusion | Number of low-income households supported | 1,000 | Ministry of Energy, Mining and Mineral Resources |

# VII. ReportING templates

Line of monthly reporting:

JTWG > MoEMMR > JTC

Monthly reporting template

Activity owner: ______________________________________________

| Item | Details | KPIs (if applicable) | Responsible party | Comments/Actions required |
| --- | --- | --- | --- | --- |
| Activity overview | - Summary of key objectives aligned with action plans. | A1: [KPI definition, target, actual]. | JTWG | Highlight significant deviations or achievements to ensure alignment with strategic goals. |
|  | - Overview of KPIs being tracked (e.g., A1, A2). | A2: [KPI definition, target, actual]. |  |  |
| Progress update | - Key activities undertaken this month. | N/A | JTWG > MoEMMR | Provide concise updates, including completion percentages or significant achievements. |
|  | - Major milestones reached or deliverables completed. |  |  |  |
| Challenges | - Issues encountered, such as delays, funding shortfalls, or stakeholder conflicts. | N/A | JTWG | Emphasize critical challenges needing escalation to MoEMMR for resolution. |
|  | - Risks identified. |  |  |  |
| Next steps | - Planned activities for the upcoming month. | N/A | JTWG | Include clear timelines and responsible entities for planned actions. |
|  | - Milestones or deliverables expected in the next period. |  |  |  |
| Stakeholder engagement | - Summary of stakeholders engaged (e.g., consultations, meetings, partnerships). | N/A | JTWG | Indicate how stakeholder feedback will be incorporated into subsequent activities. |
|  | - Key insights or recommendations provided by stakeholders. |  |  |  |

Line of quarterly reporting:

JTWG > MoEMMR > JTC

Quarterly progress report

| Section | Details | Responsible Party | Comments/Actions Required |
| --- | --- | --- | --- |
| Executive Summary | -High-level overview of progress and key achievements. | MoEMMR | Ensure alignment with strategic goals and communicate major wins effectively. |
|  | - Summary of critical updates since the previous quarter. |  |  |
| Progress by action area | Renewable Energy: | MoEMMR, JTWG | Add narrative analysis and highlight areas needing improvement. |
|  | - Key milestones achieved (e.g., installations, capacity added). |  |  |
|  | Workforce Development: |  |  |
|  | - Training sessions conducted. |  |  |
|  | - Beneficiaries reached. |  |  |
|  | Economic Diversification: |  |  |
|  | - Projects launched, ongoing, or completed. |  |  |
|  | - Economic impact metrics. |  |  |
| Key Performance Indicators | - Indicator (e.g., RE capacity installed, workers trained). | MoEMMR, JTC | Ensure clear visualization with graphs or charts for trends. |
|  | - Target for Quarter. |  |  |
|  | - Actual Result. |  |  |
|  | - Variance (if any). |  |  |
|  | - Comments on Variance. |  |  |
| Challenges and risks | - Description of challenges encountered (e.g., policy delays, stakeholder issues). | MoEMMR, JTC | Emphasize strategic implications and propose actionable solutions. |
|  | - Mitigation actions taken. |  |  |
|  | - Ongoing or potential risks. |  |  |
| Stakeholder feedback | - Key insights from consultations, surveys, or field visits. | JTC | Categorize feedback by stakeholder type and relevance to action areas. |
|  | - Summary of recommendations from stakeholders. |  |  |
| Financial overview | - Expenditure by action area (planned vs. actual). | MoEMMR, International Partners | Include detailed annex for financial breakdown, if required. |
|  | - Cumulative expenditure to date. |  |  |
|  | - Major deviations from budget allocations. |  |  |
| Recommendations | - Adjustments proposed for the next quarter. | All stakeholders | Highlight time-sensitive or critical recommendations for immediate consideration by decision-makers. |
|  | - Rationale for changes (e.g., aligning resources, revising targets). |  |  |

This structure will ensure clarity, facilitates quick reviews at each stage, and highlights areas requiring attention or action.

In order to better optimize the reporting process, the following activities will be developed early 2025:

- Develop standard templates for JTWG to fill out before submission to ensure uniformity.

- A dashboard or graphs for KPIs to allow quick understanding of progress and bottlenecks.

- Categorize challenges by severity to prioritize resolution efforts.

- Include a feedback loop mechanism to update stakeholders on how their input influenced plans or decisions.